## Planning KPI Input
plant_id | planning_group | business_area | period_start | period_end | wo_planned | wo_completed | manhours_planned | manhours_actual | pm_planned | pm_executed | backlog_hours | weekly_capacity_hours | corrective_count | total_wo | schedule_compliance_pct | release_horizon_days | pending_notices | total_notices | scheduled_capacity_hours | total_capacity_hours | proactive_wo | planned_wo
OCP-CON1 | P01 | SEC | 2026-01-06 | 2026-01-12 | 15 | 14 | 140.4 | 133.9 | 14 | 13 | 89 | 415 | 4 | 18 | 93.3 | 7 | 7 | 13 | 353 | 415 | 17 | 15
OCP-CON1 | P02 | RIP | 2026-01-06 | 2026-01-12 | 11 | 8 | 92 | 103.9 | 8 | 7 | 177 | 434 | 2 | 10 | 72.7 | 14 | 2 | 29 | 369 | 434 | 10 | 11
OCP-CON1 | P03 | HUM | 2026-01-06 | 2026-01-12 | 11 | 9 | 68.5 | 77.9 | 10 | 9 | 92 | 424 | 8 | 17 | 81.8 | 7 | 10 | 25 | 360 | 424 | 12 | 11
OCP-CON1 | ALL | ALL | 2026-01-06 | 2026-01-12 | 44 | 50 | 490 | 489.4 | 20 | 29 | 340 | 1041 | 12 | 67 | 81.3 | 21 | 23 | 44 | 1285 | 1064 | 35 | 47
OCP-CON1 | P01 | SEC | 2026-01-13 | 2026-01-19 | 13 | 10 | 145.1 | 164.3 | 5 | 4 | 193 | 409 | 4 | 14 | 76.9 | 7 | 5 | 25 | 348 | 409 | 5 | 13
OCP-CON1 | P02 | RIP | 2026-01-13 | 2026-01-19 | 13 | 9 | 141.9 | 150.6 | 10 | 9 | 237 | 454 | 8 | 17 | 69.2 | 7 | 10 | 20 | 386 | 454 | 11 | 13
OCP-CON1 | P03 | HUM | 2026-01-13 | 2026-01-19 | 20 | 17 | 175.5 | 194.5 | 6 | 4 | 146 | 361 | 6 | 23 | 85 | 7 | 3 | 21 | 307 | 361 | 7 | 20
OCP-CON1 | ALL | ALL | 2026-01-13 | 2026-01-19 | 52 | 54 | 320.6 | 323.5 | 31 | 16 | 832 | 1329 | 6 | 47 | 86.7 | 21 | 24 | 46 | 1300 | 1029 | 37 | 56
OCP-CON1 | P01 | SEC | 2026-01-20 | 2026-01-26 | 11 | 9 | 108.6 | 94.1 | 6 | 4 | 176 | 487 | 8 | 17 | 81.8 | 7 | 8 | 17 | 414 | 487 | 7 | 11
OCP-CON1 | P02 | RIP | 2026-01-20 | 2026-01-26 | 18 | 14 | 129.5 | 137.2 | 14 | 12 | 216 | 399 | 5 | 19 | 77.8 | 14 | 9 | 19 | 339 | 399 | 14 | 18
OCP-CON1 | P03 | HUM | 2026-01-20 | 2026-01-26 | 17 | 16 | 151.4 | 169.7 | 10 | 9 | 202 | 402 | 3 | 19 | 94.1 | 14 | 9 | 28 | 342 | 402 | 10 | 17
OCP-CON1 | ALL | ALL | 2026-01-20 | 2026-01-26 | 60 | 31 | 326.7 | 209.4 | 17 | 13 | 214 | 1217 | 10 | 49 | 76.7 | 14 | 19 | 70 | 1139 | 1184 | 36 | 58
OCP-CON1 | P01 | SEC | 2026-01-27 | 2026-02-02 | 12 | 10 | 122.7 | 112.2 | 15 | 12 | 163 | 393 | 7 | 17 | 83.3 | 21 | 2 | 10 | 334 | 393 | 13 | 12
OCP-CON1 | P02 | RIP | 2026-01-27 | 2026-02-02 | 17 | 13 | 158.9 | 153.7 | 9 | 7 | 232 | 415 | 6 | 19 | 76.5 | 14 | 10 | 27 | 353 | 415 | 8 | 17
OCP-CON1 | P03 | HUM | 2026-01-27 | 2026-02-02 | 19 | 18 | 171.5 | 186.2 | 15 | 13 | 254 | 369 | 2 | 20 | 94.7 | 14 | 4 | 17 | 314 | 369 | 15 | 19
OCP-CON1 | ALL | ALL | 2026-01-27 | 2026-02-02 | 58 | 31 | 270.9 | 436.6 | 29 | 15 | 745 | 1038 | 13 | 72 | 74.8 | 14 | 22 | 70 | 1262 | 1308 | 34 | 59
OCP-CON1 | P01 | SEC | 2026-02-03 | 2026-02-09 | 20 | 16 | 120.4 | 107.9 | 15 | 12 | 131 | 389 | 8 | 24 | 80 | 14 | 4 | 10 | 331 | 389 | 16 | 20
OCP-CON1 | P02 | RIP | 2026-02-03 | 2026-02-09 | 17 | 16 | 123.4 | 137.7 | 14 | 13 | 75 | 445 | 5 | 21 | 94.1 | 14 | 10 | 10 | 378 | 445 | 15 | 17
OCP-CON1 | P03 | HUM | 2026-02-03 | 2026-02-09 | 22 | 18 | 154.8 | 164.5 | 15 | 12 | 222 | 381 | 8 | 26 | 81.8 | 7 | 3 | 22 | 324 | 381 | 16 | 22
OCP-CON1 | ALL | ALL | 2026-02-03 | 2026-02-09 | 31 | 55 | 360 | 514 | 31 | 21 | 581 | 1326 | 15 | 55 | 86.9 | 14 | 14 | 79 | 1259 | 1005 | 37 | 40
OCP-CON1 | P01 | SEC | 2026-02-10 | 2026-02-16 | 22 | 20 | 133.2 | 150.8 | 10 | 9 | 125 | 495 | 3 | 23 | 90.9 | 14 | 3 | 24 | 421 | 495 | 11 | 22
OCP-CON1 | P02 | RIP | 2026-02-10 | 2026-02-16 | 23 | 20 | 252.2 | 242.3 | 7 | 5 | 154 | 391 | 6 | 26 | 87 | 14 | 5 | 15 | 332 | 391 | 8 | 23
OCP-CON1 | P03 | HUM | 2026-02-10 | 2026-02-16 | 23 | 21 | 221.8 | 241.2 | 15 | 12 | 115 | 469 | 6 | 27 | 91.3 | 14 | 2 | 20 | 399 | 469 | 13 | 23
OCP-CON1 | ALL | ALL | 2026-02-10 | 2026-02-16 | 58 | 31 | 410.4 | 414 | 15 | 37 | 235 | 1171 | 6 | 64 | 91.4 | 21 | 16 | 55 | 1002 | 1136 | 41 | 55
OCP-CON1 | P01 | SEC | 2026-02-17 | 2026-02-23 | 14 | 10 | 96.1 | 90.2 | 6 | 5 | 271 | 381 | 2 | 12 | 71.4 | 21 | 3 | 24 | 324 | 381 | 7 | 14
OCP-CON1 | P02 | RIP | 2026-02-17 | 2026-02-23 | 14 | 12 | 111.5 | 124.1 | 11 | 9 | 280 | 442 | 5 | 17 | 85.7 | 21 | 8 | 28 | 376 | 442 | 10 | 14
OCP-CON1 | P03 | HUM | 2026-02-17 | 2026-02-23 | 16 | 15 | 169 | 193.5 | 10 | 8 | 99 | 401 | 8 | 23 | 93.8 | 14 | 2 | 10 | 341 | 401 | 12 | 16
OCP-CON1 | ALL | ALL | 2026-02-17 | 2026-02-23 | 43 | 33 | 205.4 | 390.3 | 36 | 26 | 558 | 1025 | 17 | 70 | 93.3 | 7 | 13 | 47 | 1297 | 1497 | 36 | 52
OCP-CON1 | P01 | SEC | 2026-02-24 | 2026-03-02 | 17 | 14 | 137 | 141.9 | 12 | 9 | 105 | 489 | 7 | 21 | 82.4 | 7 | 2 | 25 | 416 | 489 | 10 | 17
OCP-CON1 | P02 | RIP | 2026-02-24 | 2026-03-02 | 18 | 16 | 184.3 | 160.9 | 9 | 7 | 193 | 458 | 7 | 23 | 88.9 | 7 | 5 | 17 | 389 | 458 | 8 | 18
OCP-CON1 | P03 | HUM | 2026-02-24 | 2026-03-02 | 21 | 19 | 144.5 | 138 | 15 | 12 | 236 | 354 | 6 | 25 | 90.5 | 14 | 7 | 16 | 301 | 354 | 14 | 21
OCP-CON1 | ALL | ALL | 2026-02-24 | 2026-03-02 | 44 | 48 | 251.9 | 232.3 | 34 | 14 | 704 | 1254 | 10 | 48 | 74.9 | 7 | 25 | 36 | 1106 | 1316 | 38 | 46
OCP-CON1 | P01 | SEC | 2026-03-03 | 2026-03-09 | 24 | 20 | 179.3 | 169.3 | 9 | 7 | 106 | 445 | 5 | 25 | 83.3 | 7 | 3 | 17 | 378 | 445 | 11 | 24
OCP-CON1 | P02 | RIP | 2026-03-03 | 2026-03-09 | 18 | 14 | 184.2 | 165.9 | 12 | 11 | 205 | 414 | 8 | 22 | 77.8 | 21 | 7 | 27 | 352 | 414 | 13 | 18
OCP-CON1 | P03 | HUM | 2026-03-03 | 2026-03-09 | 17 | 15 | 184.3 | 196.4 | 13 | 10 | 108 | 411 | 8 | 23 | 88.2 | 7 | 9 | 15 | 349 | 411 | 14 | 17
OCP-CON1 | ALL | ALL | 2026-03-03 | 2026-03-09 | 44 | 35 | 401.6 | 293.5 | 27 | 35 | 372 | 1414 | 6 | 42 | 71.8 | 7 | 20 | 60 | 1027 | 1353 | 22 | 43
OCP-CON1 | P01 | SEC | 2026-03-10 | 2026-03-16 | 14 | 12 | 143.9 | 164.6 | 13 | 12 | 254 | 363 | 3 | 15 | 85.7 | 14 | 3 | 19 | 309 | 363 | 13 | 14
OCP-CON1 | P02 | RIP | 2026-03-10 | 2026-03-16 | 15 | 14 | 178.2 | 153.5 | 11 | 9 | 258 | 355 | 5 | 19 | 93.3 | 14 | 3 | 22 | 302 | 355 | 10 | 15
OCP-CON1 | P03 | HUM | 2026-03-10 | 2026-03-16 | 15 | 14 | 175.7 | 157.3 | 10 | 9 | 155 | 492 | 8 | 22 | 93.3 | 7 | 8 | 20 | 418 | 492 | 13 | 15
OCP-CON1 | ALL | ALL | 2026-03-10 | 2026-03-16 | 47 | 55 | 367.4 | 399.5 | 17 | 28 | 533 | 1378 | 11 | 43 | 81.5 | 14 | 10 | 58 | 1050 | 1245 | 23 | 36
OCP-CON1 | P01 | SEC | 2026-03-17 | 2026-03-23 | 23 | 17 | 263.7 | 289.9 | 8 | 7 | 101 | 423 | 3 | 20 | 73.9 | 21 | 2 | 29 | 360 | 423 | 8 | 23
OCP-CON1 | P02 | RIP | 2026-03-17 | 2026-03-23 | 16 | 13 | 128.8 | 144.3 | 13 | 12 | 193 | 413 | 3 | 16 | 81.2 | 14 | 9 | 12 | 351 | 413 | 14 | 16
OCP-CON1 | P03 | HUM | 2026-03-17 | 2026-03-23 | 12 | 11 | 87.9 | 97.9 | 9 | 7 | 231 | 425 | 2 | 13 | 91.7 | 7 | 8 | 16 | 361 | 425 | 10 | 12
OCP-CON1 | ALL | ALL | 2026-03-17 | 2026-03-23 | 46 | 30 | 452.5 | 197 | 29 | 19 | 781 | 1428 | 20 | 38 | 74.4 | 7 | 11 | 36 | 1028 | 1146 | 32 | 49
OCP-CON1 | P01 | SEC | 2026-03-24 | 2026-03-30 | 22 | 18 | 244.9 | 218 | 11 | 9 | 229 | 366 | 2 | 20 | 81.8 | 21 | 2 | 10 | 311 | 366 | 13 | 22
OCP-CON1 | P02 | RIP | 2026-03-24 | 2026-03-30 | 25 | 20 | 278.4 | 245 | 6 | 5 | 184 | 436 | 3 | 23 | 80 | 14 | 2 | 10 | 371 | 436 | 8 | 25
OCP-CON1 | P03 | HUM | 2026-03-24 | 2026-03-30 | 21 | 18 | 137.6 | 145.7 | 8 | 6 | 96 | 361 | 6 | 24 | 85.7 | 7 | 10 | 24 | 307 | 361 | 7 | 21
OCP-CON1 | ALL | ALL | 2026-03-24 | 2026-03-30 | 58 | 35 | 214.1 | 285.2 | 28 | 20 | 319 | 1240 | 8 | 46 | 70.4 | 21 | 10 | 40 | 1210 | 1229 | 18 | 38
OCP-CON1 | P01 | SEC | 2026-03-31 | 2026-04-06 | 22 | 20 | 215.2 | 236.7 | 10 | 8 | 165 | 490 | 5 | 25 | 90.9 | 14 | 9 | 20 | 416 | 490 | 10 | 22
OCP-CON1 | P02 | RIP | 2026-03-31 | 2026-04-06 | 10 | 8 | 91.7 | 104.6 | 15 | 13 | 85 | 453 | 8 | 16 | 80 | 7 | 4 | 24 | 385 | 453 | 14 | 10
OCP-CON1 | P03 | HUM | 2026-03-31 | 2026-04-06 | 12 | 11 | 134.7 | 142.5 | 14 | 12 | 205 | 390 | 6 | 17 | 91.7 | 21 | 4 | 22 | 332 | 390 | 14 | 12
OCP-CON1 | ALL | ALL | 2026-03-31 | 2026-04-06 | 37 | 31 | 325.7 | 425.1 | 32 | 33 | 478 | 1079 | 9 | 41 | 91.5 | 14 | 14 | 71 | 1237 | 1427 | 15 | 37
OCP-CON1 | P01 | SEC | 2026-04-07 | 2026-04-13 | 21 | 17 | 151 | 158.6 | 13 | 12 | 293 | 482 | 6 | 23 | 81 | 7 | 3 | 26 | 410 | 482 | 13 | 21
OCP-CON1 | P02 | RIP | 2026-04-07 | 2026-04-13 | 12 | 10 | 111.4 | 114.2 | 7 | 6 | 103 | 355 | 8 | 18 | 83.3 | 21 | 2 | 13 | 302 | 355 | 8 | 12
OCP-CON1 | P03 | HUM | 2026-04-07 | 2026-04-13 | 16 | 12 | 104.4 | 106.8 | 8 | 7 | 120 | 379 | 5 | 17 | 75 | 7 | 9 | 30 | 322 | 379 | 11 | 16
OCP-CON1 | ALL | ALL | 2026-04-07 | 2026-04-13 | 38 | 37 | 298.5 | 519 | 25 | 20 | 825 | 1461 | 13 | 73 | 90.1 | 7 | 25 | 44 | 1068 | 1041 | 24 | 46
OCP-CON1 | P01 | SEC | 2026-04-14 | 2026-04-20 | 18 | 16 | 140.4 | 151.9 | 15 | 13 | 169 | 469 | 2 | 18 | 88.9 | 7 | 6 | 17 | 399 | 469 | 16 | 18
OCP-CON1 | P02 | RIP | 2026-04-14 | 2026-04-20 | 13 | 12 | 112.1 | 123.5 | 13 | 12 | 161 | 486 | 8 | 20 | 92.3 | 21 | 6 | 17 | 413 | 486 | 15 | 13
OCP-CON1 | P03 | HUM | 2026-04-14 | 2026-04-20 | 12 | 10 | 111.7 | 111.5 | 8 | 7 | 111 | 487 | 7 | 17 | 83.3 | 7 | 5 | 22 | 414 | 487 | 10 | 12
OCP-CON1 | ALL | ALL | 2026-04-14 | 2026-04-20 | 57 | 37 | 249.9 | 298.1 | 22 | 13 | 287 | 1080 | 11 | 48 | 80.8 | 14 | 13 | 74 | 960 | 1298 | 25 | 41
OCP-CON1 | P01 | SEC | 2026-04-21 | 2026-04-27 | 14 | 10 | 87.6 | 82.6 | 5 | 4 | 213 | 394 | 3 | 13 | 71.4 | 21 | 2 | 12 | 335 | 394 | 5 | 14
OCP-CON1 | P02 | RIP | 2026-04-21 | 2026-04-27 | 19 | 16 | 122.6 | 117.8 | 12 | 10 | 103 | 469 | 3 | 19 | 84.2 | 14 | 2 | 14 | 399 | 469 | 13 | 19
OCP-CON1 | P03 | HUM | 2026-04-21 | 2026-04-27 | 25 | 23 | 180.6 | 159.6 | 13 | 12 | 278 | 368 | 4 | 27 | 92 | 21 | 9 | 10 | 313 | 368 | 16 | 25
OCP-CON1 | ALL | ALL | 2026-04-21 | 2026-04-27 | 46 | 53 | 351.5 | 226.9 | 17 | 18 | 889 | 1342 | 7 | 49 | 89.7 | 21 | 9 | 57 | 1034 | 1366 | 20 | 52
OCP-CON1 | P01 | SEC | 2026-04-28 | 2026-05-04 | 16 | 12 | 165.1 | 159.8 | 5 | 4 | 261 | 500 | 6 | 18 | 75 | 14 | 5 | 19 | 425 | 500 | 8 | 16
OCP-CON1 | P02 | RIP | 2026-04-28 | 2026-05-04 | 10 | 9 | 112.4 | 120.9 | 13 | 10 | 298 | 496 | 4 | 13 | 90 | 14 | 10 | 17 | 422 | 496 | 13 | 10
OCP-CON1 | P03 | HUM | 2026-04-28 | 2026-05-04 | 24 | 19 | 194.7 | 192.8 | 13 | 11 | 133 | 424 | 6 | 25 | 79.2 | 14 | 6 | 20 | 360 | 424 | 12 | 24
OCP-CON1 | ALL | ALL | 2026-04-28 | 2026-05-04 | 40 | 55 | 321.5 | 209 | 31 | 22 | 621 | 1162 | 6 | 55 | 78.6 | 21 | 25 | 36 | 1046 | 1312 | 44 | 39
OCP-CON1 | P01 | SEC | 2026-05-05 | 2026-05-11 | 25 | 22 | 217.2 | 205.1 | 13 | 11 | 71 | 449 | 4 | 26 | 88 | 7 | 7 | 26 | 382 | 449 | 13 | 25
OCP-CON1 | P02 | RIP | 2026-05-05 | 2026-05-11 | 11 | 10 | 93.9 | 105.5 | 10 | 8 | 231 | 405 | 3 | 13 | 90.9 | 7 | 7 | 26 | 344 | 405 | 10 | 11
OCP-CON1 | P03 | HUM | 2026-05-05 | 2026-05-11 | 11 | 8 | 90.4 | 82.8 | 9 | 8 | 222 | 423 | 8 | 16 | 72.7 | 21 | 3 | 16 | 360 | 423 | 12 | 11
OCP-CON1 | ALL | ALL | 2026-05-05 | 2026-05-11 | 48 | 51 | 267.1 | 236.3 | 18 | 32 | 592 | 1423 | 7 | 64 | 87.5 | 14 | 20 | 56 | 1207 | 1051 | 22 | 31
OCP-CON1 | P01 | SEC | 2026-05-12 | 2026-05-18 | 16 | 15 | 129.4 | 125.1 | 7 | 6 | 69 | 470 | 3 | 18 | 93.8 | 7 | 7 | 30 | 400 | 470 | 10 | 16
OCP-CON1 | P02 | RIP | 2026-05-12 | 2026-05-18 | 16 | 12 | 117.8 | 107 | 14 | 11 | 163 | 477 | 8 | 20 | 75 | 21 | 2 | 13 | 405 | 477 | 15 | 16
OCP-CON1 | P03 | HUM | 2026-05-12 | 2026-05-18 | 15 | 12 | 176 | 173.8 | 6 | 5 | 90 | 411 | 7 | 19 | 80 | 14 | 3 | 17 | 349 | 411 | 9 | 15
OCP-CON1 | ALL | ALL | 2026-05-12 | 2026-05-18 | 56 | 50 | 393.4 | 368.1 | 32 | 33 | 584 | 1396 | 12 | 68 | 83.7 | 21 | 9 | 52 | 901 | 1283 | 36 | 49
OCP-CON1 | P01 | SEC | 2026-05-19 | 2026-05-25 | 21 | 19 | 223.2 | 232.8 | 13 | 12 | 212 | 442 | 4 | 23 | 90.5 | 21 | 9 | 15 | 376 | 442 | 15 | 21
OCP-CON1 | P02 | RIP | 2026-05-19 | 2026-05-25 | 23 | 18 | 159.9 | 183.4 | 5 | 4 | 292 | 487 | 4 | 22 | 78.3 | 7 | 4 | 28 | 414 | 487 | 5 | 23
OCP-CON1 | P03 | HUM | 2026-05-19 | 2026-05-25 | 12 | 10 | 87.9 | 79.8 | 12 | 11 | 157 | 386 | 5 | 15 | 83.3 | 21 | 2 | 28 | 328 | 386 | 14 | 12
OCP-CON1 | ALL | ALL | 2026-05-19 | 2026-05-25 | 37 | 40 | 226.3 | 419.4 | 28 | 34 | 461 | 1486 | 14 | 55 | 71.3 | 7 | 10 | 40 | 1024 | 1448 | 21 | 45
OCP-CON1 | P01 | SEC | 2026-05-26 | 2026-06-01 | 15 | 12 | 155.2 | 163.9 | 11 | 8 | 118 | 470 | 3 | 15 | 80 | 7 | 5 | 27 | 400 | 470 | 9 | 15
OCP-CON1 | P02 | RIP | 2026-05-26 | 2026-06-01 | 17 | 14 | 150.6 | 152.6 | 12 | 11 | 150 | 457 | 4 | 18 | 82.4 | 7 | 10 | 14 | 388 | 457 | 13 | 17
OCP-CON1 | P03 | HUM | 2026-05-26 | 2026-06-01 | 16 | 13 | 160.4 | 151.3 | 14 | 11 | 117 | 449 | 4 | 17 | 81.2 | 7 | 10 | 11 | 382 | 449 | 12 | 16
OCP-CON1 | ALL | ALL | 2026-05-26 | 2026-06-01 | 35 | 42 | 259.1 | 222.9 | 18 | 32 | 293 | 1410 | 15 | 66 | 78.3 | 21 | 15 | 78 | 1058 | 1179 | 23 | 38
OCP-CON1 | P01 | SEC | 2026-06-02 | 2026-06-08 | 11 | 9 | 119.8 | 103.1 | 13 | 12 | 115 | 443 | 4 | 13 | 81.8 | 7 | 3 | 29 | 377 | 443 | 14 | 11
OCP-CON1 | P02 | RIP | 2026-06-02 | 2026-06-08 | 25 | 18 | 199.8 | 178.7 | 5 | 4 | 218 | 444 | 4 | 22 | 72 | 7 | 9 | 25 | 377 | 444 | 5 | 25
OCP-CON1 | P03 | HUM | 2026-06-02 | 2026-06-08 | 18 | 16 | 157.8 | 140.7 | 8 | 6 | 238 | 428 | 2 | 18 | 88.9 | 7 | 4 | 14 | 364 | 428 | 7 | 18
OCP-CON1 | ALL | ALL | 2026-06-02 | 2026-06-08 | 39 | 40 | 464.6 | 250.4 | 26 | 37 | 431 | 1329 | 15 | 37 | 94.5 | 14 | 17 | 53 | 1195 | 1372 | 24 | 43
OCP-CON1 | P01 | SEC | 2026-06-09 | 2026-06-15 | 12 | 9 | 89.9 | 92.6 | 13 | 10 | 299 | 476 | 7 | 16 | 75 | 21 | 6 | 23 | 405 | 476 | 13 | 12
OCP-CON1 | P02 | RIP | 2026-06-09 | 2026-06-15 | 22 | 21 | 249.5 | 244.4 | 5 | 4 | 277 | 409 | 4 | 25 | 95.5 | 14 | 6 | 15 | 348 | 409 | 8 | 22
OCP-CON1 | P03 | HUM | 2026-06-09 | 2026-06-15 | 21 | 16 | 208.7 | 238 | 15 | 12 | 143 | 492 | 6 | 22 | 76.2 | 7 | 6 | 20 | 418 | 492 | 14 | 21
OCP-CON1 | ALL | ALL | 2026-06-09 | 2026-06-15 | 49 | 32 | 283 | 254.2 | 39 | 20 | 675 | 1000 | 7 | 36 | 84.6 | 7 | 25 | 75 | 1018 | 1085 | 17 | 59
OCP-CON1 | P01 | SEC | 2026-06-16 | 2026-06-22 | 20 | 16 | 185.5 | 207.5 | 9 | 8 | 268 | 403 | 5 | 21 | 80 | 21 | 6 | 18 | 343 | 403 | 9 | 20
OCP-CON1 | P02 | RIP | 2026-06-16 | 2026-06-22 | 11 | 10 | 89.7 | 83.3 | 8 | 7 | 214 | 356 | 6 | 16 | 90.9 | 7 | 2 | 14 | 303 | 356 | 9 | 11
OCP-CON1 | P03 | HUM | 2026-06-16 | 2026-06-22 | 18 | 16 | 186.8 | 192.1 | 12 | 11 | 279 | 476 | 8 | 24 | 88.9 | 7 | 8 | 12 | 405 | 476 | 13 | 18
OCP-CON1 | ALL | ALL | 2026-06-16 | 2026-06-22 | 37 | 37 | 316.9 | 316.9 | 32 | 16 | 279 | 1075 | 18 | 51 | 72.3 | 7 | 23 | 74 | 1241 | 1330 | 22 | 38
OCP-CON1 | P01 | SEC | 2026-06-23 | 2026-06-29 | 20 | 15 | 187.1 | 199.8 | 12 | 9 | 92 | 444 | 6 | 21 | 75 | 14 | 5 | 21 | 377 | 444 | 11 | 20
OCP-CON1 | P02 | RIP | 2026-06-23 | 2026-06-29 | 21 | 17 | 173.9 | 155 | 12 | 10 | 72 | 407 | 4 | 21 | 81 | 21 | 10 | 27 | 346 | 407 | 13 | 21
OCP-CON1 | P03 | HUM | 2026-06-23 | 2026-06-29 | 11 | 8 | 75.9 | 67 | 6 | 4 | 106 | 385 | 8 | 16 | 72.7 | 7 | 8 | 24 | 327 | 385 | 6 | 11
OCP-CON1 | ALL | ALL | 2026-06-23 | 2026-06-29 | 46 | 43 | 205 | 412.7 | 22 | 31 | 573 | 1493 | 8 | 70 | 83.6 | 7 | 17 | 73 | 1026 | 1343 | 41 | 60
OCP-CON1 | P01 | SEC | 2026-06-30 | 2026-07-06 | 25 | 21 | 154.7 | 159.8 | 8 | 6 | 193 | 453 | 5 | 26 | 84 | 21 | 5 | 20 | 385 | 453 | 7 | 25
OCP-CON1 | P02 | RIP | 2026-06-30 | 2026-07-06 | 20 | 19 | 176 | 157 | 12 | 10 | 258 | 405 | 3 | 22 | 95 | 21 | 7 | 14 | 344 | 405 | 14 | 20
OCP-CON1 | P03 | HUM | 2026-06-30 | 2026-07-06 | 14 | 12 | 149.7 | 169.7 | 10 | 9 | 202 | 454 | 6 | 18 | 85.7 | 14 | 7 | 22 | 386 | 454 | 11 | 14
OCP-CON1 | ALL | ALL | 2026-06-30 | 2026-07-06 | 35 | 44 | 285.5 | 514.3 | 40 | 25 | 366 | 1158 | 10 | 59 | 88.3 | 21 | 19 | 59 | 1156 | 1060 | 32 | 41
OCP-CON1 | P01 | SEC | 2026-07-07 | 2026-07-13 | 18 | 15 | 179.9 | 158.2 | 12 | 10 | 259 | 497 | 6 | 21 | 83.3 | 14 | 4 | 28 | 422 | 497 | 13 | 18
OCP-CON1 | P02 | RIP | 2026-07-07 | 2026-07-13 | 11 | 10 | 129.2 | 137.9 | 10 | 9 | 168 | 382 | 6 | 16 | 90.9 | 21 | 3 | 21 | 325 | 382 | 13 | 11
OCP-CON1 | P03 | HUM | 2026-07-07 | 2026-07-13 | 16 | 14 | 96.3 | 102.2 | 11 | 8 | 186 | 426 | 5 | 19 | 87.5 | 21 | 2 | 22 | 362 | 426 | 12 | 16
OCP-CON1 | ALL | ALL | 2026-07-07 | 2026-07-13 | 42 | 28 | 314 | 325.2 | 16 | 31 | 678 | 1063 | 12 | 40 | 76.6 | 14 | 12 | 34 | 1113 | 1242 | 34 | 43
OCP-CON1 | P01 | SEC | 2026-07-14 | 2026-07-20 | 20 | 17 | 198.7 | 198.8 | 14 | 11 | 201 | 392 | 2 | 19 | 85 | 21 | 9 | 14 | 333 | 392 | 15 | 20
OCP-CON1 | P02 | RIP | 2026-07-14 | 2026-07-20 | 13 | 10 | 148 | 149.7 | 14 | 11 | 96 | 411 | 6 | 16 | 76.9 | 7 | 5 | 22 | 349 | 411 | 13 | 13
OCP-CON1 | P03 | HUM | 2026-07-14 | 2026-07-20 | 18 | 15 | 204.4 | 193.9 | 9 | 7 | 85 | 377 | 2 | 17 | 83.3 | 21 | 5 | 16 | 320 | 377 | 9 | 18
OCP-CON1 | ALL | ALL | 2026-07-14 | 2026-07-20 | 60 | 50 | 422.8 | 487.2 | 34 | 20 | 332 | 1213 | 19 | 46 | 77.6 | 21 | 9 | 49 | 947 | 1273 | 26 | 43
OCP-CON1 | P01 | SEC | 2026-07-21 | 2026-07-27 | 17 | 16 | 179.4 | 161.3 | 9 | 8 | 220 | 389 | 7 | 23 | 94.1 | 14 | 8 | 14 | 331 | 389 | 9 | 17
OCP-CON1 | P02 | RIP | 2026-07-21 | 2026-07-27 | 13 | 11 | 148.7 | 168.2 | 5 | 4 | 253 | 400 | 5 | 16 | 84.6 | 21 | 3 | 14 | 340 | 400 | 5 | 13
OCP-CON1 | P03 | HUM | 2026-07-21 | 2026-07-27 | 17 | 13 | 172.8 | 158.6 | 9 | 7 | 134 | 489 | 5 | 18 | 76.5 | 7 | 7 | 14 | 416 | 489 | 10 | 17
OCP-CON1 | ALL | ALL | 2026-07-21 | 2026-07-27 | 34 | 37 | 259.8 | 515.1 | 18 | 36 | 435 | 1454 | 11 | 68 | 83.7 | 21 | 18 | 41 | 1075 | 1057 | 22 | 47
OCP-CON1 | P01 | SEC | 2026-07-28 | 2026-08-03 | 21 | 19 | 193.5 | 185.9 | 7 | 6 | 209 | 487 | 4 | 23 | 90.5 | 21 | 8 | 17 | 414 | 487 | 9 | 21
OCP-CON1 | P02 | RIP | 2026-07-28 | 2026-08-03 | 11 | 9 | 71.3 | 77.7 | 14 | 13 | 283 | 388 | 8 | 17 | 81.8 | 14 | 7 | 22 | 330 | 388 | 17 | 11
OCP-CON1 | P03 | HUM | 2026-07-28 | 2026-08-03 | 17 | 14 | 120.7 | 119.3 | 13 | 12 | 81 | 389 | 2 | 16 | 82.4 | 21 | 3 | 23 | 331 | 389 | 14 | 17
OCP-CON1 | ALL | ALL | 2026-07-28 | 2026-08-03 | 54 | 29 | 277.7 | 198.1 | 40 | 16 | 565 | 1189 | 16 | 44 | 90 | 7 | 10 | 36 | 1258 | 1354 | 26 | 45
OCP-CON1 | P01 | SEC | 2026-08-04 | 2026-08-10 | 11 | 9 | 78.2 | 68.7 | 15 | 14 | 159 | 432 | 3 | 12 | 81.8 | 7 | 3 | 12 | 367 | 432 | 17 | 11
OCP-CON1 | P02 | RIP | 2026-08-04 | 2026-08-10 | 20 | 15 | 149.7 | 158 | 6 | 5 | 152 | 455 | 7 | 22 | 75 | 21 | 7 | 29 | 387 | 455 | 8 | 20
OCP-CON1 | P03 | HUM | 2026-08-04 | 2026-08-10 | 19 | 14 | 224 | 250.5 | 11 | 10 | 229 | 403 | 4 | 18 | 73.7 | 14 | 3 | 26 | 343 | 403 | 14 | 19
OCP-CON1 | ALL | ALL | 2026-08-04 | 2026-08-10 | 55 | 41 | 435.4 | 453.6 | 38 | 31 | 243 | 1119 | 14 | 69 | 80.3 | 14 | 8 | 58 | 1128 | 1418 | 38 | 54
OCP-CON1 | P01 | SEC | 2026-08-11 | 2026-08-17 | 21 | 16 | 193.2 | 219.9 | 7 | 6 | 248 | 492 | 2 | 18 | 76.2 | 7 | 3 | 21 | 418 | 492 | 10 | 21
OCP-CON1 | P02 | RIP | 2026-08-11 | 2026-08-17 | 10 | 9 | 110.6 | 105.2 | 12 | 11 | 131 | 398 | 6 | 15 | 90 | 7 | 7 | 17 | 338 | 398 | 15 | 10
OCP-CON1 | P03 | HUM | 2026-08-11 | 2026-08-17 | 13 | 11 | 100 | 113.7 | 6 | 5 | 260 | 429 | 6 | 17 | 84.6 | 21 | 5 | 22 | 365 | 429 | 6 | 13
OCP-CON1 | ALL | ALL | 2026-08-11 | 2026-08-17 | 32 | 52 | 257.7 | 367.8 | 15 | 36 | 656 | 1438 | 12 | 40 | 95 | 14 | 8 | 52 | 1043 | 1191 | 42 | 32
OCP-CON1 | P01 | SEC | 2026-08-18 | 2026-08-24 | 10 | 8 | 119.7 | 116.8 | 10 | 9 | 117 | 394 | 4 | 12 | 80 | 21 | 9 | 26 | 335 | 394 | 13 | 10
OCP-CON1 | P02 | RIP | 2026-08-18 | 2026-08-24 | 23 | 17 | 210.9 | 207.1 | 14 | 13 | 73 | 416 | 3 | 20 | 73.9 | 21 | 2 | 29 | 354 | 416 | 17 | 23
OCP-CON1 | P03 | HUM | 2026-08-18 | 2026-08-24 | 13 | 12 | 137.3 | 122.9 | 14 | 13 | 296 | 410 | 5 | 17 | 92.3 | 14 | 3 | 12 | 348 | 410 | 15 | 13
OCP-CON1 | ALL | ALL | 2026-08-18 | 2026-08-24 | 42 | 37 | 401.8 | 281.7 | 36 | 18 | 538 | 1187 | 12 | 45 | 78.1 | 7 | 25 | 77 | 1160 | 1388 | 20 | 59
OCP-CON1 | P01 | SEC | 2026-08-25 | 2026-08-31 | 14 | 11 | 155.9 | 163.1 | 12 | 10 | 147 | 366 | 8 | 19 | 78.6 | 21 | 6 | 15 | 311 | 366 | 12 | 14
OCP-CON1 | P02 | RIP | 2026-08-25 | 2026-08-31 | 14 | 11 | 128.8 | 141.9 | 8 | 7 | 75 | 391 | 4 | 15 | 78.6 | 7 | 3 | 28 | 332 | 391 | 10 | 14
OCP-CON1 | P03 | HUM | 2026-08-25 | 2026-08-31 | 24 | 22 | 260 | 247.2 | 6 | 5 | 199 | 453 | 8 | 30 | 91.7 | 14 | 6 | 13 | 385 | 453 | 8 | 24
OCP-CON1 | ALL | ALL | 2026-08-25 | 2026-08-31 | 42 | 48 | 423.3 | 424.8 | 25 | 14 | 588 | 1177 | 11 | 42 | 71.5 | 7 | 19 | 80 | 1000 | 1197 | 32 | 45
OCP-CON1 | P01 | SEC | 2026-09-01 | 2026-09-07 | 12 | 10 | 87.2 | 76.9 | 13 | 12 | 132 | 364 | 7 | 17 | 83.3 | 14 | 7 | 15 | 309 | 364 | 15 | 12
OCP-CON1 | P02 | RIP | 2026-09-01 | 2026-09-07 | 21 | 16 | 178.5 | 166.5 | 6 | 5 | 153 | 442 | 6 | 22 | 76.2 | 21 | 7 | 13 | 376 | 442 | 8 | 21
OCP-CON1 | P03 | HUM | 2026-09-01 | 2026-09-07 | 17 | 14 | 112.1 | 128.9 | 9 | 8 | 243 | 482 | 2 | 16 | 82.4 | 14 | 3 | 20 | 410 | 482 | 9 | 17
OCP-CON1 | ALL | ALL | 2026-09-01 | 2026-09-07 | 58 | 26 | 218.4 | 354 | 37 | 12 | 418 | 1061 | 19 | 38 | 88.9 | 21 | 13 | 74 | 917 | 1339 | 41 | 60
OCP-CON1 | P01 | SEC | 2026-09-08 | 2026-09-14 | 10 | 9 | 73.8 | 80.2 | 9 | 7 | 62 | 474 | 5 | 14 | 90 | 7 | 5 | 22 | 403 | 474 | 8 | 10
OCP-CON1 | P02 | RIP | 2026-09-08 | 2026-09-14 | 22 | 20 | 136.8 | 143.6 | 14 | 12 | 236 | 475 | 3 | 23 | 90.9 | 7 | 8 | 10 | 404 | 475 | 14 | 22
OCP-CON1 | P03 | HUM | 2026-09-08 | 2026-09-14 | 25 | 19 | 293.4 | 291.5 | 8 | 7 | 89 | 446 | 7 | 26 | 76 | 14 | 2 | 13 | 379 | 446 | 11 | 25
OCP-CON1 | ALL | ALL | 2026-09-08 | 2026-09-14 | 46 | 47 | 424.2 | 356.5 | 40 | 23 | 457 | 1186 | 6 | 36 | 83.3 | 21 | 15 | 48 | 977 | 1366 | 32 | 47
OCP-CON1 | P01 | SEC | 2026-09-15 | 2026-09-21 | 19 | 15 | 197.9 | 183.3 | 15 | 13 | 274 | 445 | 3 | 18 | 78.9 | 14 | 3 | 15 | 378 | 445 | 17 | 19
OCP-CON1 | P02 | RIP | 2026-09-15 | 2026-09-21 | 19 | 14 | 211.7 | 201.1 | 7 | 6 | 74 | 378 | 5 | 19 | 73.7 | 21 | 8 | 30 | 321 | 378 | 8 | 19
OCP-CON1 | P03 | HUM | 2026-09-15 | 2026-09-21 | 17 | 15 | 114.4 | 105.1 | 11 | 9 | 119 | 457 | 3 | 18 | 88.2 | 14 | 3 | 16 | 388 | 457 | 11 | 17
OCP-CON1 | ALL | ALL | 2026-09-15 | 2026-09-21 | 58 | 26 | 228.9 | 353.6 | 28 | 29 | 272 | 1003 | 6 | 64 | 92 | 21 | 14 | 66 | 909 | 1457 | 35 | 53
OCP-CON1 | P01 | SEC | 2026-09-22 | 2026-09-28 | 22 | 19 | 211.7 | 207.1 | 12 | 10 | 124 | 396 | 2 | 21 | 86.4 | 7 | 8 | 13 | 337 | 396 | 13 | 22
OCP-CON1 | P02 | RIP | 2026-09-22 | 2026-09-28 | 10 | 8 | 77.1 | 68.7 | 15 | 13 | 260 | 395 | 6 | 14 | 80 | 7 | 7 | 15 | 336 | 395 | 14 | 10
OCP-CON1 | P03 | HUM | 2026-09-22 | 2026-09-28 | 15 | 11 | 104.3 | 89.3 | 14 | 13 | 171 | 494 | 6 | 17 | 73.3 | 7 | 8 | 11 | 420 | 494 | 15 | 15
OCP-CON1 | ALL | ALL | 2026-09-22 | 2026-09-28 | 44 | 39 | 222.4 | 235.7 | 16 | 32 | 483 | 1242 | 20 | 64 | 76.5 | 14 | 14 | 47 | 1231 | 1240 | 19 | 32
OCP-CON1 | P01 | SEC | 2026-09-29 | 2026-10-05 | 17 | 14 | 175 | 157.3 | 11 | 10 | 153 | 486 | 6 | 20 | 82.4 | 7 | 2 | 14 | 413 | 486 | 12 | 17
OCP-CON1 | P02 | RIP | 2026-09-29 | 2026-10-05 | 20 | 17 | 200.3 | 194.6 | 11 | 9 | 132 | 486 | 8 | 25 | 85 | 14 | 4 | 17 | 413 | 486 | 13 | 20
OCP-CON1 | P03 | HUM | 2026-09-29 | 2026-10-05 | 16 | 14 | 155.5 | 139.3 | 12 | 11 | 104 | 392 | 4 | 18 | 87.5 | 21 | 10 | 14 | 333 | 392 | 12 | 16
OCP-CON1 | ALL | ALL | 2026-09-29 | 2026-10-05 | 58 | 54 | 307.3 | 434.3 | 40 | 32 | 340 | 1233 | 13 | 59 | 86.2 | 14 | 21 | 36 | 1114 | 1138 | 43 | 39
OCP-CON1 | P01 | SEC | 2026-10-06 | 2026-10-12 | 20 | 18 | 173.9 | 150 | 13 | 12 | 83 | 493 | 3 | 21 | 90 | 7 | 3 | 17 | 419 | 493 | 14 | 20
OCP-CON1 | P02 | RIP | 2026-10-06 | 2026-10-12 | 22 | 18 | 243.5 | 235.1 | 5 | 4 | 131 | 404 | 2 | 20 | 81.8 | 7 | 3 | 12 | 343 | 404 | 7 | 22
OCP-CON1 | P03 | HUM | 2026-10-06 | 2026-10-12 | 17 | 16 | 107.3 | 107.7 | 13 | 12 | 73 | 466 | 5 | 21 | 94.1 | 21 | 6 | 11 | 396 | 466 | 14 | 17
OCP-CON1 | ALL | ALL | 2026-10-06 | 2026-10-12 | 30 | 43 | 304.9 | 382 | 35 | 36 | 424 | 1065 | 20 | 73 | 86 | 7 | 25 | 37 | 1070 | 1155 | 45 | 52
OCP-CON1 | P01 | SEC | 2026-10-13 | 2026-10-19 | 20 | 18 | 129.6 | 144.8 | 10 | 8 | 64 | 474 | 4 | 22 | 90 | 14 | 3 | 25 | 403 | 474 | 11 | 20
OCP-CON1 | P02 | RIP | 2026-10-13 | 2026-10-19 | 19 | 14 | 204.7 | 197.4 | 11 | 10 | 148 | 457 | 2 | 16 | 73.7 | 21 | 5 | 20 | 388 | 457 | 13 | 19
OCP-CON1 | P03 | HUM | 2026-10-13 | 2026-10-19 | 13 | 10 | 128.8 | 117.1 | 5 | 4 | 144 | 500 | 2 | 12 | 76.9 | 7 | 8 | 11 | 425 | 500 | 6 | 13
OCP-CON1 | ALL | ALL | 2026-10-13 | 2026-10-19 | 49 | 41 | 366.6 | 300.1 | 32 | 13 | 359 | 1206 | 11 | 75 | 82.2 | 21 | 12 | 71 | 1211 | 1269 | 40 | 46
OCP-CON1 | P01 | SEC | 2026-10-20 | 2026-10-26 | 15 | 13 | 126.7 | 136.4 | 12 | 10 | 153 | 374 | 7 | 20 | 86.7 | 7 | 3 | 30 | 318 | 374 | 14 | 15
OCP-CON1 | P02 | RIP | 2026-10-20 | 2026-10-26 | 17 | 14 | 116.8 | 115 | 11 | 9 | 64 | 357 | 6 | 20 | 82.4 | 14 | 3 | 22 | 303 | 357 | 13 | 17
OCP-CON1 | P03 | HUM | 2026-10-20 | 2026-10-26 | 18 | 15 | 169.9 | 161.5 | 14 | 11 | 270 | 374 | 7 | 22 | 83.3 | 14 | 2 | 17 | 318 | 374 | 14 | 18
OCP-CON1 | ALL | ALL | 2026-10-20 | 2026-10-26 | 34 | 54 | 209.5 | 222.2 | 20 | 23 | 417 | 1069 | 9 | 39 | 80.6 | 7 | 11 | 37 | 1214 | 1177 | 44 | 58
OCP-CON1 | P01 | SEC | 2026-10-27 | 2026-11-02 | 24 | 18 | 183.3 | 174.6 | 13 | 11 | 128 | 396 | 2 | 20 | 75 | 21 | 6 | 27 | 337 | 396 | 14 | 24
OCP-CON1 | P02 | RIP | 2026-10-27 | 2026-11-02 | 13 | 11 | 129.2 | 119.5 | 12 | 10 | 297 | 459 | 5 | 16 | 84.6 | 14 | 9 | 21 | 390 | 459 | 11 | 13
OCP-CON1 | P03 | HUM | 2026-10-27 | 2026-11-02 | 18 | 13 | 207.2 | 213.9 | 13 | 11 | 260 | 434 | 4 | 17 | 72.2 | 7 | 10 | 28 | 369 | 434 | 14 | 18
OCP-CON1 | ALL | ALL | 2026-10-27 | 2026-11-02 | 60 | 43 | 371.9 | 317.3 | 20 | 17 | 497 | 1044 | 8 | 57 | 87 | 7 | 21 | 55 | 1081 | 1491 | 17 | 34
OCP-CON1 | P01 | SEC | 2026-11-03 | 2026-11-09 | 10 | 8 | 84.6 | 72.8 | 11 | 9 | 158 | 452 | 5 | 13 | 80 | 7 | 10 | 12 | 384 | 452 | 12 | 10
OCP-CON1 | P02 | RIP | 2026-11-03 | 2026-11-09 | 14 | 13 | 158.5 | 172.1 | 7 | 6 | 168 | 417 | 7 | 20 | 92.9 | 14 | 2 | 10 | 354 | 417 | 8 | 14
OCP-CON1 | P03 | HUM | 2026-11-03 | 2026-11-09 | 22 | 19 | 229.1 | 262.4 | 15 | 12 | 292 | 440 | 2 | 21 | 86.4 | 14 | 5 | 28 | 374 | 440 | 13 | 22
OCP-CON1 | ALL | ALL | 2026-11-03 | 2026-11-09 | 57 | 34 | 276.6 | 208.2 | 27 | 29 | 752 | 1242 | 12 | 68 | 81.7 | 7 | 15 | 59 | 1187 | 1243 | 29 | 48
OCP-CON1 | P01 | SEC | 2026-11-10 | 2026-11-16 | 20 | 15 | 148.8 | 160.4 | 13 | 12 | 88 | 353 | 3 | 18 | 75 | 14 | 4 | 14 | 300 | 353 | 14 | 20
OCP-CON1 | P02 | RIP | 2026-11-10 | 2026-11-16 | 18 | 13 | 128.5 | 137 | 7 | 6 | 98 | 436 | 2 | 15 | 72.2 | 7 | 5 | 26 | 371 | 436 | 10 | 18
OCP-CON1 | P03 | HUM | 2026-11-10 | 2026-11-16 | 12 | 9 | 120 | 130.6 | 14 | 13 | 89 | 409 | 7 | 16 | 75 | 7 | 10 | 18 | 348 | 409 | 14 | 12
OCP-CON1 | ALL | ALL | 2026-11-10 | 2026-11-16 | 31 | 47 | 470.8 | 296.6 | 23 | 24 | 867 | 1456 | 11 | 49 | 79.6 | 7 | 18 | 40 | 1085 | 1217 | 23 | 45
OCP-CON1 | P01 | SEC | 2026-11-17 | 2026-11-23 | 13 | 10 | 117.6 | 101.9 | 8 | 6 | 268 | 463 | 3 | 13 | 76.9 | 7 | 7 | 25 | 394 | 463 | 9 | 13
OCP-CON1 | P02 | RIP | 2026-11-17 | 2026-11-23 | 17 | 14 | 111.3 | 121.3 | 6 | 5 | 160 | 413 | 8 | 22 | 82.4 | 14 | 2 | 13 | 351 | 413 | 7 | 17
OCP-CON1 | P03 | HUM | 2026-11-17 | 2026-11-23 | 23 | 21 | 148.2 | 152.5 | 10 | 8 | 210 | 431 | 3 | 24 | 91.3 | 21 | 6 | 18 | 366 | 431 | 12 | 23
OCP-CON1 | ALL | ALL | 2026-11-17 | 2026-11-23 | 60 | 30 | 343.6 | 410.2 | 17 | 19 | 284 | 1326 | 10 | 66 | 93.7 | 21 | 16 | 52 | 1178 | 1017 | 40 | 49
OCP-CON1 | P01 | SEC | 2026-11-24 | 2026-11-30 | 13 | 9 | 147.5 | 127.8 | 10 | 9 | 256 | 410 | 6 | 15 | 69.2 | 21 | 10 | 19 | 348 | 410 | 13 | 13
OCP-CON1 | P02 | RIP | 2026-11-24 | 2026-11-30 | 16 | 14 | 178.7 | 202.1 | 12 | 11 | 160 | 413 | 2 | 16 | 87.5 | 7 | 2 | 13 | 351 | 413 | 13 | 16
OCP-CON1 | P03 | HUM | 2026-11-24 | 2026-11-30 | 17 | 12 | 200.2 | 228 | 12 | 11 | 94 | 428 | 3 | 15 | 70.6 | 21 | 2 | 20 | 364 | 428 | 15 | 17
OCP-CON1 | ALL | ALL | 2026-11-24 | 2026-11-30 | 30 | 31 | 446.6 | 260.5 | 27 | 26 | 413 | 1221 | 10 | 75 | 84.6 | 21 | 21 | 62 | 971 | 1368 | 45 | 56
OCP-CON1 | P01 | SEC | 2026-12-01 | 2026-12-07 | 23 | 21 | 227.3 | 239.5 | 9 | 8 | 172 | 397 | 8 | 29 | 91.3 | 7 | 7 | 18 | 337 | 397 | 11 | 23
OCP-CON1 | P02 | RIP | 2026-12-01 | 2026-12-07 | 15 | 12 | 142.9 | 136.7 | 5 | 4 | 230 | 388 | 6 | 18 | 80 | 21 | 4 | 28 | 330 | 388 | 5 | 15
OCP-CON1 | P03 | HUM | 2026-12-01 | 2026-12-07 | 14 | 12 | 113.9 | 112.6 | 9 | 8 | 125 | 405 | 5 | 17 | 85.7 | 7 | 2 | 26 | 344 | 405 | 12 | 14
OCP-CON1 | ALL | ALL | 2026-12-01 | 2026-12-07 | 38 | 52 | 427.8 | 239.8 | 35 | 32 | 290 | 1278 | 8 | 72 | 84.5 | 14 | 14 | 35 | 1255 | 1195 | 39 | 38
OCP-CON1 | P01 | SEC | 2026-12-08 | 2026-12-14 | 25 | 23 | 285.7 | 247.1 | 12 | 11 | 291 | 379 | 2 | 25 | 92 | 14 | 6 | 29 | 322 | 379 | 12 | 25
OCP-CON1 | P02 | RIP | 2026-12-08 | 2026-12-14 | 23 | 22 | 260.2 | 286.3 | 12 | 11 | 239 | 457 | 8 | 30 | 95.7 | 7 | 3 | 19 | 388 | 457 | 12 | 23
OCP-CON1 | P03 | HUM | 2026-12-08 | 2026-12-14 | 19 | 15 | 163.8 | 165.1 | 10 | 9 | 154 | 420 | 8 | 23 | 78.9 | 14 | 5 | 15 | 357 | 420 | 11 | 19
OCP-CON1 | ALL | ALL | 2026-12-08 | 2026-12-14 | 31 | 33 | 330.7 | 339.8 | 28 | 30 | 859 | 1492 | 11 | 57 | 78.9 | 14 | 18 | 33 | 1065 | 1251 | 30 | 39
OCP-CON1 | P01 | SEC | 2026-12-15 | 2026-12-21 | 17 | 13 | 138.2 | 145.9 | 11 | 10 | 181 | 473 | 7 | 20 | 76.5 | 14 | 2 | 25 | 402 | 473 | 14 | 17
OCP-CON1 | P02 | RIP | 2026-12-15 | 2026-12-21 | 25 | 21 | 284.1 | 255.8 | 15 | 13 | 96 | 486 | 7 | 28 | 84 | 21 | 9 | 21 | 413 | 486 | 16 | 25
OCP-CON1 | P03 | HUM | 2026-12-15 | 2026-12-21 | 15 | 11 | 115.1 | 103.3 | 15 | 12 | 287 | 449 | 2 | 13 | 73.3 | 7 | 7 | 22 | 382 | 449 | 14 | 15
OCP-CON1 | ALL | ALL | 2026-12-15 | 2026-12-21 | 60 | 36 | 210.3 | 460 | 17 | 23 | 417 | 1035 | 20 | 66 | 74 | 21 | 15 | 52 | 915 | 1221 | 21 | 51
OCP-CON1 | P01 | SEC | 2026-12-22 | 2026-12-28 | 20 | 18 | 151.8 | 165.8 | 6 | 5 | 224 | 455 | 3 | 21 | 90 | 14 | 9 | 17 | 387 | 455 | 6 | 20
OCP-CON1 | P02 | RIP | 2026-12-22 | 2026-12-28 | 12 | 10 | 122.9 | 114.6 | 6 | 4 | 208 | 376 | 2 | 12 | 83.3 | 21 | 6 | 27 | 320 | 376 | 5 | 12
OCP-CON1 | P03 | HUM | 2026-12-22 | 2026-12-28 | 10 | 9 | 89.2 | 97.2 | 10 | 9 | 249 | 460 | 7 | 16 | 90 | 21 | 4 | 30 | 391 | 460 | 10 | 10
OCP-CON1 | ALL | ALL | 2026-12-22 | 2026-12-28 | 37 | 31 | 298.3 | 481.8 | 27 | 18 | 254 | 1386 | 20 | 43 | 86.5 | 21 | 25 | 62 | 1018 | 1358 | 19 | 36
OCP-CON1 | P01 | SEC | 2026-12-29 | 2027-01-04 | 15 | 12 | 121.7 | 118 | 5 | 4 | 168 | 417 | 2 | 14 | 80 | 21 | 5 | 10 | 354 | 417 | 8 | 15
OCP-CON1 | P02 | RIP | 2026-12-29 | 2027-01-04 | 10 | 7 | 96.4 | 109.3 | 13 | 10 | 156 | 408 | 7 | 14 | 70 | 21 | 8 | 20 | 347 | 408 | 11 | 10
OCP-CON1 | P03 | HUM | 2026-12-29 | 2027-01-04 | 20 | 16 | 223.6 | 219.9 | 7 | 5 | 93 | 418 | 4 | 20 | 80 | 14 | 3 | 14 | 355 | 418 | 7 | 20
OCP-CON1 | ALL | ALL | 2026-12-29 | 2027-01-04 | 49 | 30 | 296.3 | 233.7 | 23 | 25 | 779 | 1204 | 15 | 49 | 83 | 14 | 24 | 31 | 1248 | 1202 | 20 | 52