## Shutdown Calendar
plant_id | shutdown_name | shutdown_type | planned_start | planned_end | planned_hours | areas_csv | description | work_packages_csv
OCP-JFC1 | BRY Minor Shutdown Q1 | MINOR_8H | 2026-03-26 | 2026-03-26 | 8 | BRY | SAG mill bearing inspections and greasing | SD-WP-001,SD-WP-002,SD-WP-003
OCP-JFC1 | FLT Minor Shutdown Q1 | MINOR_8H | 2026-04-10 | 2026-04-10 | 8 | FLT | Flotation cell agitator and launder inspection | SD-WP-004,SD-WP-005,SD-WP-006
OCP-JFC1 | CVY Minor Shutdown Q1 | MINOR_8H | 2026-04-15 | 2026-04-15 | 8 | CVY | Belt splice and idler roller inspection | SD-WP-007,SD-WP-008,SD-WP-009
OCP-JFC1 | PMP Minor Shutdown Q1 | MINOR_8H | 2026-04-20 | 2026-04-20 | 8 | PMP | Pump mechanical seal and impeller check | SD-WP-010,SD-WP-011,SD-WP-012
OCP-JFC1 | SED Minor Shutdown Q1 | MINOR_8H | 2026-04-25 | 2026-04-25 | 8 | SED | Thickener rake arm and drive inspection | SD-WP-013,SD-WP-014,SD-WP-015
OCP-JFC1 | ACR Minor Shutdown Q1 | MINOR_8H | 2026-05-05 | 2026-05-05 | 8 | ACR | Reactor lining and agitator inspection | SD-WP-016,SD-WP-017,SD-WP-018
OCP-JFC1 | BRY Major Shutdown Annual | MAJOR_20H_PLUS | 2026-05-25 | 2026-05-28 | 72 | BRY,PMP | SAG liner change + mill bearing replacement + pump overhaul | SD-WP-019,SD-WP-020,SD-WP-021,SD-WP-022,SD-WP-023,SD-WP-024,SD-WP-025,SD-WP-026
OCP-JFC1 | FIL Minor Shutdown Q2 | MINOR_8H | 2026-06-14 | 2026-06-14 | 8 | FIL | Filter belt tracking and vacuum pump service | SD-WP-027,SD-WP-028,SD-WP-029
OCP-JFC1 | GRN Minor Shutdown Q2 | MINOR_8H | 2026-06-24 | 2026-06-24 | 8 | GRN | Granulator drum liner and screen inspection | SD-WP-030,SD-WP-031,SD-WP-032
OCP-JFC1 | SEQ Major Shutdown | MAJOR_20H_PLUS | 2026-07-04 | 2026-07-07 | 72 | SEQ | Dryer refractory reline and girth gear inspection | SD-WP-033,SD-WP-034,SD-WP-035,SD-WP-036
OCP-JFC1 | UTL Minor Shutdown Q2 | MINOR_8H | 2026-07-14 | 2026-07-14 | 8 | UTL | Compressor valve overhaul and cooling tower service | SD-WP-037,SD-WP-038,SD-WP-039
OCP-JFC1 | STK Minor Shutdown Q2 | MINOR_8H | 2026-07-24 | 2026-07-24 | 8 | STK | Stacker-reclaimer boom and slewing gear inspection | SD-WP-040,SD-WP-041,SD-WP-042
OCP-JFC1 | FLT Minor Shutdown Q2 | MINOR_8H | 2026-07-29 | 2026-07-29 | 8 | FLT | Cleaner flotation cell overhaul | SD-WP-043,SD-WP-044,SD-WP-045
OCP-JFC1 | CVY Minor Shutdown Q2 | MINOR_8H | 2026-08-03 | 2026-08-03 | 8 | CVY | Conveyor drive gearbox oil change and alignment | SD-WP-046,SD-WP-047,SD-WP-048
OCP-JFC1 | Plant-Wide Major Shutdown | MAJOR_20H_PLUS | 2026-08-23 | 2026-08-30 | 168 | BRY,FLT,PMP,CVY,SED,FIL,SEQ,GRN,ACR,UTL,STK | Annual plant turnaround — all areas | SD-WP-049,SD-WP-050,SD-WP-051,SD-WP-052,SD-WP-053,SD-WP-054,SD-WP-055,SD-WP-056,SD-WP-057,SD-WP-058,SD-WP-059,SD-WP-060,SD-WP-061,SD-WP-062,SD-WP-063,SD-WP-064,SD-WP-065,SD-WP-066,SD-WP-067,SD-WP-068,SD-WP-069,SD-WP-070,SD-WP-071,SD-WP-072,SD-WP-073,SD-WP-074,SD-WP-075,SD-WP-076,SD-WP-077,SD-WP-078,SD-WP-079,SD-WP-080,SD-WP-081,SD-WP-082,SD-WP-083,SD-WP-084,SD-WP-085,SD-WP-086,SD-WP-087
OCP-JFC1 | BRY Minor Shutdown Q3 | MINOR_8H | 2026-09-22 | 2026-09-22 | 8 | BRY | Post-turnaround vibration baseline and alignment verify | SD-WP-088,SD-WP-089,SD-WP-090
OCP-JFC1 | PMP Minor Shutdown Q3 | MINOR_8H | 2026-10-02 | 2026-10-02 | 8 | PMP | Pump performance test and seal inspection | SD-WP-091,SD-WP-092,SD-WP-093
OCP-JFC1 | ACR Minor Shutdown Q3 | MINOR_8H | 2026-10-22 | 2026-10-22 | 8 | ACR | Acid pump seal check and reactor vessel inspection | SD-WP-094,SD-WP-095,SD-WP-096
OCP-JFC1 | FLT Minor Shutdown Q3 | MINOR_8H | 2026-11-11 | 2026-11-11 | 8 | FLT | Flotation air blower and cell level control check | SD-WP-097,SD-WP-098,SD-WP-099
OCP-JFC1 | SEQ Minor Shutdown Q3 | MINOR_8H | 2026-11-21 | 2026-11-21 | 8 | SEQ | Dryer seal inspection and kiln alignment check | SD-WP-100,SD-WP-101,SD-WP-102

## Shutdown Work Packages
shutdown_name | wp_code | equipment_tag | task_description | estimated_hours | crew_size | priority
BRY Minor Shutdown Q1 | SD-WP-001 | BRY-SAG-ML-002 | Inspect SAG mill bearings | 4 | 2 | 2_HIGH
BRY Minor Shutdown Q1 | SD-WP-002 | BRY-BML-ML-001 | Grease SAG mill pinion | 2 | 1 | 2_HIGH
BRY Minor Shutdown Q1 | SD-WP-003 | BRY-BML-ML-002 | Check ball mill liner wear | 3 | 2 | 2_HIGH
FLT Minor Shutdown Q1 | SD-WP-004 | FLT-RGH-FC-005 | Inspect flotation agitator | 3 | 2 | 2_HIGH
FLT Minor Shutdown Q1 | SD-WP-005 | FLT-RGH-FC-006 | Check launder condition | 2 | 1 | 2_HIGH
FLT Minor Shutdown Q1 | SD-WP-006 | FLT-CLN-FC-001 | Service air blower | 4 | 2 | 2_HIGH
CVY Minor Shutdown Q1 | SD-WP-007 | CVY-OLC-CV-003 | Inspect belt splice | 3 | 2 | 2_HIGH
CVY Minor Shutdown Q1 | SD-WP-008 | CVY-PRD-CV-001 | Replace idler rollers | 4 | 2 | 2_HIGH
CVY Minor Shutdown Q1 | SD-WP-009 | CVY-PRD-CV-002 | Check belt tracking | 2 | 1 | 2_HIGH
PMP Minor Shutdown Q1 | SD-WP-010 | PMP-MDP-PP-001 | Replace mechanical seal | 6 | 2 | 2_HIGH
PMP Minor Shutdown Q1 | SD-WP-011 | PMP-MDP-PP-002 | Inspect impeller wear | 4 | 2 | 2_HIGH
PMP Minor Shutdown Q1 | SD-WP-012 | PMP-PWS-PP-001 | Check bearing vibration | 2 | 1 | 2_HIGH
SED Minor Shutdown Q1 | SD-WP-013 | SED-THK-TH-002 | Inspect rake arm | 4 | 2 | 2_HIGH
SED Minor Shutdown Q1 | SD-WP-014 | SED-THK-PP-001 | Check drive torque | 2 | 1 | 2_HIGH
SED Minor Shutdown Q1 | SD-WP-015 | SED-THK-PP-002 | Inspect underflow pump | 3 | 2 | 2_HIGH
ACR Minor Shutdown Q1 | SD-WP-016 | ACR-REA-AG-001 | Inspect reactor lining | 6 | 3 | 2_HIGH
ACR Minor Shutdown Q1 | SD-WP-017 | ACR-HEX-FC-001 | Check agitator shaft | 4 | 2 | 2_HIGH
ACR Minor Shutdown Q1 | SD-WP-018 | ACR-HEX-HE-001 | Inspect acid pump seals | 3 | 2 | 2_HIGH
BRY Major Shutdown Annual | SD-WP-019 | BRY-BML-ML-002 | Inspect SAG mill bearings | 4 | 2 | 1_CRITICAL
BRY Major Shutdown Annual | SD-WP-020 | BRY-CYC-HC-001 | Grease SAG mill pinion | 2 | 1 | 1_CRITICAL
BRY Major Shutdown Annual | SD-WP-021 | BRY-CYC-HC-002 | Check ball mill liner wear | 3 | 2 | 1_CRITICAL
BRY Major Shutdown Annual | SD-WP-022 | BRY-CYC-PP-001 | Inspect cyclone cluster | 2 | 1 | 1_CRITICAL
BRY Major Shutdown Annual | SD-WP-023 | PMP-PWS-PP-002 | Replace mechanical seal | 6 | 2 | 1_CRITICAL
BRY Major Shutdown Annual | SD-WP-024 | PMP-PWS-PP-003 | Inspect impeller wear | 4 | 2 | 1_CRITICAL
BRY Major Shutdown Annual | SD-WP-025 | PMP-MDP-PP-001 | Check bearing vibration | 2 | 1 | 1_CRITICAL
BRY Major Shutdown Annual | SD-WP-026 | PMP-MDP-PP-002 | Test pump performance | 3 | 1 | 1_CRITICAL
FIL Minor Shutdown Q2 | SD-WP-027 | FIL-BLT-BF-003 | Inspect filter belt | 3 | 2 | 2_HIGH
FIL Minor Shutdown Q2 | SD-WP-028 | FIL-DSC-DF-001 | Service vacuum pump | 4 | 2 | 2_HIGH
FIL Minor Shutdown Q2 | SD-WP-029 | FIL-DSC-DF-002 | Check belt tracking system | 2 | 1 | 2_HIGH
GRN Minor Shutdown Q2 | SD-WP-030 | GRN-SCR-SC-001 | Inspect drum liner | 4 | 2 | 2_HIGH
GRN Minor Shutdown Q2 | SD-WP-031 | GRN-SCR-CR-001 | Check screen condition | 3 | 2 | 2_HIGH
GRN Minor Shutdown Q2 | SD-WP-032 | GRN-GRD-GD-001 | Inspect scraper blades | 2 | 1 | 2_HIGH
SEQ Major Shutdown | SD-WP-033 | SEQ-DRY-RD-001 | Inspect dryer refractory | 8 | 3 | 1_CRITICAL
SEQ Major Shutdown | SD-WP-034 | SEQ-DRY-RD-002 | Check girth gear mesh | 4 | 2 | 1_CRITICAL
SEQ Major Shutdown | SD-WP-035 | SEQ-CLR-RC-001 | Inspect riding ring | 3 | 2 | 1_CRITICAL
SEQ Major Shutdown | SD-WP-036 | SEQ-DRY-RD-001 | Service seal assembly | 4 | 2 | 1_CRITICAL
UTL Minor Shutdown Q2 | SD-WP-037 | UTL-AIR-AD-001 | Service compressor valves | 4 | 2 | 2_HIGH
UTL Minor Shutdown Q2 | SD-WP-038 | UTL-CWT-CT-001 | Inspect cooling tower fill | 3 | 2 | 2_HIGH
UTL Minor Shutdown Q2 | SD-WP-039 | UTL-CWT-PP-001 | Check transformer oil | 2 | 1 | 2_HIGH
STK Minor Shutdown Q2 | SD-WP-040 | STK-STK-SK-001 | Inspect boom structure | 4 | 2 | 2_HIGH
STK Minor Shutdown Q2 | SD-WP-041 | STK-RCL-RC-001 | Check slewing gear | 3 | 2 | 2_HIGH
STK Minor Shutdown Q2 | SD-WP-042 | STK-SIL-SI-001 | Lubricate travel wheels | 2 | 1 | 2_HIGH
FLT Minor Shutdown Q2 | SD-WP-043 | FLT-RGH-FC-005 | Inspect flotation agitator | 3 | 2 | 2_HIGH
FLT Minor Shutdown Q2 | SD-WP-044 | FLT-RGH-FC-006 | Check launder condition | 2 | 1 | 2_HIGH
FLT Minor Shutdown Q2 | SD-WP-045 | FLT-CLN-FC-001 | Service air blower | 4 | 2 | 2_HIGH
CVY Minor Shutdown Q2 | SD-WP-046 | CVY-OLC-CV-002 | Inspect belt splice | 3 | 2 | 2_HIGH
CVY Minor Shutdown Q2 | SD-WP-047 | CVY-OLC-CV-003 | Replace idler rollers | 4 | 2 | 2_HIGH
CVY Minor Shutdown Q2 | SD-WP-048 | CVY-PRD-CV-001 | Check belt tracking | 2 | 1 | 2_HIGH
Plant-Wide Major Shutdown | SD-WP-049 | BRY-SAG-ML-002 | Inspect SAG mill bearings | 4 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-050 | BRY-BML-ML-001 | Grease SAG mill pinion | 2 | 1 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-051 | BRY-BML-ML-002 | Check ball mill liner wear | 3 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-052 | BRY-CYC-HC-001 | Inspect cyclone cluster | 2 | 1 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-053 | FLT-RGH-FC-002 | Inspect flotation agitator | 3 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-054 | FLT-RGH-FC-003 | Check launder condition | 2 | 1 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-055 | FLT-RGH-FC-004 | Service air blower | 4 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-056 | FLT-RGH-FC-005 | Inspect cell level control | 2 | 1 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-057 | PMP-PWS-PP-001 | Replace mechanical seal | 6 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-058 | PMP-PWS-PP-002 | Inspect impeller wear | 4 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-059 | PMP-PWS-PP-003 | Check bearing vibration | 2 | 1 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-060 | PMP-MDP-PP-001 | Test pump performance | 3 | 1 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-061 | CVY-OLC-CV-002 | Inspect belt splice | 3 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-062 | CVY-OLC-CV-003 | Replace idler rollers | 4 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-063 | CVY-PRD-CV-001 | Check belt tracking | 2 | 1 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-064 | CVY-PRD-CV-002 | Lubricate drive components | 2 | 1 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-065 | SED-THK-TH-002 | Inspect rake arm | 4 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-066 | SED-THK-PP-001 | Check drive torque | 2 | 1 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-067 | SED-THK-PP-002 | Inspect underflow pump | 3 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-068 | FIL-DSC-DF-001 | Inspect filter belt | 3 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-069 | FIL-DSC-DF-002 | Service vacuum pump | 4 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-070 | FIL-BLT-BF-001 | Check belt tracking system | 2 | 1 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-071 | SEQ-CLR-RC-001 | Inspect dryer refractory | 8 | 3 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-072 | SEQ-DRY-RD-001 | Check girth gear mesh | 4 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-073 | SEQ-DRY-RD-002 | Inspect riding ring | 3 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-074 | SEQ-CLR-RC-001 | Service seal assembly | 4 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-075 | GRN-SCR-CR-001 | Inspect drum liner | 4 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-076 | GRN-GRD-GD-001 | Check screen condition | 3 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-077 | GRN-GRD-AG-001 | Inspect scraper blades | 2 | 1 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-078 | ACR-HEX-HE-001 | Inspect reactor lining | 6 | 3 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-079 | ACR-SAC-PP-001 | Check agitator shaft | 4 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-080 | ACR-REA-RV-001 | Inspect acid pump seals | 3 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-081 | UTL-CWT-PP-001 | Service compressor valves | 4 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-082 | UTL-ELC-TR-001 | Inspect cooling tower fill | 3 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-083 | UTL-ELC-GN-001 | Check transformer oil | 2 | 1 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-084 | UTL-AIR-AC-001 | Test emergency generator | 3 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-085 | STK-RCL-RC-001 | Inspect boom structure | 4 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-086 | STK-SIL-SI-001 | Check slewing gear | 3 | 2 | 1_CRITICAL
Plant-Wide Major Shutdown | SD-WP-087 | STK-SIL-SI-002 | Lubricate travel wheels | 2 | 1 | 1_CRITICAL
BRY Minor Shutdown Q3 | SD-WP-088 | BRY-SAG-ML-001 | Inspect SAG mill bearings | 4 | 2 | 2_HIGH
BRY Minor Shutdown Q3 | SD-WP-089 | BRY-SAG-ML-002 | Grease SAG mill pinion | 2 | 1 | 2_HIGH
BRY Minor Shutdown Q3 | SD-WP-090 | BRY-BML-ML-001 | Check ball mill liner wear | 3 | 2 | 2_HIGH
PMP Minor Shutdown Q3 | SD-WP-091 | PMP-MDP-PP-002 | Replace mechanical seal | 6 | 2 | 2_HIGH
PMP Minor Shutdown Q3 | SD-WP-092 | PMP-PWS-PP-001 | Inspect impeller wear | 4 | 2 | 2_HIGH
PMP Minor Shutdown Q3 | SD-WP-093 | PMP-PWS-PP-002 | Check bearing vibration | 2 | 1 | 2_HIGH
ACR Minor Shutdown Q3 | SD-WP-094 | ACR-SAC-PP-001 | Inspect reactor lining | 6 | 3 | 2_HIGH
ACR Minor Shutdown Q3 | SD-WP-095 | ACR-REA-RV-001 | Check agitator shaft | 4 | 2 | 2_HIGH
ACR Minor Shutdown Q3 | SD-WP-096 | ACR-REA-AG-001 | Inspect acid pump seals | 3 | 2 | 2_HIGH
FLT Minor Shutdown Q3 | SD-WP-097 | FLT-CLN-FC-001 | Inspect flotation agitator | 3 | 2 | 2_HIGH
FLT Minor Shutdown Q3 | SD-WP-098 | FLT-CLN-FC-002 | Check launder condition | 2 | 1 | 2_HIGH
FLT Minor Shutdown Q3 | SD-WP-099 | FLT-CLN-FC-003 | Service air blower | 4 | 2 | 2_HIGH
SEQ Minor Shutdown Q3 | SD-WP-100 | SEQ-DRY-RD-002 | Inspect dryer refractory | 8 | 3 | 2_HIGH
SEQ Minor Shutdown Q3 | SD-WP-101 | SEQ-CLR-RC-001 | Check girth gear mesh | 4 | 2 | 2_HIGH
SEQ Minor Shutdown Q3 | SD-WP-102 | SEQ-DRY-RD-001 | Inspect riding ring | 3 | 2 | 2_HIGH