## Planning KPI Input
plant_id | period_start | period_end | wo_planned | wo_completed | manhours_planned | manhours_actual | pm_planned | pm_executed | backlog_hours | weekly_capacity_hours | corrective_count | total_wo | schedule_compliance_planned | schedule_compliance_executed | release_horizon_days | pending_notices | total_notices | scheduled_capacity_hours | total_capacity_hours | proactive_wo | planned_wo
OCP-JFC1 | 2026-02-17 | 2026-02-24 | 87 | 79 | 744.3 | 701.4 | 64 | 58 | 295 | 200 | 14 | 87 | 95 | 73 | 5 | 19 | 87 | 167 | 200 | 86 | 90
OCP-JFC1 | 2026-02-10 | 2026-02-17 | 110 | 90 | 783.6 | 740.3 | 49 | 43 | 365 | 200 | 17 | 110 | 93 | 91 | 4 | 5 | 110 | 186 | 200 | 73 | 71
OCP-JFC1 | 2026-02-03 | 2026-02-10 | 85 | 70 | 711.6 | 760.1 | 56 | 53 | 350 | 200 | 18 | 85 | 85 | 88 | 6 | 12 | 85 | 172 | 200 | 72 | 76
OCP-JFC1 | 2026-01-27 | 2026-02-03 | 110 | 102 | 924.4 | 938.8 | 44 | 42 | 298 | 200 | 13 | 110 | 92 | 80 | 7 | 10 | 110 | 167 | 200 | 63 | 92
OCP-JFC1 | 2026-01-20 | 2026-01-27 | 93 | 82 | 734.2 | 775.9 | 64 | 59 | 265 | 200 | 25 | 93 | 85 | 80 | 4 | 7 | 93 | 154 | 200 | 73 | 70
OCP-JFC1 | 2026-01-13 | 2026-01-20 | 94 | 77 | 763.5 | 827.7 | 42 | 38 | 206 | 200 | 12 | 94 | 94 | 90 | 5 | 10 | 94 | 160 | 200 | 88 | 77
OCP-JFC1 | 2026-01-06 | 2026-01-13 | 104 | 88 | 886.2 | 926.3 | 65 | 61 | 393 | 200 | 9 | 104 | 88 | 72 | 4 | 5 | 104 | 176 | 200 | 78 | 97
OCP-JFC1 | 2025-12-30 | 2026-01-06 | 91 | 76 | 799.1 | 738.8 | 44 | 39 | 424 | 200 | 10 | 91 | 82 | 85 | 5 | 11 | 91 | 166 | 200 | 75 | 95
OCP-JFC1 | 2025-12-23 | 2025-12-30 | 86 | 75 | 641.5 | 657.6 | 46 | 43 | 294 | 200 | 18 | 86 | 100 | 84 | 4 | 10 | 86 | 162 | 200 | 88 | 75
OCP-JFC1 | 2025-12-16 | 2025-12-23 | 87 | 72 | 611.5 | 592.8 | 59 | 54 | 201 | 200 | 24 | 87 | 88 | 73 | 4 | 5 | 87 | 171 | 200 | 76 | 86
OCP-JFC1 | 2025-12-09 | 2025-12-16 | 94 | 79 | 666.9 | 720.1 | 40 | 35 | 255 | 200 | 12 | 94 | 88 | 78 | 6 | 11 | 94 | 188 | 200 | 71 | 92
OCP-JFC1 | 2025-12-02 | 2025-12-09 | 120 | 109 | 888.1 | 943 | 53 | 48 | 300 | 200 | 14 | 120 | 88 | 75 | 4 | 13 | 120 | 188 | 200 | 63 | 88