## Sheet1
program_week | program_date | planning_group | work_center | specialty | available_hh | planned_hh_pm | planned_hh_cm | planned_hh_shutdown | total_planned_hh | utilization_pct | overload_flag | num_orders_pm | num_orders_cm | order_number | order_type | order_description | notification_number | backlog_hh_remaining | compliance_target_pct | notes
2026-W14 | 2026-04-06 | M01 | PASMEC01 | Mecánica | 39 | 5.2 | 6.3 | 0.4 | 11.9 | 30.5 | No | 3 | 1 | 500141 | PM02 | PM - Lava ojos emergencia |  | 192.9 | 90
2026-W14 | 2026-04-06 | M01 | PASMEC01 | Eléctrica | 33 | 12.7 | 2.8 | 0.9 | 16.4 | 49.7 | No | 2 | 2 | 500016 | PM02 | PM - Lava ojos emergencia |  | 177.3 | 90
2026-W14 | 2026-04-06 | M01 | PASMEC01 | Instrumentación | 32 | 8.6 | 5.2 | 0.1 | 13.9 | 43.4 | No | 4 | 4 | 500108 | PM02 | PM - Motor eléctrico HY0036M1 |  | 41.1 | 90
2026-W14 | 2026-04-06 | M01 | PASELE01 | Mecánica | 38 | 16.8 | 7.5 | 0.3 | 24.6 | 64.7 | No | 6 | 1 | 500055 | PM01 | CM - Baliza YL3612 | 1000546 | 105.4 | 90
2026-W14 | 2026-04-06 | M01 | PASELE01 | Eléctrica | 26 | 12.6 | 5.1 | 1 | 18.7 | 71.9 | No | 4 | 1 | 500158 | PM02 | PM - Válvula control flujo sol barren FV5601 | 1001805 | 108.7 | 90
2026-W14 | 2026-04-06 | M01 | PASELE01 | Instrumentación | 28 | 12.1 | 4.2 | 0.2 | 16.5 | 58.9 | No | 3 | 1 | 500141 | PM02 | PM - Lava ojos emergencia |  | 80 | 90
2026-W14 | 2026-04-06 | M01 | PASINS01 | Mecánica | 37 | 12.3 | 4.2 | 2.9 | 19.4 | 52.4 | No | 6 | 2 | 500096 | PM02 | PM - Válvula control descarga agua fresca HV7819 |  | 80.1 | 90
2026-W14 | 2026-04-06 | M01 | PASINS01 | Eléctrica | 19 | 9.4 | 4.9 | 0.2 | 14.5 | 76.3 | No | 3 | 1 | 500039 | PM02 | PM - Chute carbónHO0068 | 1004125 | 102.9 | 90
2026-W14 | 2026-04-06 | M01 | PASINS01 | Instrumentación | 32 | 4.4 | 4.5 | 1.7 | 10.6 | 33.1 | No | 7 | 4 | 500190 | PM01 | CM - Colector polvo horno fundición | 1004414 | 73.7 | 90
2026-W14 | 2026-04-06 | M01 | PAHMEC01 | Mecánica | 36 | 17.5 | 5.3 | 0.9 | 23.7 | 65.8 | No | 2 | 2 | 500185 | PM01 | CM - Motor eléctrico HY0036M1 | 1001772 | 102.4 | 90
2026-W14 | 2026-04-06 | M01 | PAHMEC01 | Eléctrica | 35 | 13.9 | 2.7 | 2.3 | 18.9 | 54 | No | 7 | 3 | 500121 | PM01 | CM - Calefactor eléctrico edificio |  | 108.1 | 90
2026-W14 | 2026-04-06 | M01 | PAHMEC01 | Instrumentación | 22 | 6.4 | 4.6 | 0.5 | 11.5 | 52.3 | No | 3 | 3 | 500153 | PM02 | PM - Sistema Spray Grasa Engranaje - Molino SAG |  | 29.4 | 90
2026-W14 | 2026-04-06 | M01 | PAHELE01 | Mecánica | 29 | 11.2 | 3.2 | 2.4 | 16.8 | 57.9 | No | 4 | 3 | 500084 | PM02 | PM - Motor eléctrico HY0001M1 |  | 70.7 | 90
2026-W14 | 2026-04-06 | M01 | PAHELE01 | Eléctrica | 32 | 10.2 | 3.8 | 0.4 | 14.4 | 45 | No | 6 | 3 | 500177 | PM01 | CM - Intercambiador calor por aire CQ0007 | 1001166 | 195.8 | 90
2026-W14 | 2026-04-06 | M01 | PAHELE01 | Instrumentación | 35 | 11.4 | 4.3 | 2.5 | 18.2 | 52 | No | 5 | 3 | 500120 | PM01 | CM - Transmisor presión salida sol barren PIT3241 | 1006468 | 198 | 90
2026-W14 | 2026-04-06 | M01 | PAHINS01 | Mecánica | 35 | 13.8 | 6.5 | 0.7 | 21 | 60 | No | 5 | 3 | 500146 | PM02 | PM - Válvula control alimenta pulpa HV1501C |  | 89 | 90
2026-W14 | 2026-04-06 | M01 | PAHINS01 | Eléctrica | 26 | 11.2 | 6.6 | 1.3 | 19.1 | 73.5 | No | 4 | 4 | 500153 | PM02 | PM - Sistema Spray Grasa Engranaje - Molino SAG |  | 125.9 | 90
2026-W14 | 2026-04-06 | M01 | PAHINS01 | Instrumentación | 26 | 7.4 | 6.4 | 1.4 | 15.2 | 58.5 | No | 3 | 4 | 500181 | PM01 | CM - Bomba diafragma grasa PU0001 |  | 23.2 | 90
2026-W14 | 2026-04-06 | M02 | PASMEC01 | Mecánica | 30 | 11 | 6.9 | 0.3 | 18.2 | 60.7 | No | 4 | 2 | 500073 | PM02 | PM - Válvula control sol barren a estanque HV3266 | 1000964 | 115.9 | 90
2026-W14 | 2026-04-06 | M02 | PASMEC01 | Eléctrica | 39 | 19.2 | 9.2 | 0.5 | 28.9 | 74.1 | No | 3 | 3 | 500140 | PM02 | PM - Correa retorno pebbles |  | 37.1 | 90
2026-W14 | 2026-04-06 | M02 | PASMEC01 | Instrumentación | 29 | 9.1 | 6.2 | 2.7 | 18 | 62.1 | No | 5 | 4 | 500037 | PM02 | PM - Sirena YA1151 |  | 51.2 | 90
2026-W14 | 2026-04-06 | M02 | PASELE01 | Mecánica | 22 | 4.4 | 2.9 | 0.1 | 7.4 | 33.6 | No | 6 | 2 | 500171 | PM02 | PM - Switch bajo nivel aceite LSL0253 |  | 150.2 | 90
2026-W14 | 2026-04-06 | M02 | PASELE01 | Eléctrica | 34 | 12.7 | 6 | 3.1 | 21.8 | 64.1 | No | 3 | 3 | 500039 | PM02 | PM - Chute carbónHO0068 |  | 87 | 90
2026-W14 | 2026-04-06 | M02 | PASELE01 | Instrumentación | 19 | 4.3 | 3.7 | 0.4 | 8.4 | 44.2 | No | 4 | 1 | 500046 | PM02 | PM - Gabinete servidor core switch 1 y commun |  | 136.9 | 90
2026-W14 | 2026-04-06 | M02 | PASINS01 | Mecánica | 33 | 4.7 | 6.9 | 0.2 | 11.8 | 35.8 | No | 4 | 3 | 500062 | PM01 | CM - Transmisor nivel lechada cal LIT5271 | 1020061 | 112.1 | 90
2026-W14 | 2026-04-06 | M02 | PASINS01 | Eléctrica | 37 | 4.1 | 10 | 2.1 | 16.2 | 43.8 | No | 3 | 2 | 500052 | PM01 | CM - Tablero distribución instrumentación | 1005704 | 150.2 | 90
2026-W14 | 2026-04-06 | M02 | PASINS01 | Instrumentación | 32 | 10 | 2.8 | 1.2 | 14 | 43.8 | No | 7 | 1 | 500148 | PM02 | PM - Válvula control descarga sol rica HV2810 |  | 22.8 | 90
2026-W14 | 2026-04-06 | M02 | PAHMEC01 | Mecánica | 21 | 5.9 | 2.6 | 0.3 | 8.8 | 41.9 | No | 6 | 4 | 500054 | PM01 | CM - Intercambiador calor calentamiento | 1003565 | 135.7 | 90
2026-W14 | 2026-04-06 | M02 | PAHMEC01 | Eléctrica | 17 | 8.5 | 2 | 1.1 | 11.6 | 68.2 | No | 2 | 2 | 500110 | PM02 | PM - Válvula control entrada pulpa HV1706 |  | 171.6 | 90
2026-W14 | 2026-04-06 | M02 | PAHMEC01 | Instrumentación | 26 | 4.7 | 6.1 | 1 | 11.8 | 45.4 | No | 3 | 3 | 500057 | PM01 | CM - Bomba rotativa aceite PU0510 | 1002801 | 137 | 90
2026-W14 | 2026-04-06 | M02 | PAHELE01 | Mecánica | 18 | 7.8 | 5.2 | 0.9 | 13.9 | 77.2 | No | 7 | 2 | 500003 | PM02 | PM - Tablero de comunicación |  | 162 | 90
2026-W14 | 2026-04-06 | M02 | PAHELE01 | Eléctrica | 23 | 7.7 | 2.6 | 0.9 | 11.2 | 48.7 | No | 4 | 4 | 500005 | PM02 | PM - Válvula control succión agua fresca HV7808 | 1007215 | 159.1 | 90
2026-W14 | 2026-04-06 | M02 | PAHELE01 | Instrumentación | 32 | 7.2 | 6 | 1.8 | 15 | 46.9 | No | 3 | 1 | 500177 | PM01 | CM - Intercambiador calor por aire CQ0007 | 1005140 | 160.5 | 90
2026-W14 | 2026-04-06 | M02 | PAHINS01 | Mecánica | 22 | 9 | 2.9 | 0.8 | 12.7 | 57.7 | No | 5 | 3 | 500122 | PM01 | CM - Carro mantención regeneración carbon | 1001915 | 133.1 | 90
2026-W14 | 2026-04-06 | M02 | PAHINS01 | Eléctrica | 33 | 15.9 | 2.6 | 1.2 | 19.7 | 59.7 | No | 2 | 3 | 500163 | PM02 | PM - Válvula control salida precapa HV3102 |  | 108.8 | 90
2026-W14 | 2026-04-06 | M02 | PAHINS01 | Instrumentación | 20 | 7.3 | 2.7 | 0.8 | 10.8 | 54 | No | 5 | 3 | 500062 | PM01 | CM - Transmisor nivel lechada cal LIT5271 |  | 136 | 90
2026-W14 | 2026-04-06 | P01 | PASMEC01 | Mecánica | 26 | 7.8 | 4.3 | 1.7 | 13.8 | 53.1 | No | 7 | 2 | 500003 | PM02 | PM - Tablero de comunicación |  | 117.9 | 90
2026-W14 | 2026-04-06 | P01 | PASMEC01 | Eléctrica | 24 | 10.1 | 5.2 | 0.4 | 15.7 | 65.4 | No | 3 | 1 | 500013 | PM02 | PM - Válvula control drenaje pulpa HV1006 |  | 149.6 | 90
2026-W14 | 2026-04-06 | P01 | PASMEC01 | Instrumentación | 27 | 9.3 | 7.4 | 0.8 | 17.5 | 64.8 | No | 4 | 4 | 500089 | PM02 | PM - Transmisor presión salida sol barren PIT3241 |  | 40.8 | 90
2026-W14 | 2026-04-06 | P01 | PASELE01 | Mecánica | 19 | 7 | 4.3 | 1.3 | 12.6 | 66.3 | No | 7 | 1 | 500142 | PM02 | PM - Calefactor eléctrico estanque HE0113 |  | 178.9 | 90
2026-W14 | 2026-04-06 | P01 | PASELE01 | Eléctrica | 34 | 15.1 | 3.3 | 3.3 | 21.7 | 63.8 | No | 4 | 4 | 500011 | PM02 | PM - Válvula control agua sello HV2723 |  | 110.2 | 90
2026-W14 | 2026-04-06 | P01 | PASELE01 | Instrumentación | 37 | 16.5 | 5.1 | 3.3 | 24.9 | 67.3 | No | 4 | 2 | 500067 | PM02 | PM - Indicador presión aceite hidráulico PI4895E |  | 140.8 | 90
2026-W14 | 2026-04-06 | P01 | PASINS01 | Mecánica | 30 | 4.7 | 5.8 | 1.8 | 12.3 | 41 | No | 6 | 2 | 500029 | PM02 | PM - Switch posición ZS0038A |  | 85.6 | 90
2026-W14 | 2026-04-06 | P01 | PASINS01 | Eléctrica | 30 | 13.3 | 5.8 | 2.4 | 21.5 | 71.7 | No | 4 | 1 | 500153 | PM02 | PM - Sistema Spray Grasa Engranaje - Molino SAG |  | 148.4 | 90
2026-W14 | 2026-04-06 | P01 | PASINS01 | Instrumentación | 16 | 5.8 | 2.4 | 0.2 | 8.4 | 52.5 | No | 2 | 2 | 500170 | PM02 | PM - Switch posición ZS0038A |  | 101.4 | 90
2026-W14 | 2026-04-06 | P01 | PAHMEC01 | Mecánica | 39 | 15.5 | 11.4 | 2.8 | 29.7 | 76.2 | No | 7 | 4 | 500040 | PM02 | PM - Mesa rodillos |  | 145.7 | 90
2026-W14 | 2026-04-06 | P01 | PAHMEC01 | Eléctrica | 18 | 5.8 | 2.3 | 1.3 | 9.4 | 52.2 | No | 7 | 2 | 500139 | PM02 | PM - Hidrante/ Grifos FH0136 | 1000984 | 160.9 | 90
2026-W14 | 2026-04-06 | P01 | PAHMEC01 | Instrumentación | 23 | 4.2 | 5.1 | 0.4 | 9.7 | 42.2 | No | 7 | 1 | 500124 | PM01 | CM - Extractor taller EMP | 1006472 | 87.7 | 90
2026-W14 | 2026-04-06 | P01 | PAHELE01 | Mecánica | 23 | 6.7 | 4.9 | 2 | 13.6 | 59.1 | No | 2 | 3 | 500133 | PM02 | PM - Calefactor eléctrico HE0135 | 1000914 | 107.1 | 90
2026-W14 | 2026-04-06 | P01 | PAHELE01 | Eléctrica | 37 | 7.9 | 4.5 | 3.5 | 15.9 | 43 | No | 6 | 1 | 500037 | PM02 | PM - Sirena YA1151 |  | 123.9 | 90
2026-W14 | 2026-04-06 | P01 | PAHELE01 | Instrumentación | 36 | 5.2 | 8 | 2.5 | 15.7 | 43.6 | No | 6 | 1 | 500028 | PM02 | PM - Válvula control succión agua fresca HV7808 | 1004689 | 33.8 | 90
2026-W14 | 2026-04-06 | P01 | PAHINS01 | Mecánica | 30 | 4.9 | 3.4 | 2.9 | 11.2 | 37.3 | No | 4 | 3 | 500114 | PM01 | CM - Transmisor vibración VT0020A | 1006368 | 104 | 90
2026-W14 | 2026-04-06 | P01 | PAHINS01 | Eléctrica | 32 | 4.5 | 7.5 | 1.7 | 13.7 | 42.8 | No | 6 | 2 | 500062 | PM01 | CM - Transmisor nivel lechada cal LIT5271 | 1002746 | 37 | 90
2026-W14 | 2026-04-06 | P01 | PAHINS01 | Instrumentación | 39 | 6.6 | 3.8 | 1.8 | 12.2 | 31.3 | No | 7 | 4 | 500067 | PM02 | PM - Indicador presión aceite hidráulico PI4895E |  | 64.5 | 90
2026-W14 | 2026-04-06 | P02 | PASMEC01 | Mecánica | 28 | 10.7 | 6.1 | 2.3 | 19.1 | 68.2 | No | 5 | 4 | 500098 | PM02 | PM - Unidad presurización |  | 176.3 | 90
2026-W14 | 2026-04-06 | P02 | PASMEC01 | Eléctrica | 26 | 10.3 | 3.6 | 2.6 | 16.5 | 63.5 | No | 5 | 3 | 500033 | PM02 | PM - Válvula control entrada lechada cal HV5311 |  | 26.8 | 90
2026-W14 | 2026-04-06 | P02 | PASMEC01 | Instrumentación | 38 | 15.6 | 6.2 | 1.7 | 23.5 | 61.8 | No | 2 | 1 | 500147 | PM02 | PM - Baliza YL3612 |  | 185.5 | 90
2026-W14 | 2026-04-06 | P02 | PASELE01 | Mecánica | 28 | 10.7 | 2.4 | 1.3 | 14.4 | 51.4 | No | 2 | 2 | 500092 | PM02 | PM - Bomba precipitado |  | 104.6 | 90
2026-W14 | 2026-04-06 | P02 | PASELE01 | Eléctrica | 33 | 11.3 | 4.8 | 0.5 | 16.6 | 50.3 | No | 2 | 4 | 500059 | PM01 | CM - Mezclador floculante | 1006925 | 184.9 | 90
2026-W14 | 2026-04-06 | P02 | PASELE01 | Instrumentación | 20 | 6 | 5.7 | 1.8 | 13.5 | 67.5 | No | 4 | 1 | 500107 | PM02 | PM - Gabinete manguera y equipo contraincendios HH0105 |  | 27.1 | 90
2026-W14 | 2026-04-06 | P02 | PASINS01 | Mecánica | 36 | 12.1 | 10.3 | 0.2 | 22.6 | 62.8 | No | 7 | 1 | 500181 | PM01 | CM - Bomba diafragma grasa PU0001 | 1004287 | 51.3 | 90
2026-W14 | 2026-04-06 | P02 | PASINS01 | Eléctrica | 26 | 4.3 | 3.4 | 1.2 | 8.9 | 34.2 | No | 7 | 4 | 500155 | PM02 | PM - Válvula control salida precapa HV3102 |  | 120.3 | 90
2026-W14 | 2026-04-06 | P02 | PASINS01 | Instrumentación | 28 | 6.7 | 7.3 | 1.2 | 15.2 | 54.3 | No | 2 | 4 | 500007 | PM02 | PM - Transmisor vibración VT0020A |  | 155 | 90
2026-W14 | 2026-04-06 | P02 | PAHMEC01 | Mecánica | 29 | 5.5 | 5 | 1.6 | 12.1 | 41.7 | No | 4 | 4 | 500045 | PM02 | PM - Transmisor presión agua potable PIT7025 |  | 99.9 | 90
2026-W14 | 2026-04-06 | P02 | PAHMEC01 | Eléctrica | 25 | 7.7 | 5 | 2 | 14.7 | 58.8 | No | 3 | 4 | 500031 | PM02 | PM - Celosía XM0114 |  | 192.8 | 90
2026-W14 | 2026-04-06 | P02 | PAHMEC01 | Instrumentación | 31 | 14.2 | 4.4 | 1 | 19.6 | 63.2 | No | 6 | 1 | 500138 | PM02 | PM - Motor eléctrico HY0036M1 |  | 189.3 | 90
2026-W14 | 2026-04-06 | P02 | PAHELE01 | Mecánica | 27 | 5.9 | 3.2 | 0.3 | 9.4 | 34.8 | No | 3 | 4 | 500181 | PM01 | CM - Bomba diafragma grasa PU0001 |  | 89.4 | 90
2026-W14 | 2026-04-06 | P02 | PAHELE01 | Eléctrica | 22 | 9.3 | 4.3 | 2.2 | 15.8 | 71.8 | No | 4 | 4 | 500159 | PM02 | PM - Gabinete manguera y equipo contraincendios HH0119 | 1003330 | 30.5 | 90
2026-W14 | 2026-04-06 | P02 | PAHELE01 | Instrumentación | 21 | 7.8 | 2.4 | 1.5 | 11.7 | 55.7 | No | 2 | 4 | 500077 | PM02 | PM - Válvula control entrada solucion barren FV2314 |  | 108.7 | 90
2026-W14 | 2026-04-06 | P02 | PAHINS01 | Mecánica | 35 | 13.7 | 10 | 3.1 | 26.8 | 76.6 | No | 5 | 1 | 500039 | PM02 | PM - Chute carbónHO0068 | 1005645 | 159.4 | 90
2026-W14 | 2026-04-06 | P02 | PAHINS01 | Eléctrica | 35 | 11.5 | 3 | 0.4 | 14.9 | 42.6 | No | 7 | 2 | 500046 | PM02 | PM - Gabinete servidor core switch 1 y commun |  | 148.5 | 90
2026-W14 | 2026-04-06 | P02 | PAHINS01 | Instrumentación | 23 | 9.4 | 2.2 | 1.4 | 13 | 56.5 | No | 3 | 2 | 500017 | PM02 | PM - Indicador presión agua PI0423 | 1007010 | 194.4 | 90
2026-W14 | 2026-04-07 | M01 | PASMEC01 | Mecánica | 23 | 7.2 | 3.4 | 1.4 | 12 | 52.2 | No | 3 | 3 | 500188 | PM01 | CM - Switch posición ZS1716 | 1006509 | 37 | 90
2026-W14 | 2026-04-07 | M01 | PASMEC01 | Eléctrica | 37 | 8.6 | 10.3 | 0.7 | 19.6 | 53 | No | 2 | 1 | 500163 | PM02 | PM - Válvula control salida precapa HV3102 | 1002515 | 93 | 90
2026-W14 | 2026-04-07 | M01 | PASMEC01 | Instrumentación | 21 | 8.5 | 6.2 | 1.5 | 16.2 | 77.1 | No | 7 | 1 | 500158 | PM02 | PM - Válvula control flujo sol barren FV5601 | 1005353 | 190.7 | 90
2026-W14 | 2026-04-07 | M01 | PASELE01 | Mecánica | 18 | 8.1 | 2.2 | 1 | 11.3 | 62.8 | No | 4 | 2 | 500063 | PM01 | CM - Válvula control entrada solucion barren FV2314 | 1002383 | 188.1 | 90
2026-W14 | 2026-04-07 | M01 | PASELE01 | Eléctrica | 19 | 8 | 2.8 | 0.9 | 11.7 | 61.6 | No | 7 | 3 | 500037 | PM02 | PM - Sirena YA1151 | 1005316 | 118.5 | 90
2026-W14 | 2026-04-07 | M01 | PASELE01 | Instrumentación | 30 | 14.2 | 5.6 | 0.4 | 20.2 | 67.3 | No | 7 | 4 | 500148 | PM02 | PM - Válvula control descarga sol rica HV2810 |  | 42.8 | 90
2026-W14 | 2026-04-07 | M01 | PASINS01 | Mecánica | 34 | 12.2 | 5 | 1.4 | 18.6 | 54.7 | No | 7 | 4 | 500068 | PM02 | PM - Tecle eléctrico tolva carbon |  | 108.4 | 90
2026-W14 | 2026-04-07 | M01 | PASINS01 | Eléctrica | 33 | 10.2 | 8.6 | 0.5 | 19.3 | 58.5 | No | 2 | 4 | 500017 | PM02 | PM - Indicador presión agua PI0423 |  | 31.8 | 90
2026-W14 | 2026-04-07 | M01 | PASINS01 | Instrumentación | 22 | 6.9 | 3 | 2.1 | 12 | 54.5 | No | 6 | 4 | 500145 | PM02 | PM - Transmisor presion agua PT0404 |  | 86.9 | 90
2026-W14 | 2026-04-07 | M01 | PAHMEC01 | Mecánica | 22 | 5.6 | 5.6 | 0.4 | 11.6 | 52.7 | No | 2 | 3 | 500022 | PM02 | PM - Unidad re-potabilizadora agua |  | 105.4 | 90
2026-W14 | 2026-04-07 | M01 | PAHMEC01 | Eléctrica | 26 | 4.3 | 5.8 | 0.7 | 10.8 | 41.5 | No | 5 | 1 | 500050 | PM01 | CM - Línea agua sell 3700-5476-AA1A-3"-WGS-ET |  | 70.3 | 90
2026-W14 | 2026-04-07 | M01 | PAHMEC01 | Instrumentación | 34 | 12.9 | 2.4 | 2.7 | 18 | 52.9 | No | 5 | 2 | 500175 | PM01 | CM - Válvula control aceite XV0279 |  | 163.8 | 90
2026-W14 | 2026-04-07 | M01 | PAHELE01 | Mecánica | 28 | 11.5 | 3.3 | 1.5 | 16.3 | 58.2 | No | 3 | 3 | 500164 | PM02 | PM - Bomba muestreo pulpa relaves PU0267 |  | 132.9 | 90
2026-W14 | 2026-04-07 | M01 | PAHELE01 | Eléctrica | 17 | 8.3 | 4.1 | 1.5 | 13.9 | 81.8 | No | 6 | 4 | 500180 | PM01 | CM - Bomba diesel horno reactivación carbon |  | 152.4 | 90
2026-W14 | 2026-04-07 | M01 | PAHELE01 | Instrumentación | 22 | 6.6 | 5.9 | 1.2 | 13.7 | 62.3 | No | 7 | 3 | 500007 | PM02 | PM - Transmisor vibración VT0020A | 1003105 | 186.7 | 90
2026-W14 | 2026-04-07 | M01 | PAHINS01 | Mecánica | 22 | 10.5 | 6 | 1.1 | 17.6 | 80 | No | 4 | 3 | 500134 | PM02 | PM - Intercambiador calor por aire CQ0007 |  | 148.6 | 90
2026-W14 | 2026-04-07 | M01 | PAHINS01 | Eléctrica | 19 | 5 | 5 | 1.8 | 11.8 | 62.1 | No | 5 | 2 | 500160 | PM02 | PM - Gabinete control Chancador Primario |  | 109.1 | 90
2026-W14 | 2026-04-07 | M01 | PAHINS01 | Instrumentación | 16 | 6.2 | 3.4 | 0.2 | 9.8 | 61.3 | No | 5 | 3 | 500058 | PM01 | CM - Sensor temperatura aire TS4591 | 1003554 | 80.1 | 90
2026-W14 | 2026-04-07 | M02 | PASMEC01 | Mecánica | 28 | 8.8 | 3.9 | 0.7 | 13.4 | 47.9 | No | 2 | 2 | 500174 | PM02 | PM - Bomba precipitado |  | 71.3 | 90
2026-W14 | 2026-04-07 | M02 | PASMEC01 | Eléctrica | 32 | 4.6 | 7.7 | 3.1 | 15.4 | 48.1 | No | 6 | 1 | 500004 | PM02 | PM - Válvula control aceite XV0256D |  | 78.2 | 90
2026-W14 | 2026-04-07 | M02 | PASMEC01 | Instrumentación | 17 | 6.6 | 2.5 | 0.6 | 9.7 | 57.1 | No | 5 | 1 | 500141 | PM02 | PM - Lava ojos emergencia |  | 120.8 | 90
2026-W14 | 2026-04-07 | M02 | PASELE01 | Mecánica | 20 | 6 | 5 | 1.1 | 12.1 | 60.5 | No | 2 | 2 | 500015 | PM02 | PM - Sensor temperatura aire TS4591 |  | 50.5 | 90
2026-W14 | 2026-04-07 | M02 | PASELE01 | Eléctrica | 32 | 4.9 | 7.4 | 2.9 | 15.2 | 47.5 | No | 5 | 1 | 500157 | PM02 | PM - Tablero distribución instrumentación |  | 86.7 | 90
2026-W14 | 2026-04-07 | M02 | PASELE01 | Instrumentación | 39 | 11.8 | 8.4 | 3.6 | 23.8 | 61 | No | 7 | 4 | 500032 | PM02 | PM - Válvula control entrada cianuro sodio FV1903 | 1005070 | 110.3 | 90
2026-W14 | 2026-04-07 | M02 | PASINS01 | Mecánica | 37 | 9.9 | 6.3 | 0.2 | 16.4 | 44.3 | No | 3 | 1 | 500084 | PM02 | PM - Motor eléctrico HY0001M1 |  | 162.3 | 90
2026-W14 | 2026-04-07 | M02 | PASINS01 | Eléctrica | 29 | 7.2 | 4.6 | 2.5 | 14.3 | 49.3 | No | 7 | 3 | 500027 | PM02 | PM - Válvula control aceite XV4883 |  | 69 | 90
2026-W14 | 2026-04-07 | M02 | PASINS01 | Instrumentación | 29 | 4.3 | 7.2 | 2.6 | 14.1 | 48.6 | No | 2 | 1 | 500126 | PM01 | CM - Válvula control salida carbon descargado HV3394 | 1000989 | 127.4 | 90
2026-W14 | 2026-04-07 | M02 | PAHMEC01 | Mecánica | 35 | 6.9 | 6.4 | 1.7 | 15 | 42.9 | No | 3 | 3 | 500021 | PM02 | PM - Tornillo alimentador sulfato de cobre |  | 167.3 | 90
2026-W14 | 2026-04-07 | M02 | PAHMEC01 | Eléctrica | 19 | 9.2 | 3.1 | 1.7 | 14 | 73.7 | No | 3 | 1 | 500101 | PM02 | PM - Subestación unitaria |  | 64.6 | 90
2026-W14 | 2026-04-07 | M02 | PAHMEC01 | Instrumentación | 21 | 8.4 | 4.3 | 1.4 | 14.1 | 67.1 | No | 2 | 1 | 500006 | PM02 | PM - Válvula control entrada sol precipitado HV3185 |  | 96.1 | 90
2026-W14 | 2026-04-07 | M02 | PAHELE01 | Mecánica | 23 | 9.4 | 2.6 | 0.9 | 12.9 | 56.1 | No | 7 | 3 | 500131 | PM01 | CM - Calefactor eléctrico estanque HE0012 | 1004666 | 117.3 | 90
2026-W14 | 2026-04-07 | M02 | PAHELE01 | Eléctrica | 29 | 5.8 | 7.4 | 2 | 15.2 | 52.4 | No | 3 | 2 | 500124 | PM01 | CM - Extractor taller EMP |  | 145.9 | 90
2026-W14 | 2026-04-07 | M02 | PAHELE01 | Instrumentación | 26 | 11.4 | 5.2 | 2.4 | 19 | 73.1 | No | 2 | 2 | 500162 | PM02 | PM - Tecle bomba sumergible lixiviación |  | 32.5 | 90
2026-W14 | 2026-04-07 | M02 | PAHINS01 | Mecánica | 24 | 11.3 | 5.1 | 0.2 | 16.6 | 69.2 | No | 5 | 2 | 500064 | PM01 | CM - Válvula control drenaje relaves alimentación HV4602 |  | 156.1 | 90
2026-W14 | 2026-04-07 | M02 | PAHINS01 | Eléctrica | 18 | 7 | 4.4 | 0.2 | 11.6 | 64.4 | No | 4 | 3 | 500024 | PM02 | PM - Válvula alivio presión aceite PRV0664 |  | 67.4 | 90
2026-W14 | 2026-04-07 | M02 | PAHINS01 | Instrumentación | 25 | 5.6 | 6.9 | 1.1 | 13.6 | 54.4 | No | 3 | 2 | 500015 | PM02 | PM - Sensor temperatura aire TS4591 |  | 77.7 | 90
2026-W14 | 2026-04-07 | P01 | PASMEC01 | Mecánica | 39 | 10.6 | 7.7 | 2 | 20.3 | 52.1 | No | 7 | 2 | 500027 | PM02 | PM - Válvula control aceite XV4883 |  | 44.3 | 90
2026-W14 | 2026-04-07 | P01 | PASMEC01 | Eléctrica | 26 | 9 | 4.1 | 2.1 | 15.2 | 58.5 | No | 6 | 4 | 500174 | PM02 | PM - Bomba precipitado |  | 163.3 | 90
2026-W14 | 2026-04-07 | P01 | PASMEC01 | Instrumentación | 36 | 14.6 | 4.9 | 2.7 | 22.2 | 61.7 | No | 3 | 1 | 500093 | PM02 | PM - Sensor temperatura horno TE3533 |  | 43.5 | 90
2026-W14 | 2026-04-07 | P01 | PASELE01 | Mecánica | 16 | 6.6 | 4.4 | 0.1 | 11.1 | 69.4 | No | 5 | 3 | 500079 | PM02 | PM - Gabinete RIO |  | 122.8 | 90
2026-W14 | 2026-04-07 | P01 | PASELE01 | Eléctrica | 31 | 11.3 | 3.8 | 1.7 | 16.8 | 54.2 | No | 7 | 2 | 500050 | PM01 | CM - Línea agua sell 3700-5476-AA1A-3"-WGS-ET |  | 177.6 | 90
2026-W14 | 2026-04-07 | P01 | PASELE01 | Instrumentación | 26 | 11.8 | 3.8 | 1.8 | 17.4 | 66.9 | No | 3 | 2 | 500131 | PM01 | CM - Calefactor eléctrico estanque HE0012 |  | 87.1 | 90
2026-W14 | 2026-04-07 | P01 | PASINS01 | Mecánica | 26 | 5.9 | 6.6 | 2.1 | 14.6 | 56.2 | No | 5 | 3 | 500172 | PM02 | PM - Tablero de comunicación | 1003900 | 71 | 90
2026-W14 | 2026-04-07 | P01 | PASINS01 | Eléctrica | 25 | 10.3 | 5.6 | 0.9 | 16.8 | 67.2 | No | 3 | 2 | 500122 | PM01 | CM - Carro mantención regeneración carbon | 1000527 | 73 | 90
2026-W14 | 2026-04-07 | P01 | PASINS01 | Instrumentación | 39 | 15.6 | 5.7 | 1.2 | 22.5 | 57.7 | No | 3 | 2 | 500153 | PM02 | PM - Sistema Spray Grasa Engranaje - Molino SAG | 1006599 | 167.2 | 90
2026-W14 | 2026-04-07 | P01 | PAHMEC01 | Mecánica | 24 | 6.1 | 3.3 | 0.5 | 9.9 | 41.2 | No | 6 | 4 | 500017 | PM02 | PM - Indicador presión agua PI0423 |  | 109.7 | 90
2026-W14 | 2026-04-07 | P01 | PAHMEC01 | Eléctrica | 37 | 7.2 | 3.2 | 0 | 10.4 | 28.1 | No | 7 | 3 | 500084 | PM02 | PM - Motor eléctrico HY0001M1 |  | 147 | 90
2026-W14 | 2026-04-07 | P01 | PAHMEC01 | Instrumentación | 30 | 6.5 | 4 | 2.3 | 12.8 | 42.7 | No | 6 | 3 | 500166 | PM02 | PM - Bomba muestreo pulpa relaves PU0267 |  | 169 | 90
2026-W14 | 2026-04-07 | P01 | PAHELE01 | Mecánica | 20 | 4.2 | 4.3 | 1.6 | 10.1 | 50.5 | No | 6 | 1 | 500188 | PM01 | CM - Switch posición ZS1716 | 1005110 | 193.1 | 90
2026-W14 | 2026-04-07 | P01 | PAHELE01 | Eléctrica | 30 | 9.1 | 3.6 | 2.8 | 15.5 | 51.7 | No | 5 | 1 | 500117 | PM01 | CM - Válvula control agua filtrada HV4568B | 1000584 | 121.4 | 90
2026-W14 | 2026-04-07 | P01 | PAHELE01 | Instrumentación | 28 | 4 | 3.5 | 2.6 | 10.1 | 36.1 | No | 2 | 2 | 500139 | PM02 | PM - Hidrante/ Grifos FH0136 |  | 40.4 | 90
2026-W14 | 2026-04-07 | P01 | PAHINS01 | Mecánica | 18 | 8.3 | 3.6 | 1.8 | 13.7 | 76.1 | No | 6 | 1 | 500072 | PM02 | PM - Válvula control flujo entrada agua rechazo FV3576 |  | 33.3 | 90
2026-W14 | 2026-04-07 | P01 | PAHINS01 | Eléctrica | 30 | 15 | 7.1 | 0.3 | 22.4 | 74.7 | No | 2 | 3 | 500064 | PM01 | CM - Válvula control drenaje relaves alimentación HV4602 | 1003567 | 35.6 | 90
2026-W14 | 2026-04-07 | P01 | PAHINS01 | Instrumentación | 38 | 18.4 | 3.7 | 0.7 | 22.8 | 60 | No | 3 | 3 | 500095 | PM02 | PM - Bomba sumidero lixiviación |  | 103.7 | 90
2026-W14 | 2026-04-07 | P02 | PASMEC01 | Mecánica | 32 | 11.2 | 6.6 | 0.2 | 18 | 56.2 | No | 3 | 1 | 500011 | PM02 | PM - Válvula control agua sello HV2723 |  | 117.9 | 90
2026-W14 | 2026-04-07 | P02 | PASMEC01 | Eléctrica | 29 | 9.5 | 6.1 | 0.8 | 16.4 | 56.6 | No | 5 | 4 | 500033 | PM02 | PM - Válvula control entrada lechada cal HV5311 |  | 112 | 90
2026-W14 | 2026-04-07 | P02 | PASMEC01 | Instrumentación | 19 | 7.5 | 2.6 | 0.8 | 10.9 | 57.4 | No | 7 | 2 | 500169 | PM02 | PM - Celosía XM0114 | 1000214 | 22.7 | 90
2026-W14 | 2026-04-07 | P02 | PASELE01 | Mecánica | 33 | 11.4 | 3.1 | 1.4 | 15.9 | 48.2 | No | 6 | 1 | 500179 | PM01 | CM - Transmisor nivel atricción carbón LIT3627 | 1002449 | 127.8 | 90
2026-W14 | 2026-04-07 | P02 | PASELE01 | Eléctrica | 35 | 15.8 | 10 | 2.8 | 28.6 | 81.7 | No | 2 | 2 | 500076 | PM02 | PM - Cajón (Futuro) |  | 93.9 | 90
2026-W14 | 2026-04-07 | P02 | PASELE01 | Instrumentación | 25 | 6.6 | 4.2 | 0.8 | 11.6 | 46.4 | No | 2 | 4 | 500160 | PM02 | PM - Gabinete control Chancador Primario | 1005430 | 193.1 | 90
2026-W14 | 2026-04-07 | P02 | PASINS01 | Mecánica | 31 | 6.2 | 3.1 | 0.3 | 9.6 | 31 | No | 7 | 3 | 500086 | PM02 | PM - Sensor nivel refrigerante LE0177 |  | 133 | 90
2026-W14 | 2026-04-07 | P02 | PASINS01 | Eléctrica | 18 | 6.7 | 4.7 | 1.5 | 12.9 | 71.7 | No | 2 | 2 | 500161 | PM02 | PM - Unidad aire acondicionado |  | 168.4 | 90
2026-W14 | 2026-04-07 | P02 | PASINS01 | Instrumentación | 28 | 7.2 | 7 | 0.1 | 14.3 | 51.1 | No | 2 | 3 | 500160 | PM02 | PM - Gabinete control Chancador Primario |  | 163.2 | 90
2026-W14 | 2026-04-07 | P02 | PAHMEC01 | Mecánica | 24 | 8.1 | 2.3 | 1.3 | 11.7 | 48.8 | No | 3 | 1 | 500097 | PM02 | PM - Gabinete RIO |  | 127.6 | 90
2026-W14 | 2026-04-07 | P02 | PAHMEC01 | Eléctrica | 37 | 11 | 6.7 | 3.6 | 21.3 | 57.6 | No | 7 | 2 | 500033 | PM02 | PM - Válvula control entrada lechada cal HV5311 |  | 58.7 | 90
2026-W14 | 2026-04-07 | P02 | PAHMEC01 | Instrumentación | 17 | 4.3 | 3.6 | 0.2 | 8.1 | 47.6 | No | 2 | 1 | 500158 | PM02 | PM - Válvula control flujo sol barren FV5601 | 1006260 | 72.2 | 90
2026-W14 | 2026-04-07 | P02 | PAHELE01 | Mecánica | 33 | 5.1 | 6 | 3 | 14.1 | 42.7 | No | 7 | 1 | 500154 | PM02 | PM - Lava ojos emergencia |  | 48.2 | 90
2026-W14 | 2026-04-07 | P02 | PAHELE01 | Eléctrica | 30 | 5.2 | 6.7 | 0.9 | 12.8 | 42.7 | No | 5 | 1 | 500166 | PM02 | PM - Bomba muestreo pulpa relaves PU0267 |  | 126.4 | 90
2026-W14 | 2026-04-07 | P02 | PAHELE01 | Instrumentación | 33 | 5.5 | 2.7 | 3 | 11.2 | 33.9 | No | 4 | 3 | 500174 | PM02 | PM - Bomba precipitado |  | 94.9 | 90
2026-W14 | 2026-04-07 | P02 | PAHINS01 | Mecánica | 19 | 6.8 | 3.5 | 1.6 | 11.9 | 62.6 | No | 2 | 3 | 500143 | PM02 | PM - Transmisor nivel solución barren LIT2787 |  | 160.6 | 90
2026-W14 | 2026-04-07 | P02 | PAHINS01 | Eléctrica | 32 | 5.3 | 5.9 | 2.4 | 13.6 | 42.5 | No | 2 | 4 | 500119 | PM01 | CM - Calefactor eléctrico HE0137 | 1001896 | 133.2 | 90
2026-W14 | 2026-04-07 | P02 | PAHINS01 | Instrumentación | 22 | 4.5 | 6.2 | 2.1 | 12.8 | 58.2 | No | 3 | 2 | 500061 | PM01 | CM - Transmisor presión aceite PIT4875 |  | 115.8 | 90
2026-W14 | 2026-04-08 | M01 | PASMEC01 | Mecánica | 38 | 14.7 | 5 | 1.2 | 20.9 | 55 | No | 2 | 4 | 500134 | PM02 | PM - Intercambiador calor por aire CQ0007 |  | 67.5 | 90
2026-W14 | 2026-04-08 | M01 | PASMEC01 | Eléctrica | 24 | 4.7 | 5.2 | 0.8 | 10.7 | 44.6 | No | 4 | 1 | 500073 | PM02 | PM - Válvula control sol barren a estanque HV3266 | 1001440 | 106.1 | 90
2026-W14 | 2026-04-08 | M01 | PASMEC01 | Instrumentación | 21 | 5.2 | 5.3 | 0.6 | 11.1 | 52.9 | No | 2 | 1 | 500041 | PM02 | PM - Tecle bomba sumergible lixiviación |  | 57.1 | 90
2026-W14 | 2026-04-08 | M01 | PASELE01 | Mecánica | 38 | 12 | 10 | 0 | 22 | 57.9 | No | 7 | 2 | 500008 | PM02 | PM - Bomba precipitado |  | 39.1 | 90
2026-W14 | 2026-04-08 | M01 | PASELE01 | Eléctrica | 32 | 5.8 | 5.9 | 1.5 | 13.2 | 41.2 | No | 4 | 1 | 500092 | PM02 | PM - Bomba precipitado |  | 187.4 | 90
2026-W14 | 2026-04-08 | M01 | PASELE01 | Instrumentación | 30 | 12.3 | 5.4 | 0.3 | 18 | 60 | No | 3 | 2 | 500062 | PM01 | CM - Transmisor nivel lechada cal LIT5271 | 1002431 | 77.6 | 90
2026-W14 | 2026-04-08 | M01 | PASINS01 | Mecánica | 34 | 15.2 | 7.2 | 2.6 | 25 | 73.5 | No | 5 | 3 | 500007 | PM02 | PM - Transmisor vibración VT0020A |  | 84.1 | 90
2026-W14 | 2026-04-08 | M01 | PASINS01 | Eléctrica | 19 | 8.4 | 5.2 | 0.9 | 14.5 | 76.3 | No | 6 | 4 | 500132 | PM02 | PM - Válvula control agua sello HV2723 |  | 196 | 90
2026-W14 | 2026-04-08 | M01 | PASINS01 | Instrumentación | 26 | 12.3 | 5.8 | 1 | 19.1 | 73.5 | No | 5 | 4 | 500022 | PM02 | PM - Unidad re-potabilizadora agua |  | 141 | 90
2026-W14 | 2026-04-08 | M01 | PAHMEC01 | Mecánica | 27 | 9.8 | 4.5 | 2.5 | 16.8 | 62.2 | No | 4 | 1 | 500003 | PM02 | PM - Tablero de comunicación | 1004970 | 173.1 | 90
2026-W14 | 2026-04-08 | M01 | PAHMEC01 | Eléctrica | 19 | 7 | 4.4 | 0.7 | 12.1 | 63.7 | No | 2 | 1 | 500014 | PM02 | PM - Válvula control descarga agua filtrado HV4824 | 1007158 | 150 | 90
2026-W14 | 2026-04-08 | M01 | PAHMEC01 | Instrumentación | 21 | 8.3 | 4.2 | 0.3 | 12.8 | 61 | No | 4 | 1 | 500012 | PM02 | PM - Gabinete PLC horno fundición 1 |  | 105.5 | 90
2026-W14 | 2026-04-08 | M01 | PAHELE01 | Mecánica | 36 | 9.4 | 8.7 | 1.1 | 19.2 | 53.3 | No | 2 | 1 | 500141 | PM02 | PM - Lava ojos emergencia |  | 116.8 | 90
2026-W14 | 2026-04-08 | M01 | PAHELE01 | Eléctrica | 31 | 4.5 | 6.1 | 2.4 | 13 | 41.9 | No | 7 | 2 | 500122 | PM01 | CM - Carro mantención regeneración carbon | 1000750 | 61.2 | 90
2026-W14 | 2026-04-08 | M01 | PAHELE01 | Instrumentación | 30 | 4.2 | 7.3 | 1.4 | 12.9 | 43 | No | 5 | 3 | 500100 | PM02 | PM - Puerta enrollable Stockpile |  | 104.3 | 90
2026-W14 | 2026-04-08 | M01 | PAHINS01 | Mecánica | 35 | 8.9 | 6.6 | 2.4 | 17.9 | 51.1 | No | 7 | 3 | 500119 | PM01 | CM - Calefactor eléctrico HE0137 | 1002336 | 111.6 | 90
2026-W14 | 2026-04-08 | M01 | PAHINS01 | Eléctrica | 37 | 9.8 | 10.7 | 2.4 | 22.9 | 61.9 | No | 5 | 2 | 500051 | PM01 | CM - Tablero distribución UPS | 1001990 | 144.4 | 90
2026-W14 | 2026-04-08 | M01 | PAHINS01 | Instrumentación | 16 | 7.4 | 3.2 | 0.2 | 10.8 | 67.5 | No | 3 | 2 | 500146 | PM02 | PM - Válvula control alimenta pulpa HV1501C |  | 123.9 | 90
2026-W14 | 2026-04-08 | M02 | PASMEC01 | Mecánica | 29 | 8.3 | 5.7 | 1.3 | 15.3 | 52.8 | No | 7 | 1 | 500037 | PM02 | PM - Sirena YA1151 |  | 83.6 | 90
2026-W14 | 2026-04-08 | M02 | PASMEC01 | Eléctrica | 39 | 4.6 | 3.9 | 2.1 | 10.6 | 27.2 | No | 2 | 2 | 500105 | PM02 | PM - Tablero SCI |  | 78.6 | 90
2026-W14 | 2026-04-08 | M02 | PASMEC01 | Instrumentación | 38 | 17.2 | 2.4 | 3.1 | 22.7 | 59.7 | No | 7 | 4 | 500156 | PM02 | PM - Hidrante/ Grifos FH0138 | 1004131 | 173.8 | 90
2026-W14 | 2026-04-08 | M02 | PASELE01 | Mecánica | 30 | 7.8 | 6.9 | 0.5 | 15.2 | 50.7 | No | 5 | 2 | 500189 | PM01 | CM - Switch gear SAG 630 A, 6.9 Kv, 31.5 kA | 1006079 | 92.8 | 90
2026-W14 | 2026-04-08 | M02 | PASELE01 | Eléctrica | 33 | 15.4 | 4.7 | 2.1 | 22.2 | 67.3 | No | 4 | 1 | 500097 | PM02 | PM - Gabinete RIO |  | 53.6 | 90
2026-W14 | 2026-04-08 | M02 | PASELE01 | Instrumentación | 32 | 8.4 | 7.2 | 1.2 | 16.8 | 52.5 | No | 4 | 3 | 500049 | PM01 | CM - Válvula control alimenta pulpa HV1501K |  | 20 | 90
2026-W14 | 2026-04-08 | M02 | PASINS01 | Mecánica | 27 | 10.4 | 3.5 | 0 | 13.9 | 51.5 | No | 2 | 3 | 500159 | PM02 | PM - Gabinete manguera y equipo contraincendios HH0119 |  | 129.2 | 90
2026-W14 | 2026-04-08 | M02 | PASINS01 | Eléctrica | 38 | 11.6 | 10.1 | 0.9 | 22.6 | 59.5 | No | 5 | 3 | 500024 | PM02 | PM - Válvula alivio presión aceite PRV0664 |  | 84.2 | 90
2026-W14 | 2026-04-08 | M02 | PASINS01 | Instrumentación | 35 | 7.1 | 8.3 | 1.1 | 16.5 | 47.1 | No | 4 | 1 | 500004 | PM02 | PM - Válvula control aceite XV0256D |  | 146.1 | 90
2026-W14 | 2026-04-08 | M02 | PAHMEC01 | Mecánica | 38 | 11.4 | 2.4 | 3.7 | 17.5 | 46.1 | No | 2 | 4 | 500126 | PM01 | CM - Válvula control salida carbon descargado HV3394 |  | 47.4 | 90
2026-W14 | 2026-04-08 | M02 | PAHMEC01 | Eléctrica | 24 | 6.3 | 5 | 1.4 | 12.7 | 52.9 | No | 5 | 3 | 500152 | PM02 | PM - Válvula control entrada pulpa HV1706 |  | 170.5 | 90
2026-W14 | 2026-04-08 | M02 | PAHMEC01 | Instrumentación | 33 | 16.5 | 3.2 | 2.8 | 22.5 | 68.2 | No | 2 | 4 | 500179 | PM01 | CM - Transmisor nivel atricción carbón LIT3627 | 1006564 | 126.3 | 90
2026-W14 | 2026-04-08 | M02 | PAHELE01 | Mecánica | 26 | 9.8 | 2.9 | 2.4 | 15.1 | 58.1 | No | 2 | 3 | 500117 | PM01 | CM - Válvula control agua filtrada HV4568B | 1003812 | 151.3 | 90
2026-W14 | 2026-04-08 | M02 | PAHELE01 | Eléctrica | 32 | 13.5 | 3 | 1.4 | 17.9 | 55.9 | No | 6 | 1 | 500066 | PM02 | PM - Hidrante/ Grifos FH0137 |  | 74.5 | 90
2026-W14 | 2026-04-08 | M02 | PAHELE01 | Instrumentación | 34 | 10.3 | 6 | 0.4 | 16.7 | 49.1 | No | 2 | 2 | 500164 | PM02 | PM - Bomba muestreo pulpa relaves PU0267 |  | 64.5 | 90
2026-W14 | 2026-04-08 | M02 | PAHINS01 | Mecánica | 16 | 5.6 | 3.3 | 0 | 8.9 | 55.6 | No | 5 | 4 | 500170 | PM02 | PM - Switch posición ZS0038A |  | 160.1 | 90
2026-W14 | 2026-04-08 | M02 | PAHINS01 | Eléctrica | 39 | 11 | 5.3 | 1.5 | 17.8 | 45.6 | No | 3 | 3 | 500186 | PM01 | CM - Tablero distribución instrumentación |  | 186.4 | 90
2026-W14 | 2026-04-08 | M02 | PAHINS01 | Instrumentación | 38 | 9.5 | 6.1 | 2.4 | 18 | 47.4 | No | 6 | 2 | 500012 | PM02 | PM - Gabinete PLC horno fundición 1 |  | 165 | 90
2026-W14 | 2026-04-08 | P01 | PASMEC01 | Mecánica | 19 | 7.2 | 4.4 | 1.1 | 12.7 | 66.8 | No | 2 | 3 | 500018 | PM02 | PM - Transmisor presión aceite PIT4875 |  | 80.4 | 90
2026-W14 | 2026-04-08 | P01 | PASMEC01 | Eléctrica | 35 | 9.8 | 6.1 | 2.3 | 18.2 | 52 | No | 6 | 4 | 500143 | PM02 | PM - Transmisor nivel solución barren LIT2787 |  | 114.3 | 90
2026-W14 | 2026-04-08 | P01 | PASMEC01 | Instrumentación | 37 | 8.5 | 2.8 | 0.3 | 11.6 | 31.4 | No | 5 | 4 | 500026 | PM02 | PM - Estanque almacenamiento aceite hidráulico TK0088 |  | 144.1 | 90
2026-W14 | 2026-04-08 | P01 | PASELE01 | Mecánica | 32 | 4.5 | 4.4 | 1 | 9.9 | 30.9 | No | 6 | 2 | 500087 | PM02 | PM - Línea agua sell 3700-5476-AA1A-3"-WGS-ET |  | 137.8 | 90
2026-W14 | 2026-04-08 | P01 | PASELE01 | Eléctrica | 22 | 10.2 | 2 | 0.4 | 12.6 | 57.3 | No | 5 | 3 | 500014 | PM02 | PM - Válvula control descarga agua filtrado HV4824 |  | 130.4 | 90
2026-W14 | 2026-04-08 | P01 | PASELE01 | Instrumentación | 35 | 8.2 | 6.1 | 2.3 | 16.6 | 47.4 | No | 3 | 4 | 500119 | PM01 | CM - Calefactor eléctrico HE0137 | 1004006 | 194.5 | 90
2026-W14 | 2026-04-08 | P01 | PASINS01 | Mecánica | 20 | 9.5 | 3.6 | 0.4 | 13.5 | 67.5 | No | 5 | 1 | 500041 | PM02 | PM - Tecle bomba sumergible lixiviación |  | 183.5 | 90
2026-W14 | 2026-04-08 | P01 | PASINS01 | Eléctrica | 19 | 5.8 | 2 | 1.3 | 9.1 | 47.9 | No | 6 | 1 | 500060 | PM01 | CM - Indicador presión descarga agua PI5057 | 1000014 | 108.5 | 90
2026-W14 | 2026-04-08 | P01 | PASINS01 | Instrumentación | 37 | 16.8 | 5.7 | 1.8 | 24.3 | 65.7 | No | 7 | 1 | 500084 | PM02 | PM - Motor eléctrico HY0001M1 |  | 106.2 | 90
2026-W14 | 2026-04-08 | P01 | PAHMEC01 | Mecánica | 33 | 15.8 | 4.2 | 1.5 | 21.5 | 65.2 | No | 7 | 2 | 500070 | PM02 | PM - Transmisor nivel hidrox sodio LIT3467 |  | 49.2 | 90
2026-W14 | 2026-04-08 | P01 | PAHMEC01 | Eléctrica | 37 | 14.7 | 9.9 | 2.3 | 26.9 | 72.7 | No | 2 | 1 | 500089 | PM02 | PM - Transmisor presión salida sol barren PIT3241 |  | 159.4 | 90
2026-W14 | 2026-04-08 | P01 | PAHMEC01 | Instrumentación | 18 | 4.7 | 4.6 | 0.5 | 9.8 | 54.4 | No | 2 | 3 | 500066 | PM02 | PM - Hidrante/ Grifos FH0137 |  | 132.7 | 90
2026-W14 | 2026-04-08 | P01 | PAHELE01 | Mecánica | 21 | 7.3 | 2.3 | 0.6 | 10.2 | 48.6 | No | 4 | 1 | 500005 | PM02 | PM - Válvula control succión agua fresca HV7808 |  | 63.1 | 90
2026-W14 | 2026-04-08 | P01 | PAHELE01 | Eléctrica | 36 | 16.5 | 4.4 | 3 | 23.9 | 66.4 | No | 4 | 2 | 500168 | PM02 | PM - Gabinete RIO |  | 103.1 | 90
2026-W14 | 2026-04-08 | P01 | PAHELE01 | Instrumentación | 35 | 7.9 | 8.3 | 0.2 | 16.4 | 46.9 | No | 3 | 4 | 500164 | PM02 | PM - Bomba muestreo pulpa relaves PU0267 |  | 109.9 | 90
2026-W14 | 2026-04-08 | P01 | PAHINS01 | Mecánica | 34 | 13.2 | 2.4 | 2.9 | 18.5 | 54.4 | No | 7 | 2 | 500047 | PM01 | CM - Indicador presión agua PI0251 | 1003082 | 67.2 | 90
2026-W14 | 2026-04-08 | P01 | PAHINS01 | Eléctrica | 39 | 18 | 9.9 | 1.4 | 29.3 | 75.1 | No | 6 | 3 | 500118 | PM01 | CM - Gabinete RIO | 1001994 | 84.2 | 90
2026-W14 | 2026-04-08 | P01 | PAHINS01 | Instrumentación | 39 | 11.4 | 11.6 | 3 | 26 | 66.7 | No | 5 | 4 | 500093 | PM02 | PM - Sensor temperatura horno TE3533 |  | 110.3 | 90
2026-W14 | 2026-04-08 | P02 | PASMEC01 | Mecánica | 32 | 15.8 | 3 | 1 | 19.8 | 61.9 | No | 5 | 2 | 500094 | PM02 | PM - Switch baja presión descarga fluido térmico PSL3498 | 1006277 | 106 | 90
2026-W14 | 2026-04-08 | P02 | PASMEC01 | Eléctrica | 18 | 7 | 3.3 | 0.9 | 11.2 | 62.2 | No | 3 | 4 | 500020 | PM02 | PM - Cajón (Futuro) |  | 120.8 | 90
2026-W14 | 2026-04-08 | P02 | PASMEC01 | Instrumentación | 33 | 10.3 | 3.4 | 2.7 | 16.4 | 49.7 | No | 5 | 1 | 500001 | PM02 | PM - Válvula control entrada lechada cal AV1902B |  | 60.4 | 90
2026-W14 | 2026-04-08 | P02 | PASELE01 | Mecánica | 30 | 14.3 | 8.6 | 1.1 | 24 | 80 | No | 3 | 3 | 500118 | PM01 | CM - Gabinete RIO | 1003193 | 113.3 | 90
2026-W14 | 2026-04-08 | P02 | PASELE01 | Eléctrica | 29 | 13.6 | 4 | 1.4 | 19 | 65.5 | No | 4 | 3 | 500107 | PM02 | PM - Gabinete manguera y equipo contraincendios HH0105 |  | 95.7 | 90
2026-W14 | 2026-04-08 | P02 | PASELE01 | Instrumentación | 22 | 7.2 | 2.8 | 0.6 | 10.6 | 48.2 | No | 7 | 2 | 500165 | PM02 | PM - Motor eléctrico HY0036M1 |  | 160.7 | 90
2026-W14 | 2026-04-08 | P02 | PASINS01 | Mecánica | 26 | 5 | 2.6 | 0 | 7.6 | 29.2 | No | 2 | 3 | 500120 | PM01 | CM - Transmisor presión salida sol barren PIT3241 |  | 64 | 90
2026-W14 | 2026-04-08 | P02 | PASINS01 | Eléctrica | 26 | 8.9 | 7.6 | 0.7 | 17.2 | 66.2 | No | 6 | 1 | 500156 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 118.4 | 90
2026-W14 | 2026-04-08 | P02 | PASINS01 | Instrumentación | 32 | 15.4 | 5.2 | 0 | 20.6 | 64.4 | No | 6 | 3 | 500134 | PM02 | PM - Intercambiador calor por aire CQ0007 |  | 28.3 | 90
2026-W14 | 2026-04-08 | P02 | PAHMEC01 | Mecánica | 24 | 11.1 | 3.9 | 0.3 | 15.3 | 63.8 | No | 7 | 3 | 500189 | PM01 | CM - Switch gear SAG 630 A, 6.9 Kv, 31.5 kA | 1002382 | 49.6 | 90
2026-W14 | 2026-04-08 | P02 | PAHMEC01 | Eléctrica | 30 | 14.6 | 7.5 | 0.1 | 22.2 | 74 | No | 5 | 2 | 500130 | PM01 | CM - Tablero de enchufes | 1001317 | 145.2 | 90
2026-W14 | 2026-04-08 | P02 | PAHMEC01 | Instrumentación | 20 | 4.3 | 4.7 | 1.7 | 10.7 | 53.5 | No | 3 | 1 | 500020 | PM02 | PM - Cajón (Futuro) | 1007169 | 166.2 | 90
2026-W14 | 2026-04-08 | P02 | PAHELE01 | Mecánica | 16 | 7.3 | 4.6 | 1 | 12.9 | 80.6 | No | 4 | 2 | 500119 | PM01 | CM - Calefactor eléctrico HE0137 | 1002533 | 65.7 | 90
2026-W14 | 2026-04-08 | P02 | PAHELE01 | Eléctrica | 39 | 4.7 | 9 | 1.7 | 15.4 | 39.5 | No | 4 | 3 | 500059 | PM01 | CM - Mezclador floculante | 1001009 | 54.3 | 90
2026-W14 | 2026-04-08 | P02 | PAHELE01 | Instrumentación | 37 | 9.9 | 5 | 2.8 | 17.7 | 47.8 | No | 6 | 3 | 500179 | PM01 | CM - Transmisor nivel atricción carbón LIT3627 | 1004586 | 28.7 | 90
2026-W14 | 2026-04-08 | P02 | PAHINS01 | Mecánica | 35 | 10.5 | 5 | 1.1 | 16.6 | 47.4 | No | 5 | 4 | 500020 | PM02 | PM - Cajón (Futuro) |  | 135.5 | 90
2026-W14 | 2026-04-08 | P02 | PAHINS01 | Eléctrica | 22 | 4.2 | 2.3 | 1.5 | 8 | 36.4 | No | 6 | 4 | 500043 | PM02 | PM - Sirena YA3453 | 1004313 | 157.4 | 90
2026-W14 | 2026-04-08 | P02 | PAHINS01 | Instrumentación | 16 | 6.4 | 3.6 | 0.1 | 10.1 | 63.1 | No | 4 | 4 | 500050 | PM01 | CM - Línea agua sell 3700-5476-AA1A-3"-WGS-ET |  | 132.1 | 90
2026-W14 | 2026-04-09 | M01 | PASMEC01 | Mecánica | 24 | 8 | 4.8 | 0.7 | 13.5 | 56.2 | No | 2 | 4 | 500039 | PM02 | PM - Chute carbónHO0068 |  | 150 | 90
2026-W14 | 2026-04-09 | M01 | PASMEC01 | Eléctrica | 21 | 4.7 | 4.1 | 0.3 | 9.1 | 43.3 | No | 3 | 3 | 500171 | PM02 | PM - Switch bajo nivel aceite LSL0253 |  | 48.5 | 90
2026-W14 | 2026-04-09 | M01 | PASMEC01 | Instrumentación | 26 | 7.3 | 5.7 | 0.3 | 13.3 | 51.2 | No | 5 | 2 | 500172 | PM02 | PM - Tablero de comunicación |  | 69.4 | 90
2026-W14 | 2026-04-09 | M01 | PASELE01 | Mecánica | 32 | 12 | 2.5 | 0.8 | 15.3 | 47.8 | No | 4 | 1 | 500151 | PM02 | PM - Válvula control flujo entrada agua rechazo FV3576 | 1004404 | 106.4 | 90
2026-W14 | 2026-04-09 | M01 | PASELE01 | Eléctrica | 32 | 4.4 | 9.3 | 1.7 | 15.4 | 48.1 | No | 4 | 3 | 500080 | PM02 | PM - Válvula control aire soplado HV4658 |  | 21 | 90
2026-W14 | 2026-04-09 | M01 | PASELE01 | Instrumentación | 39 | 19.3 | 2.4 | 2.6 | 24.3 | 62.3 | No | 2 | 4 | 500124 | PM01 | CM - Extractor taller EMP | 1002034 | 190.8 | 90
2026-W14 | 2026-04-09 | M01 | PASINS01 | Mecánica | 37 | 7.4 | 7.5 | 1.5 | 16.4 | 44.3 | No | 7 | 3 | 500085 | PM02 | PM - Gabinete servidor core switch 1 y commun | 1001800 | 54.9 | 90
2026-W14 | 2026-04-09 | M01 | PASINS01 | Eléctrica | 25 | 9.6 | 3.3 | 0.2 | 13.1 | 52.4 | No | 2 | 3 | 500157 | PM02 | PM - Tablero distribución instrumentación |  | 189.6 | 90
2026-W14 | 2026-04-09 | M01 | PASINS01 | Instrumentación | 36 | 5.1 | 10.7 | 2.8 | 18.6 | 51.7 | No | 5 | 3 | 500005 | PM02 | PM - Válvula control succión agua fresca HV7808 |  | 55.1 | 90
2026-W14 | 2026-04-09 | M01 | PAHMEC01 | Mecánica | 26 | 12.5 | 4.3 | 1.8 | 18.6 | 71.5 | No | 2 | 1 | 500175 | PM01 | CM - Válvula control aceite XV0279 | 1006455 | 43.1 | 90
2026-W14 | 2026-04-09 | M01 | PAHMEC01 | Eléctrica | 18 | 6.3 | 3.6 | 1.3 | 11.2 | 62.2 | No | 4 | 3 | 500119 | PM01 | CM - Calefactor eléctrico HE0137 |  | 79.3 | 90
2026-W14 | 2026-04-09 | M01 | PAHMEC01 | Instrumentación | 32 | 4.2 | 3.2 | 3.2 | 10.6 | 33.1 | No | 2 | 4 | 500158 | PM02 | PM - Válvula control flujo sol barren FV5601 |  | 142.2 | 90
2026-W14 | 2026-04-09 | M01 | PAHELE01 | Mecánica | 32 | 15.3 | 3.5 | 2.8 | 21.6 | 67.5 | No | 5 | 1 | 500145 | PM02 | PM - Transmisor presion agua PT0404 |  | 137.9 | 90
2026-W14 | 2026-04-09 | M01 | PAHELE01 | Eléctrica | 26 | 11.6 | 4.8 | 1 | 17.4 | 66.9 | No | 6 | 1 | 500047 | PM01 | CM - Indicador presión agua PI0251 | 1004684 | 124.2 | 90
2026-W14 | 2026-04-09 | M01 | PAHELE01 | Instrumentación | 31 | 14.4 | 6.9 | 2 | 23.3 | 75.2 | No | 4 | 2 | 500072 | PM02 | PM - Válvula control flujo entrada agua rechazo FV3576 |  | 128.8 | 90
2026-W14 | 2026-04-09 | M01 | PAHINS01 | Mecánica | 32 | 4.9 | 6 | 1.3 | 12.2 | 38.1 | No | 4 | 3 | 500033 | PM02 | PM - Válvula control entrada lechada cal HV5311 |  | 36.1 | 90
2026-W14 | 2026-04-09 | M01 | PAHINS01 | Eléctrica | 28 | 9 | 7 | 2.4 | 18.4 | 65.7 | No | 3 | 2 | 500031 | PM02 | PM - Celosía XM0114 |  | 131.4 | 90
2026-W14 | 2026-04-09 | M01 | PAHINS01 | Instrumentación | 16 | 7.6 | 2.1 | 0.6 | 10.3 | 64.4 | No | 6 | 4 | 500053 | PM01 | CM - Indicador presión aceite hidráulico PI4895E | 1002409 | 165.8 | 90
2026-W14 | 2026-04-09 | M02 | PASMEC01 | Mecánica | 30 | 10.2 | 7.2 | 2.4 | 19.8 | 66 | No | 2 | 3 | 500090 | PM02 | PM - Válvula control succión sol rica HV2807 |  | 23.3 | 90
2026-W14 | 2026-04-09 | M02 | PASMEC01 | Eléctrica | 26 | 6.2 | 2.4 | 1.8 | 10.4 | 40 | No | 7 | 2 | 500192 | PM01 | CM - Calefactor eléctrico edificio | 1005705 | 110.8 | 90
2026-W14 | 2026-04-09 | M02 | PASMEC01 | Instrumentación | 26 | 6 | 5.9 | 2.5 | 14.4 | 55.4 | No | 2 | 1 | 500161 | PM02 | PM - Unidad aire acondicionado |  | 36.1 | 90
2026-W14 | 2026-04-09 | M02 | PASELE01 | Mecánica | 19 | 6.5 | 2.9 | 1.6 | 11 | 57.9 | No | 6 | 4 | 500176 | PM01 | CM - Válvula control succión nitrato plomo HV2962 |  | 117.8 | 90
2026-W14 | 2026-04-09 | M02 | PASELE01 | Eléctrica | 35 | 8 | 3.6 | 0.4 | 12 | 34.3 | No | 6 | 4 | 500077 | PM02 | PM - Válvula control entrada solucion barren FV2314 |  | 90.3 | 90
2026-W14 | 2026-04-09 | M02 | PASELE01 | Instrumentación | 36 | 6.1 | 6.9 | 1.9 | 14.9 | 41.4 | No | 5 | 3 | 500068 | PM02 | PM - Tecle eléctrico tolva carbon |  | 29.9 | 90
2026-W14 | 2026-04-09 | M02 | PASINS01 | Mecánica | 25 | 9.7 | 3.6 | 1.2 | 14.5 | 58 | No | 6 | 2 | 500102 | PM02 | PM - Ciclo convertidor potencia MI0001SE |  | 57.9 | 90
2026-W14 | 2026-04-09 | M02 | PASINS01 | Eléctrica | 27 | 12 | 5.2 | 2.3 | 19.5 | 72.2 | No | 2 | 1 | 500102 | PM02 | PM - Ciclo convertidor potencia MI0001SE |  | 26.3 | 90
2026-W14 | 2026-04-09 | M02 | PASINS01 | Instrumentación | 19 | 6.5 | 4.8 | 1.8 | 13.1 | 68.9 | No | 4 | 3 | 500082 | PM02 | PM - Válvula control agua filtrada HV4568B |  | 120.3 | 90
2026-W14 | 2026-04-09 | M02 | PAHMEC01 | Mecánica | 38 | 6.5 | 9.8 | 0.7 | 17 | 44.7 | No | 3 | 1 | 500023 | PM02 | PM - Válvula control entrada aire FV1804 |  | 102.6 | 90
2026-W14 | 2026-04-09 | M02 | PAHMEC01 | Eléctrica | 21 | 7.9 | 5.7 | 2.1 | 15.7 | 74.8 | No | 5 | 3 | 500075 | PM02 | PM - Switch posición giro rastras ZS4377D |  | 92.8 | 90
2026-W14 | 2026-04-09 | M02 | PAHMEC01 | Instrumentación | 37 | 7.7 | 6.4 | 1.4 | 15.5 | 41.9 | No | 2 | 3 | 500054 | PM01 | CM - Intercambiador calor calentamiento | 1002773 | 86.3 | 90
2026-W14 | 2026-04-09 | M02 | PAHELE01 | Mecánica | 31 | 10.4 | 8.3 | 2.6 | 21.3 | 68.7 | No | 4 | 2 | 500143 | PM02 | PM - Transmisor nivel solución barren LIT2787 |  | 145.7 | 90
2026-W14 | 2026-04-09 | M02 | PAHELE01 | Eléctrica | 16 | 7.3 | 2.1 | 1.4 | 10.8 | 67.5 | No | 2 | 4 | 500143 | PM02 | PM - Transmisor nivel solución barren LIT2787 |  | 91.7 | 90
2026-W14 | 2026-04-09 | M02 | PAHELE01 | Instrumentación | 28 | 12.5 | 2.9 | 1.5 | 16.9 | 60.4 | No | 6 | 3 | 500060 | PM01 | CM - Indicador presión descarga agua PI5057 | 1001441 | 37.1 | 90
2026-W14 | 2026-04-09 | M02 | PAHINS01 | Mecánica | 35 | 5.9 | 5.7 | 1.7 | 13.3 | 38 | No | 6 | 1 | 500049 | PM01 | CM - Válvula control alimenta pulpa HV1501K | 1006435 | 178 | 90
2026-W14 | 2026-04-09 | M02 | PAHINS01 | Eléctrica | 39 | 18.9 | 7.8 | 3.1 | 29.8 | 76.4 | No | 7 | 1 | 500172 | PM02 | PM - Tablero de comunicación | 1003339 | 80.6 | 90
2026-W14 | 2026-04-09 | M02 | PAHINS01 | Instrumentación | 33 | 6.7 | 6.8 | 1.7 | 15.2 | 46.1 | No | 2 | 4 | 500099 | PM02 | PM - Indicador presión agua PI0251 | 1007118 | 191.5 | 90
2026-W14 | 2026-04-09 | P01 | PASMEC01 | Mecánica | 30 | 10 | 7.8 | 0.4 | 18.2 | 60.7 | No | 6 | 2 | 500074 | PM02 | PM - Transmisor presión agua potable PIT7025 |  | 120.2 | 90
2026-W14 | 2026-04-09 | P01 | PASMEC01 | Eléctrica | 16 | 5.7 | 2.9 | 1 | 9.6 | 60 | No | 2 | 4 | 500009 | PM02 | PM - Estanque diesel dia regeneración carbón |  | 170.6 | 90
2026-W14 | 2026-04-09 | P01 | PASMEC01 | Instrumentación | 36 | 10.9 | 10.5 | 2.8 | 24.2 | 67.2 | No | 3 | 2 | 500026 | PM02 | PM - Estanque almacenamiento aceite hidráulico TK0088 |  | 80.8 | 90
2026-W14 | 2026-04-09 | P01 | PASELE01 | Mecánica | 25 | 6 | 6.3 | 0.1 | 12.4 | 49.6 | No | 4 | 2 | 500156 | PM02 | PM - Hidrante/ Grifos FH0138 | 1001178 | 111 | 90
2026-W14 | 2026-04-09 | P01 | PASELE01 | Eléctrica | 34 | 16.5 | 9.6 | 2.7 | 28.8 | 84.7 | No | 3 | 1 | 500153 | PM02 | PM - Sistema Spray Grasa Engranaje - Molino SAG |  | 69.3 | 90
2026-W14 | 2026-04-09 | P01 | PASELE01 | Instrumentación | 24 | 9.1 | 3.3 | 0.2 | 12.6 | 52.5 | No | 4 | 1 | 500048 | PM01 | CM - Válvula control flujo aire secado FV4662 | 1003372 | 60.4 | 90
2026-W14 | 2026-04-09 | P01 | PASINS01 | Mecánica | 26 | 8.1 | 4.9 | 0.1 | 13.1 | 50.4 | No | 5 | 4 | 500015 | PM02 | PM - Sensor temperatura aire TS4591 |  | 92.8 | 90
2026-W14 | 2026-04-09 | P01 | PASINS01 | Eléctrica | 24 | 6.3 | 6.5 | 1.9 | 14.7 | 61.2 | No | 5 | 2 | 500087 | PM02 | PM - Línea agua sell 3700-5476-AA1A-3"-WGS-ET |  | 154.7 | 90
2026-W14 | 2026-04-09 | P01 | PASINS01 | Instrumentación | 21 | 7 | 3 | 2 | 12 | 57.1 | No | 5 | 3 | 500108 | PM02 | PM - Motor eléctrico HY0036M1 |  | 38.9 | 90
2026-W14 | 2026-04-09 | P01 | PAHMEC01 | Mecánica | 33 | 9.1 | 7.2 | 1.5 | 17.8 | 53.9 | No | 6 | 1 | 500021 | PM02 | PM - Tornillo alimentador sulfato de cobre | 1001015 | 141.6 | 90
2026-W14 | 2026-04-09 | P01 | PAHMEC01 | Eléctrica | 28 | 6.3 | 5.7 | 2.3 | 14.3 | 51.1 | No | 7 | 3 | 500080 | PM02 | PM - Válvula control aire soplado HV4658 |  | 133.6 | 90
2026-W14 | 2026-04-09 | P01 | PAHMEC01 | Instrumentación | 22 | 9 | 4.3 | 2 | 15.3 | 69.5 | No | 2 | 2 | 500124 | PM01 | CM - Extractor taller EMP |  | 152 | 90
2026-W14 | 2026-04-09 | P01 | PAHELE01 | Mecánica | 17 | 5.7 | 3.7 | 0.3 | 9.7 | 57.1 | No | 3 | 4 | 500036 | PM02 | PM - Colector polvo horno fundición |  | 21.5 | 90
2026-W14 | 2026-04-09 | P01 | PAHELE01 | Eléctrica | 19 | 7.2 | 4.6 | 1.7 | 13.5 | 71.1 | No | 5 | 1 | 500015 | PM02 | PM - Sensor temperatura aire TS4591 | 1000141 | 140.9 | 90
2026-W14 | 2026-04-09 | P01 | PAHELE01 | Instrumentación | 36 | 14.1 | 7.9 | 2.5 | 24.5 | 68.1 | No | 5 | 1 | 500019 | PM02 | PM - Transmisor nivel lechada cal LIT5314 | 1006013 | 88.9 | 90
2026-W14 | 2026-04-09 | P01 | PAHINS01 | Mecánica | 31 | 12.4 | 5.8 | 0.2 | 18.4 | 59.4 | No | 7 | 1 | 500117 | PM01 | CM - Válvula control agua filtrada HV4568B | 1003611 | 171.2 | 90
2026-W14 | 2026-04-09 | P01 | PAHINS01 | Eléctrica | 31 | 14.3 | 2.9 | 3.1 | 20.3 | 65.5 | No | 6 | 4 | 500157 | PM02 | PM - Tablero distribución instrumentación |  | 22.1 | 90
2026-W14 | 2026-04-09 | P01 | PAHINS01 | Instrumentación | 20 | 5.8 | 2.7 | 1.6 | 10.1 | 50.5 | No | 2 | 3 | 500035 | PM02 | PM - Agitador estanque filtración |  | 77.6 | 90
2026-W14 | 2026-04-09 | P02 | PASMEC01 | Mecánica | 22 | 5.3 | 4.9 | 0.7 | 10.9 | 49.5 | No | 7 | 3 | 500106 | PM02 | PM - Válvula control succión ayuda filtrante HV3281 |  | 73.2 | 90
2026-W14 | 2026-04-09 | P02 | PASMEC01 | Eléctrica | 31 | 14.4 | 4.9 | 0.8 | 20.1 | 64.8 | No | 5 | 1 | 500146 | PM02 | PM - Válvula control alimenta pulpa HV1501C |  | 77.7 | 90
2026-W14 | 2026-04-09 | P02 | PASMEC01 | Instrumentación | 32 | 15.1 | 9.3 | 0.6 | 25 | 78.1 | No | 6 | 4 | 500077 | PM02 | PM - Válvula control entrada solucion barren FV2314 |  | 48.3 | 90
2026-W14 | 2026-04-09 | P02 | PASELE01 | Mecánica | 18 | 5.7 | 4.3 | 0.7 | 10.7 | 59.4 | No | 2 | 1 | 500089 | PM02 | PM - Transmisor presión salida sol barren PIT3241 |  | 93.1 | 90
2026-W14 | 2026-04-09 | P02 | PASELE01 | Eléctrica | 22 | 8 | 2.2 | 1.2 | 11.4 | 51.8 | No | 7 | 3 | 500007 | PM02 | PM - Transmisor vibración VT0020A |  | 170.8 | 90
2026-W14 | 2026-04-09 | P02 | PASELE01 | Instrumentación | 18 | 4.2 | 3.1 | 1.1 | 8.4 | 46.7 | No | 4 | 2 | 500074 | PM02 | PM - Transmisor presión agua potable PIT7025 |  | 180.9 | 90
2026-W14 | 2026-04-09 | P02 | PASINS01 | Mecánica | 28 | 7.3 | 4.8 | 0.7 | 12.8 | 45.7 | No | 6 | 2 | 500159 | PM02 | PM - Gabinete manguera y equipo contraincendios HH0119 |  | 144 | 90
2026-W14 | 2026-04-09 | P02 | PASINS01 | Eléctrica | 38 | 5.8 | 6.5 | 2.6 | 14.9 | 39.2 | No | 3 | 1 | 500056 | PM01 | CM - Gabinete control Merril Crowe & Refinación |  | 180.3 | 90
2026-W14 | 2026-04-09 | P02 | PASINS01 | Instrumentación | 26 | 11.3 | 6.4 | 2 | 19.7 | 75.8 | No | 5 | 1 | 500189 | PM01 | CM - Switch gear SAG 630 A, 6.9 Kv, 31.5 kA | 1000036 | 140.5 | 90
2026-W14 | 2026-04-09 | P02 | PAHMEC01 | Mecánica | 24 | 9.1 | 2.2 | 1.5 | 12.8 | 53.3 | No | 6 | 1 | 500084 | PM02 | PM - Motor eléctrico HY0001M1 |  | 110.1 | 90
2026-W14 | 2026-04-09 | P02 | PAHMEC01 | Eléctrica | 24 | 9.4 | 2.2 | 1.7 | 13.3 | 55.4 | No | 3 | 4 | 500007 | PM02 | PM - Transmisor vibración VT0020A |  | 94.7 | 90
2026-W14 | 2026-04-09 | P02 | PAHMEC01 | Instrumentación | 28 | 11.7 | 5.6 | 2.5 | 19.8 | 70.7 | No | 4 | 2 | 500172 | PM02 | PM - Tablero de comunicación | 1005482 | 113.2 | 90
2026-W14 | 2026-04-09 | P02 | PAHELE01 | Mecánica | 25 | 10.4 | 7.3 | 0.2 | 17.9 | 71.6 | No | 4 | 3 | 500047 | PM01 | CM - Indicador presión agua PI0251 |  | 115.4 | 90
2026-W14 | 2026-04-09 | P02 | PAHELE01 | Eléctrica | 18 | 6.8 | 4.5 | 0.9 | 12.2 | 67.8 | No | 3 | 3 | 500119 | PM01 | CM - Calefactor eléctrico HE0137 | 1001301 | 50.5 | 90
2026-W14 | 2026-04-09 | P02 | PAHELE01 | Instrumentación | 21 | 8.7 | 4.4 | 1.6 | 14.7 | 70 | No | 4 | 3 | 500137 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 126.7 | 90
2026-W14 | 2026-04-09 | P02 | PAHINS01 | Mecánica | 30 | 5.4 | 5.2 | 2.5 | 13.1 | 43.7 | No | 5 | 1 | 500015 | PM02 | PM - Sensor temperatura aire TS4591 |  | 69.9 | 90
2026-W14 | 2026-04-09 | P02 | PAHINS01 | Eléctrica | 16 | 4.4 | 2.1 | 0.9 | 7.4 | 46.2 | No | 5 | 3 | 500122 | PM01 | CM - Carro mantención regeneración carbon | 1006826 | 25.6 | 90
2026-W14 | 2026-04-09 | P02 | PAHINS01 | Instrumentación | 30 | 4.1 | 5.4 | 0 | 9.5 | 31.7 | No | 2 | 1 | 500072 | PM02 | PM - Válvula control flujo entrada agua rechazo FV3576 |  | 78.8 | 90
2026-W14 | 2026-04-10 | M01 | PASMEC01 | Mecánica | 38 | 7.6 | 6.2 | 0.3 | 14.1 | 37.1 | No | 6 | 3 | 500049 | PM01 | CM - Válvula control alimenta pulpa HV1501K | 1001317 | 60.2 | 90
2026-W14 | 2026-04-10 | M01 | PASMEC01 | Eléctrica | 17 | 5.9 | 5.1 | 0.9 | 11.9 | 70 | No | 4 | 1 | 500068 | PM02 | PM - Tecle eléctrico tolva carbon |  | 21 | 90
2026-W14 | 2026-04-10 | M01 | PASMEC01 | Instrumentación | 37 | 12.2 | 10.4 | 0.2 | 22.8 | 61.6 | No | 4 | 1 | 500019 | PM02 | PM - Transmisor nivel lechada cal LIT5314 |  | 188.1 | 90
2026-W14 | 2026-04-10 | M01 | PASELE01 | Mecánica | 26 | 11.3 | 3 | 2.5 | 16.8 | 64.6 | No | 2 | 2 | 500167 | PM02 | PM - Sensor temperatura TE0802 |  | 81.5 | 90
2026-W14 | 2026-04-10 | M01 | PASELE01 | Eléctrica | 21 | 7.7 | 4.2 | 1.5 | 13.4 | 63.8 | No | 7 | 4 | 500146 | PM02 | PM - Válvula control alimenta pulpa HV1501C |  | 128.7 | 90
2026-W14 | 2026-04-10 | M01 | PASELE01 | Instrumentación | 20 | 4.8 | 5.2 | 2 | 12 | 60 | No | 3 | 1 | 500183 | PM01 | CM - Estanque separador TK0054 | 1006831 | 100.1 | 90
2026-W14 | 2026-04-10 | M01 | PASINS01 | Mecánica | 35 | 14 | 4.6 | 2.3 | 20.9 | 59.7 | No | 2 | 4 | 500049 | PM01 | CM - Válvula control alimenta pulpa HV1501K |  | 143.9 | 90
2026-W14 | 2026-04-10 | M01 | PASINS01 | Eléctrica | 24 | 11.1 | 4.7 | 1.4 | 17.2 | 71.7 | No | 7 | 2 | 500161 | PM02 | PM - Unidad aire acondicionado |  | 193 | 90
2026-W14 | 2026-04-10 | M01 | PASINS01 | Instrumentación | 33 | 15.1 | 3.6 | 2 | 20.7 | 62.7 | No | 6 | 3 | 500150 | PM02 | PM - Válvula control entrada sol precipitado HV3185 | 1002467 | 188.5 | 90
2026-W14 | 2026-04-10 | M01 | PAHMEC01 | Mecánica | 22 | 8.4 | 3.3 | 0.8 | 12.5 | 56.8 | No | 2 | 1 | 500160 | PM02 | PM - Gabinete control Chancador Primario |  | 149.4 | 90
2026-W14 | 2026-04-10 | M01 | PAHMEC01 | Eléctrica | 37 | 14.3 | 4.3 | 1.2 | 19.8 | 53.5 | No | 3 | 3 | 500078 | PM02 | PM - Unidad aire acondicionado |  | 24.6 | 90
2026-W14 | 2026-04-10 | M01 | PAHMEC01 | Instrumentación | 34 | 12.2 | 8.1 | 1.5 | 21.8 | 64.1 | No | 3 | 2 | 500185 | PM01 | CM - Motor eléctrico HY0036M1 | 1000770 | 133.8 | 90
2026-W14 | 2026-04-10 | M01 | PAHELE01 | Mecánica | 19 | 8.8 | 2 | 1.8 | 12.6 | 66.3 | No | 7 | 3 | 500064 | PM01 | CM - Válvula control drenaje relaves alimentación HV4602 | 1003730 | 81.5 | 90
2026-W14 | 2026-04-10 | M01 | PAHELE01 | Eléctrica | 37 | 11.3 | 8.2 | 1.5 | 21 | 56.8 | No | 6 | 4 | 500067 | PM02 | PM - Indicador presión aceite hidráulico PI4895E |  | 191.8 | 90
2026-W14 | 2026-04-10 | M01 | PAHELE01 | Instrumentación | 25 | 9.5 | 6 | 0 | 15.5 | 62 | No | 7 | 2 | 500125 | PM01 | CM - Transmisor presión aceite PIT4824 |  | 49.6 | 90
2026-W14 | 2026-04-10 | M01 | PAHINS01 | Mecánica | 27 | 5.8 | 3.6 | 2.2 | 11.6 | 43 | No | 6 | 1 | 500024 | PM02 | PM - Válvula alivio presión aceite PRV0664 | 1003603 | 140.7 | 90
2026-W14 | 2026-04-10 | M01 | PAHINS01 | Eléctrica | 30 | 5.3 | 2.7 | 2.2 | 10.2 | 34 | No | 7 | 2 | 500068 | PM02 | PM - Tecle eléctrico tolva carbon |  | 66.3 | 90
2026-W14 | 2026-04-10 | M01 | PAHINS01 | Instrumentación | 18 | 5.2 | 3.4 | 1.1 | 9.7 | 53.9 | No | 3 | 1 | 500042 | PM02 | PM - Válvula control salida precapa HV3102 |  | 102.7 | 90
2026-W14 | 2026-04-10 | M02 | PASMEC01 | Mecánica | 20 | 7.5 | 4.5 | 1.3 | 13.3 | 66.5 | No | 4 | 3 | 500109 | PM02 | PM - Variador frecuencia 3620PU0239M1VF | 1004840 | 133.6 | 90
2026-W14 | 2026-04-10 | M02 | PASMEC01 | Eléctrica | 33 | 8.8 | 5.3 | 2.4 | 16.5 | 50 | No | 6 | 3 | 500097 | PM02 | PM - Gabinete RIO |  | 174.2 | 90
2026-W14 | 2026-04-10 | M02 | PASMEC01 | Instrumentación | 18 | 4.9 | 3.5 | 0.7 | 9.1 | 50.6 | No | 5 | 2 | 500073 | PM02 | PM - Válvula control sol barren a estanque HV3266 |  | 166.5 | 90
2026-W14 | 2026-04-10 | M02 | PASELE01 | Mecánica | 37 | 16.7 | 3.4 | 1.7 | 21.8 | 58.9 | No | 6 | 2 | 500123 | PM01 | CM - Válvula control flujo sol barren FV5601 | 1003047 | 144.5 | 90
2026-W14 | 2026-04-10 | M02 | PASELE01 | Eléctrica | 32 | 9.7 | 5.1 | 0.8 | 15.6 | 48.8 | No | 6 | 3 | 500013 | PM02 | PM - Válvula control drenaje pulpa HV1006 |  | 43.7 | 90
2026-W14 | 2026-04-10 | M02 | PASELE01 | Instrumentación | 39 | 16.7 | 8 | 3.2 | 27.9 | 71.5 | No | 3 | 3 | 500130 | PM01 | CM - Tablero de enchufes | 1002476 | 184.3 | 90
2026-W14 | 2026-04-10 | M02 | PASINS01 | Mecánica | 24 | 6.4 | 5.6 | 1.9 | 13.9 | 57.9 | No | 4 | 3 | 500027 | PM02 | PM - Válvula control aceite XV4883 |  | 44.3 | 90
2026-W14 | 2026-04-10 | M02 | PASINS01 | Eléctrica | 25 | 7.5 | 3.3 | 0.3 | 11.1 | 44.4 | No | 4 | 3 | 500008 | PM02 | PM - Bomba precipitado |  | 30 | 90
2026-W14 | 2026-04-10 | M02 | PASINS01 | Instrumentación | 31 | 4.2 | 6.2 | 1.2 | 11.6 | 37.4 | No | 5 | 4 | 500050 | PM01 | CM - Línea agua sell 3700-5476-AA1A-3"-WGS-ET | 1002429 | 52.9 | 90
2026-W14 | 2026-04-10 | M02 | PAHMEC01 | Mecánica | 33 | 8.3 | 4.8 | 0 | 13.1 | 39.7 | No | 4 | 3 | 500058 | PM01 | CM - Sensor temperatura aire TS4591 | 1005250 | 189.2 | 90
2026-W14 | 2026-04-10 | M02 | PAHMEC01 | Eléctrica | 18 | 7.1 | 5 | 0 | 12.1 | 67.2 | No | 5 | 2 | 500172 | PM02 | PM - Tablero de comunicación |  | 136.5 | 90
2026-W14 | 2026-04-10 | M02 | PAHMEC01 | Instrumentación | 35 | 9.6 | 8.3 | 0.3 | 18.2 | 52 | No | 5 | 3 | 500035 | PM02 | PM - Agitador estanque filtración |  | 38.8 | 90
2026-W14 | 2026-04-10 | M02 | PAHELE01 | Mecánica | 37 | 14.6 | 5.5 | 3.5 | 23.6 | 63.8 | No | 6 | 4 | 500030 | PM02 | PM - Indicador nivel solución LI5563 |  | 122.8 | 90
2026-W14 | 2026-04-10 | M02 | PAHELE01 | Eléctrica | 32 | 10 | 8.1 | 1.4 | 19.5 | 60.9 | No | 7 | 3 | 500150 | PM02 | PM - Válvula control entrada sol precipitado HV3185 |  | 172.8 | 90
2026-W14 | 2026-04-10 | M02 | PAHELE01 | Instrumentación | 21 | 7.2 | 3.1 | 1.9 | 12.2 | 58.1 | No | 3 | 1 | 500036 | PM02 | PM - Colector polvo horno fundición |  | 59.8 | 90
2026-W14 | 2026-04-10 | M02 | PAHINS01 | Mecánica | 38 | 15.4 | 6.5 | 0.2 | 22.1 | 58.2 | No | 6 | 4 | 500031 | PM02 | PM - Celosía XM0114 |  | 72.6 | 90
2026-W14 | 2026-04-10 | M02 | PAHINS01 | Eléctrica | 38 | 9.9 | 6.6 | 3.3 | 19.8 | 52.1 | No | 7 | 3 | 500055 | PM01 | CM - Baliza YL3612 | 1002494 | 116.7 | 90
2026-W14 | 2026-04-10 | M02 | PAHINS01 | Instrumentación | 16 | 6.7 | 3.7 | 1.2 | 11.6 | 72.5 | No | 3 | 3 | 500158 | PM02 | PM - Válvula control flujo sol barren FV5601 |  | 105.1 | 90
2026-W14 | 2026-04-10 | P01 | PASMEC01 | Mecánica | 35 | 5.5 | 5.7 | 3.4 | 14.6 | 41.7 | No | 7 | 4 | 500144 | PM02 | PM - Motor eléctrico PU0516M1 | 1005520 | 76.9 | 90
2026-W14 | 2026-04-10 | P01 | PASMEC01 | Eléctrica | 32 | 7.1 | 8.5 | 2.8 | 18.4 | 57.5 | No | 2 | 4 | 500140 | PM02 | PM - Correa retorno pebbles |  | 167.9 | 90
2026-W14 | 2026-04-10 | P01 | PASMEC01 | Instrumentación | 20 | 5.9 | 5.9 | 0.1 | 11.9 | 59.5 | No | 2 | 3 | 500003 | PM02 | PM - Tablero de comunicación |  | 40.4 | 90
2026-W14 | 2026-04-10 | P01 | PASELE01 | Mecánica | 28 | 9.9 | 4.3 | 1.3 | 15.5 | 55.4 | No | 3 | 2 | 500023 | PM02 | PM - Válvula control entrada aire FV1804 |  | 182.2 | 90
2026-W14 | 2026-04-10 | P01 | PASELE01 | Eléctrica | 32 | 5.7 | 8.9 | 3.1 | 17.7 | 55.3 | No | 5 | 2 | 500104 | PM02 | PM - Hidrante/ Grifos FH0138 | 1006100 | 162.2 | 90
2026-W14 | 2026-04-10 | P01 | PASELE01 | Instrumentación | 34 | 7.6 | 9.8 | 0.2 | 17.6 | 51.8 | No | 7 | 3 | 500104 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 168.8 | 90
2026-W14 | 2026-04-10 | P01 | PASINS01 | Mecánica | 31 | 11.7 | 8.1 | 0.5 | 20.3 | 65.5 | No | 3 | 2 | 500065 | PM02 | PM - Muestreador alimentación filtros |  | 178.2 | 90
2026-W14 | 2026-04-10 | P01 | PASINS01 | Eléctrica | 39 | 6 | 6.5 | 2.3 | 14.8 | 37.9 | No | 6 | 3 | 500149 | PM02 | PM - Indicador presión aceite PI1315 | 1006550 | 69.5 | 90
2026-W14 | 2026-04-10 | P01 | PASINS01 | Instrumentación | 34 | 15.6 | 10.1 | 2.2 | 27.9 | 82.1 | No | 7 | 3 | 500032 | PM02 | PM - Válvula control entrada cianuro sodio FV1903 | 1002832 | 183.1 | 90
2026-W14 | 2026-04-10 | P01 | PAHMEC01 | Mecánica | 26 | 12.2 | 4 | 1.1 | 17.3 | 66.5 | No | 2 | 2 | 500038 | PM02 | PM - Switch bajo flujo aire FSL1357A | 1002557 | 68.7 | 90
2026-W14 | 2026-04-10 | P01 | PAHMEC01 | Eléctrica | 37 | 6.9 | 3.9 | 2.5 | 13.3 | 35.9 | No | 5 | 4 | 500142 | PM02 | PM - Calefactor eléctrico estanque HE0113 | 1005783 | 160.8 | 90
2026-W14 | 2026-04-10 | P01 | PAHMEC01 | Instrumentación | 18 | 5.5 | 4.2 | 0.2 | 9.9 | 55 | No | 7 | 2 | 500114 | PM01 | CM - Transmisor vibración VT0020A | 1002409 | 184.4 | 90
2026-W14 | 2026-04-10 | P01 | PAHELE01 | Mecánica | 26 | 6.8 | 2.7 | 0.7 | 10.2 | 39.2 | No | 4 | 4 | 500085 | PM02 | PM - Gabinete servidor core switch 1 y commun |  | 72.6 | 90
2026-W14 | 2026-04-10 | P01 | PAHELE01 | Eléctrica | 33 | 5.3 | 7.7 | 2.3 | 15.3 | 46.4 | No | 6 | 1 | 500075 | PM02 | PM - Switch posición giro rastras ZS4377D |  | 186.1 | 90
2026-W14 | 2026-04-10 | P01 | PAHELE01 | Instrumentación | 38 | 9.5 | 9.1 | 1 | 19.6 | 51.6 | No | 4 | 2 | 500190 | PM01 | CM - Colector polvo horno fundición | 1003268 | 171.1 | 90
2026-W14 | 2026-04-10 | P01 | PAHINS01 | Mecánica | 19 | 8.6 | 3.5 | 1 | 13.1 | 68.9 | No | 3 | 2 | 500055 | PM01 | CM - Baliza YL3612 | 1000406 | 131.2 | 90
2026-W14 | 2026-04-10 | P01 | PAHINS01 | Eléctrica | 25 | 10.1 | 3.1 | 0.6 | 13.8 | 55.2 | No | 5 | 2 | 500171 | PM02 | PM - Switch bajo nivel aceite LSL0253 |  | 93.9 | 90
2026-W14 | 2026-04-10 | P01 | PAHINS01 | Instrumentación | 35 | 14.1 | 3.8 | 0 | 17.9 | 51.1 | No | 6 | 4 | 500060 | PM01 | CM - Indicador presión descarga agua PI5057 |  | 167.9 | 90
2026-W14 | 2026-04-10 | P02 | PASMEC01 | Mecánica | 26 | 7.2 | 5.7 | 0.6 | 13.5 | 51.9 | No | 6 | 1 | 500012 | PM02 | PM - Gabinete PLC horno fundición 1 |  | 163 | 90
2026-W14 | 2026-04-10 | P02 | PASMEC01 | Eléctrica | 29 | 12.2 | 3.8 | 2.4 | 18.4 | 63.4 | No | 4 | 4 | 500042 | PM02 | PM - Válvula control salida precapa HV3102 |  | 29.5 | 90
2026-W14 | 2026-04-10 | P02 | PASMEC01 | Instrumentación | 16 | 5.1 | 2.1 | 1.1 | 8.3 | 51.9 | No | 5 | 1 | 500173 | PM02 | PM - Bomba agua sello |  | 38.1 | 90
2026-W14 | 2026-04-10 | P02 | PASELE01 | Mecánica | 30 | 7 | 5.3 | 2.1 | 14.4 | 48 | No | 7 | 1 | 500158 | PM02 | PM - Válvula control flujo sol barren FV5601 |  | 40.3 | 90
2026-W14 | 2026-04-10 | P02 | PASELE01 | Eléctrica | 27 | 10.2 | 6.7 | 1 | 17.9 | 66.3 | No | 5 | 1 | 500067 | PM02 | PM - Indicador presión aceite hidráulico PI4895E |  | 106.5 | 90
2026-W14 | 2026-04-10 | P02 | PASELE01 | Instrumentación | 22 | 8.4 | 3.2 | 2.1 | 13.7 | 62.3 | No | 4 | 1 | 500180 | PM01 | CM - Bomba diesel horno reactivación carbon |  | 193.8 | 90
2026-W14 | 2026-04-10 | P02 | PASINS01 | Mecánica | 24 | 4.1 | 3.2 | 2 | 9.3 | 38.8 | No | 5 | 2 | 500143 | PM02 | PM - Transmisor nivel solución barren LIT2787 |  | 63.4 | 90
2026-W14 | 2026-04-10 | P02 | PASINS01 | Eléctrica | 26 | 7.7 | 6.2 | 1.8 | 15.7 | 60.4 | No | 2 | 2 | 500066 | PM02 | PM - Hidrante/ Grifos FH0137 | 1002979 | 119.9 | 90
2026-W14 | 2026-04-10 | P02 | PASINS01 | Instrumentación | 30 | 9.9 | 8.5 | 2.9 | 21.3 | 71 | No | 4 | 1 | 500020 | PM02 | PM - Cajón (Futuro) |  | 160 | 90
2026-W14 | 2026-04-10 | P02 | PAHMEC01 | Mecánica | 33 | 5.3 | 7.4 | 2.2 | 14.9 | 45.2 | No | 2 | 3 | 500010 | PM02 | PM - Tablero SCI |  | 151.3 | 90
2026-W14 | 2026-04-10 | P02 | PAHMEC01 | Eléctrica | 25 | 6 | 3.3 | 0.9 | 10.2 | 40.8 | No | 5 | 2 | 500025 | PM02 | PM - Válvula control succión agua filtrada HV4771A |  | 121 | 90
2026-W14 | 2026-04-10 | P02 | PAHMEC01 | Instrumentación | 26 | 6.9 | 7.3 | 1.1 | 15.3 | 58.8 | No | 5 | 2 | 500033 | PM02 | PM - Válvula control entrada lechada cal HV5311 |  | 40.4 | 90
2026-W14 | 2026-04-10 | P02 | PAHELE01 | Mecánica | 35 | 15 | 10.4 | 1.4 | 26.8 | 76.6 | No | 4 | 4 | 500014 | PM02 | PM - Válvula control descarga agua filtrado HV4824 | 1006480 | 183.9 | 90
2026-W14 | 2026-04-10 | P02 | PAHELE01 | Eléctrica | 25 | 5.7 | 4.7 | 1.9 | 12.3 | 49.2 | No | 6 | 2 | 500054 | PM01 | CM - Intercambiador calor calentamiento |  | 109.9 | 90
2026-W14 | 2026-04-10 | P02 | PAHELE01 | Instrumentación | 31 | 13 | 2.1 | 1.5 | 16.6 | 53.5 | No | 5 | 3 | 500180 | PM01 | CM - Bomba diesel horno reactivación carbon | 1001961 | 153.3 | 90
2026-W14 | 2026-04-10 | P02 | PAHINS01 | Mecánica | 24 | 5.9 | 2.9 | 1.3 | 10.1 | 42.1 | No | 3 | 3 | 500134 | PM02 | PM - Intercambiador calor por aire CQ0007 | 1020025 | 133.2 | 90
2026-W14 | 2026-04-10 | P02 | PAHINS01 | Eléctrica | 26 | 12.9 | 2.2 | 0.9 | 16 | 61.5 | No | 7 | 1 | 500136 | PM02 | PM - Calefactor eléctrico edificio |  | 67.2 | 90
2026-W14 | 2026-04-10 | P02 | PAHINS01 | Instrumentación | 19 | 5.3 | 4.9 | 1.2 | 11.4 | 60 | No | 6 | 2 | 500025 | PM02 | PM - Válvula control succión agua filtrada HV4771A |  | 87.2 | 90
2026-W14 | 2026-04-11 | M01 | PASMEC01 | Mecánica | 37 | 4.9 | 5.6 | 3.6 | 14.1 | 38.1 | No | 7 | 3 | 500173 | PM02 | PM - Bomba agua sello |  | 71.8 | 90
2026-W14 | 2026-04-11 | M01 | PASMEC01 | Eléctrica | 25 | 7.5 | 4.2 | 0.1 | 11.8 | 47.2 | No | 7 | 1 | 500032 | PM02 | PM - Válvula control entrada cianuro sodio FV1903 | 1004188 | 147.6 | 90
2026-W14 | 2026-04-11 | M01 | PASMEC01 | Instrumentación | 21 | 6 | 6 | 0.7 | 12.7 | 60.5 | No | 2 | 3 | 500141 | PM02 | PM - Lava ojos emergencia |  | 116.2 | 90
2026-W14 | 2026-04-11 | M01 | PASELE01 | Mecánica | 19 | 4.6 | 5.5 | 1.5 | 11.6 | 61.1 | No | 5 | 3 | 500020 | PM02 | PM - Cajón (Futuro) |  | 148.2 | 90
2026-W14 | 2026-04-11 | M01 | PASELE01 | Eléctrica | 19 | 4.7 | 4.5 | 1.1 | 10.3 | 54.2 | No | 4 | 2 | 500060 | PM01 | CM - Indicador presión descarga agua PI5057 |  | 108.5 | 90
2026-W14 | 2026-04-11 | M01 | PASELE01 | Instrumentación | 32 | 9.8 | 4.9 | 1.2 | 15.9 | 49.7 | No | 4 | 2 | 500160 | PM02 | PM - Gabinete control Chancador Primario |  | 98.5 | 90
2026-W14 | 2026-04-11 | M01 | PASINS01 | Mecánica | 16 | 7.3 | 4.2 | 0.8 | 12.3 | 76.9 | No | 5 | 1 | 500130 | PM01 | CM - Tablero de enchufes | 1006611 | 71.9 | 90
2026-W14 | 2026-04-11 | M01 | PASINS01 | Eléctrica | 23 | 5.5 | 2.7 | 0.1 | 8.3 | 36.1 | No | 2 | 3 | 500031 | PM02 | PM - Celosía XM0114 | 1001954 | 32.4 | 90
2026-W14 | 2026-04-11 | M01 | PASINS01 | Instrumentación | 36 | 8.8 | 10.7 | 1.9 | 21.4 | 59.4 | No | 2 | 1 | 500010 | PM02 | PM - Tablero SCI |  | 80.3 | 90
2026-W14 | 2026-04-11 | M01 | PAHMEC01 | Mecánica | 25 | 4.2 | 2.7 | 1.7 | 8.6 | 34.4 | No | 3 | 2 | 500126 | PM01 | CM - Válvula control salida carbon descargado HV3394 |  | 61.5 | 90
2026-W14 | 2026-04-11 | M01 | PAHMEC01 | Eléctrica | 37 | 8.6 | 8.2 | 1.1 | 17.9 | 48.4 | No | 4 | 4 | 500159 | PM02 | PM - Gabinete manguera y equipo contraincendios HH0119 |  | 54.4 | 90
2026-W14 | 2026-04-11 | M01 | PAHMEC01 | Instrumentación | 18 | 8.7 | 2.4 | 0.7 | 11.8 | 65.6 | No | 3 | 2 | 500083 | PM02 | PM - Válvula control descarga agua filtrado HV4824 | 1004245 | 98.3 | 90
2026-W14 | 2026-04-11 | M01 | PAHELE01 | Mecánica | 16 | 4.2 | 2.9 | 0.3 | 7.4 | 46.2 | No | 5 | 3 | 500073 | PM02 | PM - Válvula control sol barren a estanque HV3266 |  | 156.9 | 90
2026-W14 | 2026-04-11 | M01 | PAHELE01 | Eléctrica | 20 | 9.4 | 4.9 | 0.7 | 15 | 75 | No | 3 | 4 | 500115 | PM01 | CM - Bomba vacío retorta | 1000400 | 144 | 90
2026-W14 | 2026-04-11 | M01 | PAHELE01 | Instrumentación | 30 | 7.2 | 7.1 | 2.6 | 16.9 | 56.3 | No | 7 | 2 | 500097 | PM02 | PM - Gabinete RIO |  | 37.6 | 90
2026-W14 | 2026-04-11 | M01 | PAHINS01 | Mecánica | 18 | 5.7 | 2.6 | 1 | 9.3 | 51.7 | No | 4 | 3 | 500103 | PM02 | PM - Tablero SCI |  | 157.1 | 90
2026-W14 | 2026-04-11 | M01 | PAHINS01 | Eléctrica | 21 | 4 | 3.3 | 1.1 | 8.4 | 40 | No | 6 | 1 | 500101 | PM02 | PM - Subestación unitaria |  | 40 | 90
2026-W14 | 2026-04-11 | M01 | PAHINS01 | Instrumentación | 36 | 13.8 | 9 | 2.3 | 25.1 | 69.7 | No | 3 | 3 | 500052 | PM01 | CM - Tablero distribución instrumentación | 1000420 | 147.8 | 90
2026-W14 | 2026-04-11 | M02 | PASMEC01 | Mecánica | 33 | 12.3 | 7.8 | 1.5 | 21.6 | 65.5 | No | 6 | 3 | 500124 | PM01 | CM - Extractor taller EMP |  | 58.9 | 90
2026-W14 | 2026-04-11 | M02 | PASMEC01 | Eléctrica | 20 | 4.2 | 3.6 | 1.6 | 9.4 | 47 | No | 5 | 4 | 500178 | PM01 | CM - Sensor temperatura TE0802 | 1005694 | 148.9 | 90
2026-W14 | 2026-04-11 | M02 | PASMEC01 | Instrumentación | 35 | 7.3 | 10.5 | 0.4 | 18.2 | 52 | No | 2 | 4 | 500007 | PM02 | PM - Transmisor vibración VT0020A |  | 43.4 | 90
2026-W14 | 2026-04-11 | M02 | PASELE01 | Mecánica | 23 | 10 | 2.4 | 0.4 | 12.8 | 55.7 | No | 3 | 4 | 500014 | PM02 | PM - Válvula control descarga agua filtrado HV4824 | 1006141 | 24 | 90
2026-W14 | 2026-04-11 | M02 | PASELE01 | Eléctrica | 27 | 7 | 5.6 | 1.6 | 14.2 | 52.6 | No | 6 | 4 | 500086 | PM02 | PM - Sensor nivel refrigerante LE0177 |  | 166.8 | 90
2026-W14 | 2026-04-11 | M02 | PASELE01 | Instrumentación | 35 | 8.6 | 2.9 | 0.2 | 11.7 | 33.4 | No | 3 | 1 | 500183 | PM01 | CM - Estanque separador TK0054 | 1006549 | 113.7 | 90
2026-W14 | 2026-04-11 | M02 | PASINS01 | Mecánica | 31 | 5.9 | 2.2 | 0.4 | 8.5 | 27.4 | No | 6 | 1 | 500079 | PM02 | PM - Gabinete RIO |  | 52.3 | 90
2026-W14 | 2026-04-11 | M02 | PASINS01 | Eléctrica | 39 | 19.1 | 10.5 | 1.3 | 30.9 | 79.2 | No | 3 | 3 | 500058 | PM01 | CM - Sensor temperatura aire TS4591 | 1000901 | 172.5 | 90
2026-W14 | 2026-04-11 | M02 | PASINS01 | Instrumentación | 27 | 12.6 | 6.1 | 2.4 | 21.1 | 78.1 | No | 6 | 2 | 500065 | PM02 | PM - Muestreador alimentación filtros |  | 98.7 | 90
2026-W14 | 2026-04-11 | M02 | PAHMEC01 | Mecánica | 19 | 4.4 | 2.7 | 1.5 | 8.6 | 45.3 | No | 5 | 2 | 500181 | PM01 | CM - Bomba diafragma grasa PU0001 |  | 131.2 | 90
2026-W14 | 2026-04-11 | M02 | PAHMEC01 | Eléctrica | 23 | 9.2 | 3 | 0 | 12.2 | 53 | No | 3 | 1 | 500173 | PM02 | PM - Bomba agua sello | 1000465 | 112.5 | 90
2026-W14 | 2026-04-11 | M02 | PAHMEC01 | Instrumentación | 37 | 7.1 | 2.4 | 0.7 | 10.2 | 27.6 | No | 7 | 3 | 500188 | PM01 | CM - Switch posición ZS1716 | 1006037 | 80.8 | 90
2026-W14 | 2026-04-11 | M02 | PAHELE01 | Mecánica | 34 | 10.6 | 5.9 | 0.9 | 17.4 | 51.2 | No | 6 | 2 | 500052 | PM01 | CM - Tablero distribución instrumentación | 1004725 | 128.9 | 90
2026-W14 | 2026-04-11 | M02 | PAHELE01 | Eléctrica | 38 | 9.7 | 2.7 | 0.7 | 13.1 | 34.5 | No | 4 | 4 | 500026 | PM02 | PM - Estanque almacenamiento aceite hidráulico TK0088 | 1000546 | 43.6 | 90
2026-W14 | 2026-04-11 | M02 | PAHELE01 | Instrumentación | 39 | 7.2 | 6.3 | 0.3 | 13.8 | 35.4 | No | 4 | 1 | 500052 | PM01 | CM - Tablero distribución instrumentación | 1000594 | 42.7 | 90
2026-W14 | 2026-04-11 | M02 | PAHINS01 | Mecánica | 27 | 9.3 | 7.5 | 0.3 | 17.1 | 63.3 | No | 7 | 2 | 500180 | PM01 | CM - Bomba diesel horno reactivación carbon |  | 97.2 | 90
2026-W14 | 2026-04-11 | M02 | PAHINS01 | Eléctrica | 36 | 10 | 8.9 | 1.7 | 20.6 | 57.2 | No | 4 | 1 | 500042 | PM02 | PM - Válvula control salida precapa HV3102 |  | 103.3 | 90
2026-W14 | 2026-04-11 | M02 | PAHINS01 | Instrumentación | 26 | 5.5 | 2.7 | 0.1 | 8.3 | 31.9 | No | 3 | 1 | 500141 | PM02 | PM - Lava ojos emergencia | 1006336 | 178.4 | 90
2026-W14 | 2026-04-11 | P01 | PASMEC01 | Mecánica | 31 | 13.3 | 2.2 | 1.5 | 17 | 54.8 | No | 5 | 1 | 500017 | PM02 | PM - Indicador presión agua PI0423 |  | 169.4 | 90
2026-W14 | 2026-04-11 | P01 | PASMEC01 | Eléctrica | 26 | 11.5 | 4.8 | 2 | 18.3 | 70.4 | No | 7 | 3 | 500169 | PM02 | PM - Celosía XM0114 |  | 70.7 | 90
2026-W14 | 2026-04-11 | P01 | PASMEC01 | Instrumentación | 36 | 10.6 | 6.6 | 3.6 | 20.8 | 57.8 | No | 2 | 4 | 500060 | PM01 | CM - Indicador presión descarga agua PI5057 | 1001121 | 62 | 90
2026-W14 | 2026-04-11 | P01 | PASELE01 | Mecánica | 21 | 8.1 | 5 | 1.4 | 14.5 | 69 | No | 2 | 4 | 500010 | PM02 | PM - Tablero SCI |  | 175.3 | 90
2026-W14 | 2026-04-11 | P01 | PASELE01 | Eléctrica | 22 | 4.8 | 2.7 | 1 | 8.5 | 38.6 | No | 7 | 1 | 500188 | PM01 | CM - Switch posición ZS1716 |  | 153.8 | 90
2026-W14 | 2026-04-11 | P01 | PASELE01 | Instrumentación | 18 | 6.3 | 3 | 0.5 | 9.8 | 54.4 | No | 4 | 3 | 500028 | PM02 | PM - Válvula control succión agua fresca HV7808 |  | 96.2 | 90
2026-W14 | 2026-04-11 | P01 | PASINS01 | Mecánica | 33 | 8 | 6.6 | 0.2 | 14.8 | 44.8 | No | 2 | 2 | 500034 | PM02 | PM - Puerta enrollable Molienda |  | 121.2 | 90
2026-W14 | 2026-04-11 | P01 | PASINS01 | Eléctrica | 37 | 18.1 | 5 | 2.2 | 25.3 | 68.4 | No | 4 | 2 | 500177 | PM01 | CM - Intercambiador calor por aire CQ0007 | 1007100 | 129.1 | 90
2026-W14 | 2026-04-11 | P01 | PASINS01 | Instrumentación | 21 | 10.3 | 5.2 | 0.4 | 15.9 | 75.7 | No | 4 | 4 | 500087 | PM02 | PM - Línea agua sell 3700-5476-AA1A-3"-WGS-ET |  | 126.2 | 90
2026-W14 | 2026-04-11 | P01 | PAHMEC01 | Mecánica | 39 | 16.5 | 5.6 | 1.2 | 23.3 | 59.7 | No | 6 | 1 | 500069 | PM02 | PM - Puerta Taller Camiones |  | 116.9 | 90
2026-W14 | 2026-04-11 | P01 | PAHMEC01 | Eléctrica | 22 | 9.8 | 5.9 | 0.9 | 16.6 | 75.5 | No | 3 | 3 | 500087 | PM02 | PM - Línea agua sell 3700-5476-AA1A-3"-WGS-ET |  | 20.3 | 90
2026-W14 | 2026-04-11 | P01 | PAHMEC01 | Instrumentación | 16 | 5.4 | 4.8 | 1.2 | 11.4 | 71.2 | No | 4 | 4 | 500077 | PM02 | PM - Válvula control entrada solucion barren FV2314 | 1004183 | 191.9 | 90
2026-W14 | 2026-04-11 | P01 | PAHELE01 | Mecánica | 23 | 8.3 | 5.7 | 0.3 | 14.3 | 62.2 | No | 6 | 4 | 500043 | PM02 | PM - Sirena YA3453 |  | 65.7 | 90
2026-W14 | 2026-04-11 | P01 | PAHELE01 | Eléctrica | 30 | 8.6 | 7.5 | 0.8 | 16.9 | 56.3 | No | 4 | 1 | 500179 | PM01 | CM - Transmisor nivel atricción carbón LIT3627 | 1002712 | 20.3 | 90
2026-W14 | 2026-04-11 | P01 | PAHELE01 | Instrumentación | 31 | 5.5 | 3.5 | 1.8 | 10.8 | 34.8 | No | 2 | 4 | 500017 | PM02 | PM - Indicador presión agua PI0423 |  | 109.5 | 90
2026-W14 | 2026-04-11 | P01 | PAHINS01 | Mecánica | 29 | 6 | 4.2 | 2.1 | 12.3 | 42.4 | No | 5 | 3 | 500021 | PM02 | PM - Tornillo alimentador sulfato de cobre |  | 32.9 | 90
2026-W14 | 2026-04-11 | P01 | PAHINS01 | Eléctrica | 36 | 4.7 | 6.8 | 0.9 | 12.4 | 34.4 | No | 5 | 2 | 500159 | PM02 | PM - Gabinete manguera y equipo contraincendios HH0119 |  | 67 | 90
2026-W14 | 2026-04-11 | P01 | PAHINS01 | Instrumentación | 29 | 13 | 2.8 | 2.3 | 18.1 | 62.4 | No | 2 | 3 | 500139 | PM02 | PM - Hidrante/ Grifos FH0136 |  | 151.5 | 90
2026-W14 | 2026-04-11 | P02 | PASMEC01 | Mecánica | 28 | 13.4 | 2.9 | 1.8 | 18.1 | 64.6 | No | 4 | 4 | 500135 | PM02 | PM - Compresor de aire neumático |  | 192.2 | 90
2026-W14 | 2026-04-11 | P02 | PASMEC01 | Eléctrica | 23 | 9.6 | 5.4 | 1.7 | 16.7 | 72.6 | No | 7 | 3 | 500051 | PM01 | CM - Tablero distribución UPS | 1005381 | 135 | 90
2026-W14 | 2026-04-11 | P02 | PASMEC01 | Instrumentación | 36 | 7.5 | 5.8 | 1.9 | 15.2 | 42.2 | No | 4 | 2 | 500005 | PM02 | PM - Válvula control succión agua fresca HV7808 |  | 37.2 | 90
2026-W14 | 2026-04-11 | P02 | PASELE01 | Mecánica | 27 | 6.7 | 4.7 | 0.5 | 11.9 | 44.1 | No | 4 | 1 | 500096 | PM02 | PM - Válvula control descarga agua fresca HV7819 | 1006282 | 141.9 | 90
2026-W14 | 2026-04-11 | P02 | PASELE01 | Eléctrica | 37 | 13.4 | 7.9 | 3.5 | 24.8 | 67 | No | 7 | 1 | 500038 | PM02 | PM - Switch bajo flujo aire FSL1357A | 1006512 | 64.6 | 90
2026-W14 | 2026-04-11 | P02 | PASELE01 | Instrumentación | 24 | 7.4 | 3.6 | 0.1 | 11.1 | 46.2 | No | 6 | 3 | 500081 | PM02 | PM - Transmisor nivel lechada cal LIT5271 |  | 157.5 | 90
2026-W14 | 2026-04-11 | P02 | PASINS01 | Mecánica | 24 | 5.9 | 2.9 | 1.9 | 10.7 | 44.6 | No | 2 | 4 | 500104 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 189.4 | 90
2026-W14 | 2026-04-11 | P02 | PASINS01 | Eléctrica | 16 | 7.9 | 4.8 | 0.9 | 13.6 | 85 | No | 2 | 1 | 500178 | PM01 | CM - Sensor temperatura TE0802 | 1001828 | 176.4 | 90
2026-W14 | 2026-04-11 | P02 | PASINS01 | Instrumentación | 34 | 8 | 4.3 | 3.3 | 15.6 | 45.9 | No | 6 | 3 | 500126 | PM01 | CM - Válvula control salida carbon descargado HV3394 | 1001641 | 152 | 90
2026-W14 | 2026-04-11 | P02 | PAHMEC01 | Mecánica | 32 | 11.2 | 9 | 0.9 | 21.1 | 65.9 | No | 6 | 3 | 500169 | PM02 | PM - Celosía XM0114 |  | 137.3 | 90
2026-W14 | 2026-04-11 | P02 | PAHMEC01 | Eléctrica | 39 | 17.3 | 2.5 | 0.6 | 20.4 | 52.3 | No | 6 | 1 | 500119 | PM01 | CM - Calefactor eléctrico HE0137 | 1000370 | 107 | 90
2026-W14 | 2026-04-11 | P02 | PAHMEC01 | Instrumentación | 18 | 6.3 | 4.9 | 0.8 | 12 | 66.7 | No | 7 | 3 | 500010 | PM02 | PM - Tablero SCI |  | 48.2 | 90
2026-W14 | 2026-04-11 | P02 | PAHELE01 | Mecánica | 21 | 4.7 | 4.1 | 1.5 | 10.3 | 49 | No | 4 | 4 | 500140 | PM02 | PM - Correa retorno pebbles |  | 90.5 | 90
2026-W14 | 2026-04-11 | P02 | PAHELE01 | Eléctrica | 36 | 12.9 | 10 | 0.1 | 23 | 63.9 | No | 2 | 3 | 500002 | PM02 | PM - Chute carbónHO0068 |  | 161.7 | 90
2026-W14 | 2026-04-11 | P02 | PAHELE01 | Instrumentación | 25 | 6.8 | 2.7 | 2.2 | 11.7 | 46.8 | No | 5 | 2 | 500181 | PM01 | CM - Bomba diafragma grasa PU0001 |  | 178.1 | 90
2026-W14 | 2026-04-11 | P02 | PAHINS01 | Mecánica | 39 | 16.7 | 3.2 | 3.4 | 23.3 | 59.7 | No | 5 | 2 | 500144 | PM02 | PM - Motor eléctrico PU0516M1 |  | 166.9 | 90
2026-W14 | 2026-04-11 | P02 | PAHINS01 | Eléctrica | 30 | 8.1 | 4.7 | 0.3 | 13.1 | 43.7 | No | 6 | 1 | 500124 | PM01 | CM - Extractor taller EMP | 1000522 | 84.3 | 90
2026-W14 | 2026-04-11 | P02 | PAHINS01 | Instrumentación | 32 | 9 | 5.1 | 2.2 | 16.3 | 50.9 | No | 3 | 3 | 500015 | PM02 | PM - Sensor temperatura aire TS4591 | 1002231 | 71.9 | 90
2026-W14 | 2026-04-12 | M01 | PASMEC01 | Mecánica | 38 | 16.4 | 3.6 | 3.4 | 23.4 | 61.6 | No | 6 | 1 | 500153 | PM02 | PM - Sistema Spray Grasa Engranaje - Molino SAG |  | 178.7 | 90
2026-W14 | 2026-04-12 | M01 | PASMEC01 | Eléctrica | 26 | 6.6 | 2.5 | 1.3 | 10.4 | 40 | No | 6 | 3 | 500078 | PM02 | PM - Unidad aire acondicionado |  | 56.4 | 90
2026-W14 | 2026-04-12 | M01 | PASMEC01 | Instrumentación | 31 | 9.1 | 3.3 | 0.6 | 13 | 41.9 | No | 7 | 3 | 500114 | PM01 | CM - Transmisor vibración VT0020A |  | 199.9 | 90
2026-W14 | 2026-04-12 | M01 | PASELE01 | Mecánica | 21 | 8.4 | 2.7 | 0.7 | 11.8 | 56.2 | No | 5 | 4 | 500158 | PM02 | PM - Válvula control flujo sol barren FV5601 |  | 68.6 | 90
2026-W14 | 2026-04-12 | M01 | PASELE01 | Eléctrica | 34 | 8.1 | 2.9 | 0.1 | 11.1 | 32.6 | No | 2 | 3 | 500172 | PM02 | PM - Tablero de comunicación | 1000686 | 44.8 | 90
2026-W14 | 2026-04-12 | M01 | PASELE01 | Instrumentación | 17 | 7.4 | 3.6 | 1.1 | 12.1 | 71.2 | No | 4 | 4 | 500113 | PM01 | CM - Puerta enrollable Molienda | 1004067 | 21.7 | 90
2026-W14 | 2026-04-12 | M01 | PASINS01 | Mecánica | 19 | 7.3 | 4.4 | 0 | 11.7 | 61.6 | No | 4 | 1 | 500122 | PM01 | CM - Carro mantención regeneración carbon |  | 31.9 | 90
2026-W14 | 2026-04-12 | M01 | PASINS01 | Eléctrica | 32 | 10.2 | 7 | 1.3 | 18.5 | 57.8 | No | 3 | 3 | 500119 | PM01 | CM - Calefactor eléctrico HE0137 |  | 168.2 | 90
2026-W14 | 2026-04-12 | M01 | PASINS01 | Instrumentación | 23 | 7.4 | 4 | 1.6 | 13 | 56.5 | No | 2 | 4 | 500012 | PM02 | PM - Gabinete PLC horno fundición 1 |  | 135.2 | 90
2026-W14 | 2026-04-12 | M01 | PAHMEC01 | Mecánica | 35 | 9 | 4.8 | 1.5 | 15.3 | 43.7 | No | 3 | 2 | 500018 | PM02 | PM - Transmisor presión aceite PIT4875 |  | 182.5 | 90
2026-W14 | 2026-04-12 | M01 | PAHMEC01 | Eléctrica | 29 | 14 | 8.4 | 0.3 | 22.7 | 78.3 | No | 7 | 1 | 500149 | PM02 | PM - Indicador presión aceite PI1315 |  | 38.4 | 90
2026-W14 | 2026-04-12 | M01 | PAHMEC01 | Instrumentación | 26 | 9.2 | 7.7 | 1.7 | 18.6 | 71.5 | No | 5 | 2 | 500046 | PM02 | PM - Gabinete servidor core switch 1 y commun |  | 164 | 90
2026-W14 | 2026-04-12 | M01 | PAHELE01 | Mecánica | 22 | 7 | 4.1 | 0.5 | 11.6 | 52.7 | No | 6 | 1 | 500135 | PM02 | PM - Compresor de aire neumático | 1001760 | 117.7 | 90
2026-W14 | 2026-04-12 | M01 | PAHELE01 | Eléctrica | 28 | 6.9 | 7.2 | 2.2 | 16.3 | 58.2 | No | 3 | 3 | 500086 | PM02 | PM - Sensor nivel refrigerante LE0177 |  | 129.2 | 90
2026-W14 | 2026-04-12 | M01 | PAHELE01 | Instrumentación | 30 | 7.9 | 4.7 | 1.3 | 13.9 | 46.3 | No | 5 | 1 | 500089 | PM02 | PM - Transmisor presión salida sol barren PIT3241 |  | 119.6 | 90
2026-W14 | 2026-04-12 | M01 | PAHINS01 | Mecánica | 32 | 9.4 | 5.3 | 0.3 | 15 | 46.9 | No | 5 | 2 | 500029 | PM02 | PM - Switch posición ZS0038A |  | 58.5 | 90
2026-W14 | 2026-04-12 | M01 | PAHINS01 | Eléctrica | 26 | 10.9 | 7.6 | 1.3 | 19.8 | 76.2 | No | 3 | 2 | 500002 | PM02 | PM - Chute carbónHO0068 | 1004559 | 99.3 | 90
2026-W14 | 2026-04-12 | M01 | PAHINS01 | Instrumentación | 19 | 7 | 2.8 | 0.3 | 10.1 | 53.2 | No | 6 | 2 | 500180 | PM01 | CM - Bomba diesel horno reactivación carbon |  | 98.1 | 90
2026-W14 | 2026-04-12 | M02 | PASMEC01 | Mecánica | 21 | 4.1 | 5.9 | 2 | 12 | 57.1 | No | 7 | 2 | 500095 | PM02 | PM - Bomba sumidero lixiviación |  | 22.4 | 90
2026-W14 | 2026-04-12 | M02 | PASMEC01 | Eléctrica | 30 | 11.2 | 2.2 | 0.2 | 13.6 | 45.3 | No | 3 | 2 | 500151 | PM02 | PM - Válvula control flujo entrada agua rechazo FV3576 |  | 112.2 | 90
2026-W14 | 2026-04-12 | M02 | PASMEC01 | Instrumentación | 38 | 7.2 | 2.6 | 1.2 | 11 | 28.9 | No | 3 | 3 | 500022 | PM02 | PM - Unidad re-potabilizadora agua |  | 147.8 | 90
2026-W14 | 2026-04-12 | M02 | PASELE01 | Mecánica | 34 | 5.9 | 2.1 | 2.7 | 10.7 | 31.5 | No | 4 | 4 | 500189 | PM01 | CM - Switch gear SAG 630 A, 6.9 Kv, 31.5 kA |  | 129.1 | 90
2026-W14 | 2026-04-12 | M02 | PASELE01 | Eléctrica | 37 | 14 | 5.8 | 2.4 | 22.2 | 60 | No | 6 | 3 | 500003 | PM02 | PM - Tablero de comunicación |  | 53.9 | 90
2026-W14 | 2026-04-12 | M02 | PASELE01 | Instrumentación | 27 | 4.2 | 6.8 | 0 | 11 | 40.7 | No | 5 | 2 | 500019 | PM02 | PM - Transmisor nivel lechada cal LIT5314 | 1005150 | 21.1 | 90
2026-W14 | 2026-04-12 | M02 | PASINS01 | Mecánica | 18 | 4.3 | 5.1 | 0.7 | 10.1 | 56.1 | No | 2 | 4 | 500039 | PM02 | PM - Chute carbónHO0068 |  | 83 | 90
2026-W14 | 2026-04-12 | M02 | PASINS01 | Eléctrica | 37 | 8.7 | 4.2 | 1 | 13.9 | 37.6 | No | 6 | 1 | 500025 | PM02 | PM - Válvula control succión agua filtrada HV4771A |  | 153.9 | 90
2026-W14 | 2026-04-12 | M02 | PASINS01 | Instrumentación | 30 | 11.4 | 3.5 | 1.9 | 16.8 | 56 | No | 5 | 4 | 500111 | PM02 | PM - Servidor secundario | 1020094 | 149.1 | 90
2026-W14 | 2026-04-12 | M02 | PAHMEC01 | Mecánica | 31 | 8.9 | 8.5 | 2.6 | 20 | 64.5 | No | 2 | 4 | 500144 | PM02 | PM - Motor eléctrico PU0516M1 |  | 144.5 | 90
2026-W14 | 2026-04-12 | M02 | PAHMEC01 | Eléctrica | 20 | 9.4 | 5.3 | 1.4 | 16.1 | 80.5 | No | 3 | 3 | 500108 | PM02 | PM - Motor eléctrico HY0036M1 |  | 150.8 | 90
2026-W14 | 2026-04-12 | M02 | PAHMEC01 | Instrumentación | 27 | 11.9 | 5.8 | 1.8 | 19.5 | 72.2 | No | 3 | 4 | 500132 | PM02 | PM - Válvula control agua sello HV2723 | 1005344 | 96.4 | 90
2026-W14 | 2026-04-12 | M02 | PAHELE01 | Mecánica | 23 | 10 | 4.5 | 2.2 | 16.7 | 72.6 | No | 2 | 3 | 500064 | PM01 | CM - Válvula control drenaje relaves alimentación HV4602 |  | 106.5 | 90
2026-W14 | 2026-04-12 | M02 | PAHELE01 | Eléctrica | 17 | 4.4 | 2.3 | 1 | 7.7 | 45.3 | No | 5 | 3 | 500010 | PM02 | PM - Tablero SCI |  | 95.4 | 90
2026-W14 | 2026-04-12 | M02 | PAHELE01 | Instrumentación | 30 | 4.6 | 5.6 | 1.5 | 11.7 | 39 | No | 5 | 4 | 500046 | PM02 | PM - Gabinete servidor core switch 1 y commun |  | 38.7 | 90
2026-W14 | 2026-04-12 | M02 | PAHINS01 | Mecánica | 18 | 8.7 | 4.4 | 1.3 | 14.4 | 80 | No | 7 | 1 | 500155 | PM02 | PM - Válvula control salida precapa HV3102 |  | 51.2 | 90
2026-W14 | 2026-04-12 | M02 | PAHINS01 | Eléctrica | 37 | 16.4 | 4.1 | 1.2 | 21.7 | 58.6 | No | 2 | 2 | 500112 | PM02 | PM - Hidrante/ Grifos FH0129 |  | 108.5 | 90
2026-W14 | 2026-04-12 | M02 | PAHINS01 | Instrumentación | 30 | 5.2 | 7.6 | 0.8 | 13.6 | 45.3 | No | 5 | 2 | 500164 | PM02 | PM - Bomba muestreo pulpa relaves PU0267 | 1002650 | 126.3 | 90
2026-W14 | 2026-04-12 | P01 | PASMEC01 | Mecánica | 36 | 15.1 | 3.1 | 1.4 | 19.6 | 54.4 | No | 2 | 3 | 500058 | PM01 | CM - Sensor temperatura aire TS4591 | 1002257 | 65.8 | 90
2026-W14 | 2026-04-12 | P01 | PASMEC01 | Eléctrica | 22 | 7.4 | 2.2 | 1.2 | 10.8 | 49.1 | No | 7 | 1 | 500014 | PM02 | PM - Válvula control descarga agua filtrado HV4824 |  | 81 | 90
2026-W14 | 2026-04-12 | P01 | PASMEC01 | Instrumentación | 20 | 5.4 | 5.1 | 0.7 | 11.2 | 56 | No | 3 | 2 | 500181 | PM01 | CM - Bomba diafragma grasa PU0001 | 1002635 | 174.4 | 90
2026-W14 | 2026-04-12 | P01 | PASELE01 | Mecánica | 36 | 13.2 | 7 | 1.7 | 21.9 | 60.8 | No | 6 | 2 | 500144 | PM02 | PM - Motor eléctrico PU0516M1 | 1005111 | 151.8 | 90
2026-W14 | 2026-04-12 | P01 | PASELE01 | Eléctrica | 36 | 5.6 | 5 | 3.5 | 14.1 | 39.2 | No | 7 | 2 | 500070 | PM02 | PM - Transmisor nivel hidrox sodio LIT3467 |  | 149 | 90
2026-W14 | 2026-04-12 | P01 | PASELE01 | Instrumentación | 35 | 8.4 | 2.2 | 1.8 | 12.4 | 35.4 | No | 3 | 1 | 500101 | PM02 | PM - Subestación unitaria | 1001405 | 48.4 | 90
2026-W14 | 2026-04-12 | P01 | PASINS01 | Mecánica | 34 | 10.4 | 4.8 | 0.5 | 15.7 | 46.2 | No | 7 | 2 | 500132 | PM02 | PM - Válvula control agua sello HV2723 |  | 155.5 | 90
2026-W14 | 2026-04-12 | P01 | PASINS01 | Eléctrica | 35 | 9.6 | 8.5 | 0.1 | 18.2 | 52 | No | 5 | 4 | 500024 | PM02 | PM - Válvula alivio presión aceite PRV0664 |  | 56.6 | 90
2026-W14 | 2026-04-12 | P01 | PASINS01 | Instrumentación | 31 | 5 | 2.3 | 1.9 | 9.2 | 29.7 | No | 2 | 4 | 500154 | PM02 | PM - Lava ojos emergencia |  | 35.6 | 90
2026-W14 | 2026-04-12 | P01 | PAHMEC01 | Mecánica | 30 | 7.9 | 6 | 1 | 14.9 | 49.7 | No | 6 | 4 | 500054 | PM01 | CM - Intercambiador calor calentamiento | 1002453 | 198.7 | 90
2026-W14 | 2026-04-12 | P01 | PAHMEC01 | Eléctrica | 31 | 15.1 | 7.1 | 0.4 | 22.6 | 72.9 | No | 4 | 4 | 500038 | PM02 | PM - Switch bajo flujo aire FSL1357A | 1004284 | 79.2 | 90
2026-W14 | 2026-04-12 | P01 | PAHMEC01 | Instrumentación | 21 | 9.5 | 4.5 | 0.1 | 14.1 | 67.1 | No | 4 | 2 | 500057 | PM01 | CM - Bomba rotativa aceite PU0510 | 1002321 | 112.1 | 90
2026-W14 | 2026-04-12 | P01 | PAHELE01 | Mecánica | 28 | 4.4 | 5.2 | 1.6 | 11.2 | 40 | No | 7 | 1 | 500119 | PM01 | CM - Calefactor eléctrico HE0137 |  | 28.8 | 90
2026-W14 | 2026-04-12 | P01 | PAHELE01 | Eléctrica | 35 | 8 | 6.8 | 0 | 14.8 | 42.3 | No | 3 | 4 | 500014 | PM02 | PM - Válvula control descarga agua filtrado HV4824 |  | 42.7 | 90
2026-W14 | 2026-04-12 | P01 | PAHELE01 | Instrumentación | 20 | 9.6 | 4.6 | 0.9 | 15.1 | 75.5 | No | 6 | 2 | 500080 | PM02 | PM - Válvula control aire soplado HV4658 |  | 185.6 | 90
2026-W14 | 2026-04-12 | P01 | PAHINS01 | Mecánica | 37 | 11.2 | 3.3 | 3.4 | 17.9 | 48.4 | No | 7 | 2 | 500132 | PM02 | PM - Válvula control agua sello HV2723 | 1002584 | 199 | 90
2026-W14 | 2026-04-12 | P01 | PAHINS01 | Eléctrica | 20 | 4.4 | 4.3 | 1.2 | 9.9 | 49.5 | No | 4 | 2 | 500162 | PM02 | PM - Tecle bomba sumergible lixiviación |  | 170.4 | 90
2026-W14 | 2026-04-12 | P01 | PAHINS01 | Instrumentación | 29 | 10.5 | 2.1 | 2 | 14.6 | 50.3 | No | 4 | 4 | 500147 | PM02 | PM - Baliza YL3612 |  | 136.8 | 90
2026-W14 | 2026-04-12 | P02 | PASMEC01 | Mecánica | 38 | 13.6 | 8.7 | 0.9 | 23.2 | 61.1 | No | 3 | 1 | 500060 | PM01 | CM - Indicador presión descarga agua PI5057 | 1003391 | 185 | 90
2026-W14 | 2026-04-12 | P02 | PASMEC01 | Eléctrica | 26 | 4.9 | 3.9 | 1 | 9.8 | 37.7 | No | 6 | 2 | 500110 | PM02 | PM - Válvula control entrada pulpa HV1706 | 1000664 | 125.3 | 90
2026-W14 | 2026-04-12 | P02 | PASMEC01 | Instrumentación | 25 | 12 | 7 | 1.4 | 20.4 | 81.6 | No | 5 | 2 | 500109 | PM02 | PM - Variador frecuencia 3620PU0239M1VF |  | 21.3 | 90
2026-W14 | 2026-04-12 | P02 | PASELE01 | Mecánica | 21 | 8.5 | 3.3 | 0.2 | 12 | 57.1 | No | 5 | 2 | 500058 | PM01 | CM - Sensor temperatura aire TS4591 |  | 169.7 | 90
2026-W14 | 2026-04-12 | P02 | PASELE01 | Eléctrica | 39 | 11.7 | 2.1 | 0.5 | 14.3 | 36.7 | No | 2 | 4 | 500159 | PM02 | PM - Gabinete manguera y equipo contraincendios HH0119 |  | 124.1 | 90
2026-W14 | 2026-04-12 | P02 | PASELE01 | Instrumentación | 38 | 11.9 | 5.1 | 0.6 | 17.6 | 46.3 | No | 7 | 3 | 500019 | PM02 | PM - Transmisor nivel lechada cal LIT5314 |  | 23.7 | 90
2026-W14 | 2026-04-12 | P02 | PASINS01 | Mecánica | 33 | 11.6 | 7 | 2.1 | 20.7 | 62.7 | No | 5 | 1 | 500094 | PM02 | PM - Switch baja presión descarga fluido térmico PSL3498 |  | 46.6 | 90
2026-W14 | 2026-04-12 | P02 | PASINS01 | Eléctrica | 33 | 13.2 | 8.1 | 2.9 | 24.2 | 73.3 | No | 3 | 4 | 500183 | PM01 | CM - Estanque separador TK0054 | 1000831 | 35.1 | 90
2026-W14 | 2026-04-12 | P02 | PASINS01 | Instrumentación | 32 | 10.2 | 8.3 | 1.4 | 19.9 | 62.2 | No | 4 | 4 | 500116 | PM01 | CM - Transmisor nivel hidrox sodio LIT3467 | 1000476 | 114.9 | 90
2026-W14 | 2026-04-12 | P02 | PAHMEC01 | Mecánica | 20 | 7.9 | 4 | 1.4 | 13.3 | 66.5 | No | 3 | 3 | 500047 | PM01 | CM - Indicador presión agua PI0251 |  | 126.6 | 90
2026-W14 | 2026-04-12 | P02 | PAHMEC01 | Eléctrica | 38 | 9.4 | 3 | 1.6 | 14 | 36.8 | No | 3 | 2 | 500118 | PM01 | CM - Gabinete RIO | 1002449 | 140.2 | 90
2026-W14 | 2026-04-12 | P02 | PAHMEC01 | Instrumentación | 33 | 12 | 2.7 | 2.9 | 17.6 | 53.3 | No | 2 | 2 | 500004 | PM02 | PM - Válvula control aceite XV0256D |  | 156 | 90
2026-W14 | 2026-04-12 | P02 | PAHELE01 | Mecánica | 19 | 6.1 | 5.2 | 1.8 | 13.1 | 68.9 | No | 6 | 3 | 500047 | PM01 | CM - Indicador presión agua PI0251 | 1001734 | 58.7 | 90
2026-W14 | 2026-04-12 | P02 | PAHELE01 | Eléctrica | 20 | 9.6 | 3 | 1.2 | 13.8 | 69 | No | 7 | 1 | 500047 | PM01 | CM - Indicador presión agua PI0251 |  | 50.6 | 90
2026-W14 | 2026-04-12 | P02 | PAHELE01 | Instrumentación | 17 | 6.5 | 3.1 | 0.5 | 10.1 | 59.4 | No | 3 | 2 | 500075 | PM02 | PM - Switch posición giro rastras ZS4377D |  | 173.3 | 90
2026-W14 | 2026-04-12 | P02 | PAHINS01 | Mecánica | 33 | 8.3 | 8.2 | 0.6 | 17.1 | 51.8 | No | 4 | 1 | 500090 | PM02 | PM - Válvula control succión sol rica HV2807 |  | 137.8 | 90
2026-W14 | 2026-04-12 | P02 | PAHINS01 | Eléctrica | 36 | 11.8 | 7.8 | 2.1 | 21.7 | 60.3 | No | 7 | 2 | 500061 | PM01 | CM - Transmisor presión aceite PIT4875 |  | 32 | 90
2026-W14 | 2026-04-12 | P02 | PAHINS01 | Instrumentación | 32 | 12.1 | 6.6 | 1.3 | 20 | 62.5 | No | 6 | 4 | 500003 | PM02 | PM - Tablero de comunicación | 1003697 | 50.3 | 90
2026-W15 | 2026-04-13 | M01 | PASMEC01 | Mecánica | 27 | 7.1 | 6.4 | 1.7 | 15.2 | 56.3 | No | 5 | 1 | 500094 | PM02 | PM - Switch baja presión descarga fluido térmico PSL3498 |  | 155.9 | 90
2026-W15 | 2026-04-13 | M01 | PASMEC01 | Eléctrica | 39 | 13.9 | 7.4 | 0 | 21.3 | 54.6 | No | 5 | 3 | 500081 | PM02 | PM - Transmisor nivel lechada cal LIT5271 |  | 87.7 | 90
2026-W15 | 2026-04-13 | M01 | PASMEC01 | Instrumentación | 27 | 10.5 | 5.1 | 1.2 | 16.8 | 62.2 | No | 6 | 3 | 500051 | PM01 | CM - Tablero distribución UPS |  | 142.4 | 90
2026-W15 | 2026-04-13 | M01 | PASELE01 | Mecánica | 19 | 6.6 | 3.1 | 1 | 10.7 | 56.3 | No | 6 | 1 | 500170 | PM02 | PM - Switch posición ZS0038A |  | 196 | 90
2026-W15 | 2026-04-13 | M01 | PASELE01 | Eléctrica | 28 | 9.6 | 2.3 | 0.1 | 12 | 42.9 | No | 5 | 1 | 500154 | PM02 | PM - Lava ojos emergencia |  | 144.1 | 90
2026-W15 | 2026-04-13 | M01 | PASELE01 | Instrumentación | 30 | 10.9 | 4.4 | 0.9 | 16.2 | 54 | No | 5 | 1 | 500093 | PM02 | PM - Sensor temperatura horno TE3533 |  | 109.7 | 90
2026-W15 | 2026-04-13 | M01 | PASINS01 | Mecánica | 38 | 15.4 | 10.7 | 1.7 | 27.8 | 73.2 | No | 4 | 1 | 500049 | PM01 | CM - Válvula control alimenta pulpa HV1501K | 1000704 | 184.6 | 90
2026-W15 | 2026-04-13 | M01 | PASINS01 | Eléctrica | 29 | 4.8 | 2.7 | 2.4 | 9.9 | 34.1 | No | 7 | 3 | 500005 | PM02 | PM - Válvula control succión agua fresca HV7808 |  | 138.6 | 90
2026-W15 | 2026-04-13 | M01 | PASINS01 | Instrumentación | 34 | 14.3 | 2.9 | 1.8 | 19 | 55.9 | No | 4 | 2 | 500090 | PM02 | PM - Válvula control succión sol rica HV2807 | 1006887 | 177.1 | 90
2026-W15 | 2026-04-13 | M01 | PAHMEC01 | Mecánica | 17 | 6.5 | 2.4 | 1.7 | 10.6 | 62.4 | No | 6 | 3 | 500039 | PM02 | PM - Chute carbónHO0068 |  | 82.7 | 90
2026-W15 | 2026-04-13 | M01 | PAHMEC01 | Eléctrica | 37 | 12.1 | 2.2 | 1.9 | 16.2 | 43.8 | No | 3 | 4 | 500129 | PM01 | CM - Gabinete control Chancador Primario |  | 123.9 | 90
2026-W15 | 2026-04-13 | M01 | PAHMEC01 | Instrumentación | 37 | 14.7 | 3.9 | 0.5 | 19.1 | 51.6 | No | 6 | 2 | 500100 | PM02 | PM - Puerta enrollable Stockpile |  | 96.5 | 90
2026-W15 | 2026-04-13 | M01 | PAHELE01 | Mecánica | 31 | 9.2 | 2.2 | 1.2 | 12.6 | 40.6 | No | 7 | 4 | 500182 | PM01 | CM - Transmisor nivel agua potable LIT0060 | 1004284 | 191.6 | 90
2026-W15 | 2026-04-13 | M01 | PAHELE01 | Eléctrica | 17 | 8.2 | 3 | 0.2 | 11.4 | 67.1 | No | 7 | 2 | 500057 | PM01 | CM - Bomba rotativa aceite PU0510 |  | 199.5 | 90
2026-W15 | 2026-04-13 | M01 | PAHELE01 | Instrumentación | 30 | 14.5 | 8 | 0.7 | 23.2 | 77.3 | No | 7 | 2 | 500152 | PM02 | PM - Válvula control entrada pulpa HV1706 |  | 56.2 | 90
2026-W15 | 2026-04-13 | M01 | PAHINS01 | Mecánica | 22 | 10.6 | 5.7 | 1.6 | 17.9 | 81.4 | No | 7 | 2 | 500158 | PM02 | PM - Válvula control flujo sol barren FV5601 |  | 69.7 | 90
2026-W15 | 2026-04-13 | M01 | PAHINS01 | Eléctrica | 27 | 4.3 | 2.8 | 2.4 | 9.5 | 35.2 | No | 4 | 1 | 500106 | PM02 | PM - Válvula control succión ayuda filtrante HV3281 |  | 96.1 | 90
2026-W15 | 2026-04-13 | M01 | PAHINS01 | Instrumentación | 37 | 13.6 | 9.6 | 2.7 | 25.9 | 70 | No | 5 | 3 | 500135 | PM02 | PM - Compresor de aire neumático |  | 28.1 | 90
2026-W15 | 2026-04-13 | M02 | PASMEC01 | Mecánica | 16 | 4.8 | 2.9 | 0.8 | 8.5 | 53.1 | No | 3 | 3 | 500014 | PM02 | PM - Válvula control descarga agua filtrado HV4824 |  | 155.9 | 90
2026-W15 | 2026-04-13 | M02 | PASMEC01 | Eléctrica | 28 | 5.4 | 4.6 | 2.7 | 12.7 | 45.4 | No | 4 | 1 | 500080 | PM02 | PM - Válvula control aire soplado HV4658 |  | 88.2 | 90
2026-W15 | 2026-04-13 | M02 | PASMEC01 | Instrumentación | 33 | 5.3 | 6.8 | 2.9 | 15 | 45.5 | No | 6 | 1 | 500106 | PM02 | PM - Válvula control succión ayuda filtrante HV3281 |  | 101.2 | 90
2026-W15 | 2026-04-13 | M02 | PASELE01 | Mecánica | 38 | 11.8 | 9.3 | 2 | 23.1 | 60.8 | No | 4 | 3 | 500070 | PM02 | PM - Transmisor nivel hidrox sodio LIT3467 | 1005933 | 148.9 | 90
2026-W15 | 2026-04-13 | M02 | PASELE01 | Eléctrica | 21 | 6.3 | 6 | 1.7 | 14 | 66.7 | No | 7 | 1 | 500184 | PM01 | CM - Válvula control descarga agua filtrado HV4812 | 1002298 | 108.8 | 90
2026-W15 | 2026-04-13 | M02 | PASELE01 | Instrumentación | 38 | 14.6 | 9.5 | 0.9 | 25 | 65.8 | No | 2 | 3 | 500107 | PM02 | PM - Gabinete manguera y equipo contraincendios HH0105 | 1006340 | 105.6 | 90
2026-W15 | 2026-04-13 | M02 | PASINS01 | Mecánica | 27 | 13.4 | 7.7 | 2.3 | 23.4 | 86.7 | No | 3 | 1 | 500178 | PM01 | CM - Sensor temperatura TE0802 | 1003142 | 104.2 | 90
2026-W15 | 2026-04-13 | M02 | PASINS01 | Eléctrica | 32 | 14.6 | 9.3 | 2.9 | 26.8 | 83.8 | No | 4 | 2 | 500127 | PM01 | CM - Válvula control succión agua filtrado HV4810 | 1000672 | 125.3 | 90
2026-W15 | 2026-04-13 | M02 | PASINS01 | Instrumentación | 39 | 18.6 | 4.4 | 2.1 | 25.1 | 64.4 | No | 5 | 3 | 500148 | PM02 | PM - Válvula control descarga sol rica HV2810 | 1000944 | 142.3 | 90
2026-W15 | 2026-04-13 | M02 | PAHMEC01 | Mecánica | 25 | 10.6 | 5 | 1.7 | 17.3 | 69.2 | No | 3 | 4 | 500149 | PM02 | PM - Indicador presión aceite PI1315 | 1002540 | 106.6 | 90
2026-W15 | 2026-04-13 | M02 | PAHMEC01 | Eléctrica | 33 | 15.7 | 6.2 | 2 | 23.9 | 72.4 | No | 3 | 2 | 500120 | PM01 | CM - Transmisor presión salida sol barren PIT3241 | 1005433 | 50.6 | 90
2026-W15 | 2026-04-13 | M02 | PAHMEC01 | Instrumentación | 21 | 6.7 | 3.5 | 0.9 | 11.1 | 52.9 | No | 6 | 2 | 500165 | PM02 | PM - Motor eléctrico HY0036M1 |  | 118 | 90
2026-W15 | 2026-04-13 | M02 | PAHELE01 | Mecánica | 32 | 6.2 | 6.8 | 2.6 | 15.6 | 48.8 | No | 5 | 1 | 500082 | PM02 | PM - Válvula control agua filtrada HV4568B | 1003671 | 75.9 | 90
2026-W15 | 2026-04-13 | M02 | PAHELE01 | Eléctrica | 25 | 5.8 | 3.8 | 0.6 | 10.2 | 40.8 | No | 3 | 1 | 500165 | PM02 | PM - Motor eléctrico HY0036M1 |  | 39.5 | 90
2026-W15 | 2026-04-13 | M02 | PAHELE01 | Instrumentación | 29 | 12.1 | 4.5 | 2.8 | 19.4 | 66.9 | No | 6 | 2 | 500147 | PM02 | PM - Baliza YL3612 |  | 173.7 | 90
2026-W15 | 2026-04-13 | M02 | PAHINS01 | Mecánica | 26 | 7.1 | 2.8 | 0.7 | 10.6 | 40.8 | No | 7 | 1 | 500085 | PM02 | PM - Gabinete servidor core switch 1 y commun |  | 25.5 | 90
2026-W15 | 2026-04-13 | M02 | PAHINS01 | Eléctrica | 26 | 9.6 | 5.5 | 1.4 | 16.5 | 63.5 | No | 4 | 4 | 500189 | PM01 | CM - Switch gear SAG 630 A, 6.9 Kv, 31.5 kA | 1020086 | 121.4 | 90
2026-W15 | 2026-04-13 | M02 | PAHINS01 | Instrumentación | 31 | 4.5 | 3.4 | 0.5 | 8.4 | 27.1 | No | 3 | 1 | 500117 | PM01 | CM - Válvula control agua filtrada HV4568B | 1006634 | 140.9 | 90
2026-W15 | 2026-04-13 | P01 | PASMEC01 | Mecánica | 24 | 9.8 | 5.8 | 0 | 15.6 | 65 | No | 6 | 1 | 500071 | PM02 | PM - Calefactor eléctrico estanque HE0112 |  | 166.6 | 90
2026-W15 | 2026-04-13 | P01 | PASMEC01 | Eléctrica | 30 | 9.2 | 5.9 | 2.5 | 17.6 | 58.7 | No | 2 | 2 | 500033 | PM02 | PM - Válvula control entrada lechada cal HV5311 |  | 57.1 | 90
2026-W15 | 2026-04-13 | P01 | PASMEC01 | Instrumentación | 39 | 15.5 | 11.3 | 2.6 | 29.4 | 75.4 | No | 2 | 2 | 500061 | PM01 | CM - Transmisor presión aceite PIT4875 | 1006172 | 190.2 | 90
2026-W15 | 2026-04-13 | P01 | PASELE01 | Mecánica | 22 | 4.9 | 6 | 1.1 | 12 | 54.5 | No | 2 | 1 | 500186 | PM01 | CM - Tablero distribución instrumentación | 1006567 | 49.2 | 90
2026-W15 | 2026-04-13 | P01 | PASELE01 | Eléctrica | 18 | 7.4 | 4.7 | 1 | 13.1 | 72.8 | No | 6 | 2 | 500086 | PM02 | PM - Sensor nivel refrigerante LE0177 |  | 189.6 | 90
2026-W15 | 2026-04-13 | P01 | PASELE01 | Instrumentación | 28 | 4 | 6 | 1.7 | 11.7 | 41.8 | No | 7 | 4 | 500098 | PM02 | PM - Unidad presurización | 1004294 | 101.3 | 90
2026-W15 | 2026-04-13 | P01 | PASINS01 | Mecánica | 21 | 9.5 | 2.5 | 0.2 | 12.2 | 58.1 | No | 4 | 4 | 500098 | PM02 | PM - Unidad presurización |  | 115.8 | 90
2026-W15 | 2026-04-13 | P01 | PASINS01 | Eléctrica | 39 | 16.8 | 6.4 | 2 | 25.2 | 64.6 | No | 4 | 2 | 500085 | PM02 | PM - Gabinete servidor core switch 1 y commun | 1006166 | 100.7 | 90
2026-W15 | 2026-04-13 | P01 | PASINS01 | Instrumentación | 24 | 5 | 2.5 | 1.8 | 9.3 | 38.8 | No | 4 | 2 | 500112 | PM02 | PM - Hidrante/ Grifos FH0129 |  | 163.6 | 90
2026-W15 | 2026-04-13 | P01 | PAHMEC01 | Mecánica | 23 | 4.1 | 2.5 | 1.1 | 7.7 | 33.5 | No | 6 | 4 | 500074 | PM02 | PM - Transmisor presión agua potable PIT7025 |  | 80.3 | 90
2026-W15 | 2026-04-13 | P01 | PAHMEC01 | Eléctrica | 28 | 12.4 | 5.3 | 0.4 | 18.1 | 64.6 | No | 7 | 2 | 500112 | PM02 | PM - Hidrante/ Grifos FH0129 |  | 100.6 | 90
2026-W15 | 2026-04-13 | P01 | PAHMEC01 | Instrumentación | 29 | 6.8 | 5.6 | 2.4 | 14.8 | 51 | No | 5 | 4 | 500167 | PM02 | PM - Sensor temperatura TE0802 |  | 149.1 | 90
2026-W15 | 2026-04-13 | P01 | PAHELE01 | Mecánica | 30 | 7.3 | 7.4 | 1 | 15.7 | 52.3 | No | 5 | 2 | 500088 | PM02 | PM - Transmisor presión entrada sol precipitado PIT3017 |  | 50.4 | 90
2026-W15 | 2026-04-13 | P01 | PAHELE01 | Eléctrica | 23 | 5 | 4.2 | 1.2 | 10.4 | 45.2 | No | 4 | 2 | 500038 | PM02 | PM - Switch bajo flujo aire FSL1357A |  | 134 | 90
2026-W15 | 2026-04-13 | P01 | PAHELE01 | Instrumentación | 31 | 12.8 | 7.7 | 1.8 | 22.3 | 71.9 | No | 6 | 4 | 500138 | PM02 | PM - Motor eléctrico HY0036M1 |  | 77.3 | 90
2026-W15 | 2026-04-13 | P01 | PAHINS01 | Mecánica | 33 | 7.9 | 6.1 | 2.2 | 16.2 | 49.1 | No | 7 | 1 | 500063 | PM01 | CM - Válvula control entrada solucion barren FV2314 | 1002080 | 165.9 | 90
2026-W15 | 2026-04-13 | P01 | PAHINS01 | Eléctrica | 19 | 5.6 | 4 | 0 | 9.6 | 50.5 | No | 7 | 4 | 500135 | PM02 | PM - Compresor de aire neumático |  | 95.2 | 90
2026-W15 | 2026-04-13 | P01 | PAHINS01 | Instrumentación | 21 | 9.4 | 5.5 | 2 | 16.9 | 80.5 | No | 2 | 4 | 500154 | PM02 | PM - Lava ojos emergencia |  | 135.9 | 90
2026-W15 | 2026-04-13 | P02 | PASMEC01 | Mecánica | 19 | 8.5 | 3.5 | 0.4 | 12.4 | 65.3 | No | 6 | 1 | 500110 | PM02 | PM - Válvula control entrada pulpa HV1706 |  | 118.8 | 90
2026-W15 | 2026-04-13 | P02 | PASMEC01 | Eléctrica | 33 | 11.2 | 5.5 | 2.2 | 18.9 | 57.3 | No | 6 | 1 | 500143 | PM02 | PM - Transmisor nivel solución barren LIT2787 |  | 23.2 | 90
2026-W15 | 2026-04-13 | P02 | PASMEC01 | Instrumentación | 18 | 8.7 | 2.3 | 0.5 | 11.5 | 63.9 | No | 6 | 3 | 500079 | PM02 | PM - Gabinete RIO |  | 81.3 | 90
2026-W15 | 2026-04-13 | P02 | PASELE01 | Mecánica | 39 | 15.6 | 3.3 | 1 | 19.9 | 51 | No | 5 | 2 | 500092 | PM02 | PM - Bomba precipitado |  | 49.7 | 90
2026-W15 | 2026-04-13 | P02 | PASELE01 | Eléctrica | 26 | 6.4 | 4 | 1.9 | 12.3 | 47.3 | No | 2 | 1 | 500125 | PM01 | CM - Transmisor presión aceite PIT4824 | 1002106 | 182.8 | 90
2026-W15 | 2026-04-13 | P02 | PASELE01 | Instrumentación | 39 | 5.5 | 9.8 | 1.4 | 16.7 | 42.8 | No | 4 | 1 | 500028 | PM02 | PM - Válvula control succión agua fresca HV7808 |  | 150.6 | 90
2026-W15 | 2026-04-13 | P02 | PASINS01 | Mecánica | 33 | 11.7 | 5.9 | 3.3 | 20.9 | 63.3 | No | 4 | 3 | 500191 | PM01 | CM - Calefactor eléctrico estanque HE0112 | 1005880 | 33.4 | 90
2026-W15 | 2026-04-13 | P02 | PASINS01 | Eléctrica | 31 | 12.7 | 3.5 | 1 | 17.2 | 55.5 | No | 2 | 3 | 500131 | PM01 | CM - Calefactor eléctrico estanque HE0012 |  | 115.4 | 90
2026-W15 | 2026-04-13 | P02 | PASINS01 | Instrumentación | 20 | 5.3 | 4.5 | 2 | 11.8 | 59 | No | 3 | 2 | 500097 | PM02 | PM - Gabinete RIO |  | 103 | 90
2026-W15 | 2026-04-13 | P02 | PAHMEC01 | Mecánica | 19 | 7.8 | 5.3 | 0.9 | 14 | 73.7 | No | 4 | 2 | 500006 | PM02 | PM - Válvula control entrada sol precipitado HV3185 |  | 65.2 | 90
2026-W15 | 2026-04-13 | P02 | PAHMEC01 | Eléctrica | 19 | 8.8 | 3.2 | 0.8 | 12.8 | 67.4 | No | 4 | 4 | 500023 | PM02 | PM - Válvula control entrada aire FV1804 |  | 120.9 | 90
2026-W15 | 2026-04-13 | P02 | PAHMEC01 | Instrumentación | 23 | 10.6 | 3 | 0.2 | 13.8 | 60 | No | 3 | 1 | 500178 | PM01 | CM - Sensor temperatura TE0802 | 1006853 | 170.4 | 90
2026-W15 | 2026-04-13 | P02 | PAHELE01 | Mecánica | 27 | 5.7 | 6.5 | 0.5 | 12.7 | 47 | No | 4 | 1 | 500051 | PM01 | CM - Tablero distribución UPS | 1006412 | 95.5 | 90
2026-W15 | 2026-04-13 | P02 | PAHELE01 | Eléctrica | 39 | 4.8 | 2.7 | 3.1 | 10.6 | 27.2 | No | 3 | 2 | 500074 | PM02 | PM - Transmisor presión agua potable PIT7025 | 1002556 | 64.2 | 90
2026-W15 | 2026-04-13 | P02 | PAHELE01 | Instrumentación | 25 | 8.9 | 6.3 | 0.5 | 15.7 | 62.8 | No | 6 | 4 | 500041 | PM02 | PM - Tecle bomba sumergible lixiviación |  | 33.6 | 90
2026-W15 | 2026-04-13 | P02 | PAHINS01 | Mecánica | 27 | 10.6 | 4.5 | 2.4 | 17.5 | 64.8 | No | 5 | 3 | 500085 | PM02 | PM - Gabinete servidor core switch 1 y commun |  | 22.1 | 90
2026-W15 | 2026-04-13 | P02 | PAHINS01 | Eléctrica | 24 | 8.6 | 4 | 1.3 | 13.9 | 57.9 | No | 5 | 3 | 500137 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 184.2 | 90
2026-W15 | 2026-04-13 | P02 | PAHINS01 | Instrumentación | 18 | 7.3 | 3.2 | 0.1 | 10.6 | 58.9 | No | 7 | 1 | 500176 | PM01 | CM - Válvula control succión nitrato plomo HV2962 |  | 149.5 | 90
2026-W15 | 2026-04-14 | M01 | PASMEC01 | Mecánica | 39 | 9.9 | 2.1 | 0 | 12 | 30.8 | No | 2 | 4 | 500042 | PM02 | PM - Válvula control salida precapa HV3102 |  | 107.9 | 90
2026-W15 | 2026-04-14 | M01 | PASMEC01 | Eléctrica | 31 | 8.6 | 3.3 | 2.6 | 14.5 | 46.8 | No | 2 | 3 | 500012 | PM02 | PM - Gabinete PLC horno fundición 1 | 1004944 | 50.1 | 90
2026-W15 | 2026-04-14 | M01 | PASMEC01 | Instrumentación | 37 | 5.4 | 4.7 | 0.2 | 10.3 | 27.8 | No | 7 | 4 | 500131 | PM01 | CM - Calefactor eléctrico estanque HE0012 | 1000283 | 48.3 | 90
2026-W15 | 2026-04-14 | M01 | PASELE01 | Mecánica | 35 | 14.2 | 2.9 | 1.6 | 18.7 | 53.4 | No | 6 | 1 | 500114 | PM01 | CM - Transmisor vibración VT0020A | 1006630 | 127.7 | 90
2026-W15 | 2026-04-14 | M01 | PASELE01 | Eléctrica | 31 | 5.6 | 8.1 | 0 | 13.7 | 44.2 | No | 3 | 3 | 500161 | PM02 | PM - Unidad aire acondicionado |  | 87.5 | 90
2026-W15 | 2026-04-14 | M01 | PASELE01 | Instrumentación | 28 | 13.5 | 7 | 0.8 | 21.3 | 76.1 | No | 5 | 4 | 500008 | PM02 | PM - Bomba precipitado |  | 97.8 | 90
2026-W15 | 2026-04-14 | M01 | PASINS01 | Mecánica | 17 | 5.2 | 4.9 | 0.6 | 10.7 | 62.9 | No | 2 | 3 | 500124 | PM01 | CM - Extractor taller EMP |  | 199.9 | 90
2026-W15 | 2026-04-14 | M01 | PASINS01 | Eléctrica | 31 | 7.4 | 7.3 | 0.7 | 15.4 | 49.7 | No | 7 | 2 | 500101 | PM02 | PM - Subestación unitaria |  | 148.7 | 90
2026-W15 | 2026-04-14 | M01 | PASINS01 | Instrumentación | 29 | 8.1 | 6.8 | 0.2 | 15.1 | 52.1 | No | 7 | 4 | 500110 | PM02 | PM - Válvula control entrada pulpa HV1706 | 1002592 | 22.6 | 90
2026-W15 | 2026-04-14 | M01 | PAHMEC01 | Mecánica | 27 | 13.2 | 6.4 | 0.9 | 20.5 | 75.9 | No | 5 | 1 | 500137 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 100.7 | 90
2026-W15 | 2026-04-14 | M01 | PAHMEC01 | Eléctrica | 23 | 6.1 | 4.1 | 0.8 | 11 | 47.8 | No | 6 | 4 | 500046 | PM02 | PM - Gabinete servidor core switch 1 y commun |  | 141.2 | 90
2026-W15 | 2026-04-14 | M01 | PAHMEC01 | Instrumentación | 36 | 8.3 | 10.7 | 0.3 | 19.3 | 53.6 | No | 3 | 1 | 500129 | PM01 | CM - Gabinete control Chancador Primario | 1001911 | 100.7 | 90
2026-W15 | 2026-04-14 | M01 | PAHELE01 | Mecánica | 19 | 6.7 | 5 | 1.8 | 13.5 | 71.1 | No | 4 | 1 | 500021 | PM02 | PM - Tornillo alimentador sulfato de cobre |  | 183.7 | 90
2026-W15 | 2026-04-14 | M01 | PAHELE01 | Eléctrica | 28 | 7.6 | 5 | 1.9 | 14.5 | 51.8 | No | 7 | 1 | 500162 | PM02 | PM - Tecle bomba sumergible lixiviación | 1001126 | 57.3 | 90
2026-W15 | 2026-04-14 | M01 | PAHELE01 | Instrumentación | 21 | 7.9 | 4.8 | 0.8 | 13.5 | 64.3 | No | 2 | 1 | 500059 | PM01 | CM - Mezclador floculante | 1001561 | 87.3 | 90
2026-W15 | 2026-04-14 | M01 | PAHINS01 | Mecánica | 30 | 11.4 | 3.1 | 0 | 14.5 | 48.3 | No | 4 | 2 | 500131 | PM01 | CM - Calefactor eléctrico estanque HE0012 | 1003865 | 132.3 | 90
2026-W15 | 2026-04-14 | M01 | PAHINS01 | Eléctrica | 32 | 4 | 5.3 | 1.6 | 10.9 | 34.1 | No | 5 | 3 | 500148 | PM02 | PM - Válvula control descarga sol rica HV2810 |  | 73.3 | 90
2026-W15 | 2026-04-14 | M01 | PAHINS01 | Instrumentación | 30 | 7.8 | 3.3 | 1.9 | 13 | 43.3 | No | 6 | 1 | 500126 | PM01 | CM - Válvula control salida carbon descargado HV3394 | 1000227 | 109.2 | 90
2026-W15 | 2026-04-14 | M02 | PASMEC01 | Mecánica | 17 | 4.3 | 3.4 | 1 | 8.7 | 51.2 | No | 4 | 2 | 500189 | PM01 | CM - Switch gear SAG 630 A, 6.9 Kv, 31.5 kA | 1000265 | 191.1 | 90
2026-W15 | 2026-04-14 | M02 | PASMEC01 | Eléctrica | 29 | 13.8 | 4.5 | 1.3 | 19.6 | 67.6 | No | 7 | 2 | 500116 | PM01 | CM - Transmisor nivel hidrox sodio LIT3467 |  | 27.1 | 90
2026-W15 | 2026-04-14 | M02 | PASMEC01 | Instrumentación | 18 | 4.8 | 3.9 | 1 | 9.7 | 53.9 | No | 3 | 3 | 500134 | PM02 | PM - Intercambiador calor por aire CQ0007 |  | 168.1 | 90
2026-W15 | 2026-04-14 | M02 | PASELE01 | Mecánica | 26 | 6.2 | 5.7 | 0.7 | 12.6 | 48.5 | No | 7 | 2 | 500172 | PM02 | PM - Tablero de comunicación |  | 65.8 | 90
2026-W15 | 2026-04-14 | M02 | PASELE01 | Eléctrica | 28 | 10.1 | 8 | 1.9 | 20 | 71.4 | No | 6 | 2 | 500175 | PM01 | CM - Válvula control aceite XV0279 | 1002505 | 102.9 | 90
2026-W15 | 2026-04-14 | M02 | PASELE01 | Instrumentación | 27 | 13.3 | 3.1 | 1 | 17.4 | 64.4 | No | 3 | 3 | 500131 | PM01 | CM - Calefactor eléctrico estanque HE0012 |  | 193.5 | 90
2026-W15 | 2026-04-14 | M02 | PASINS01 | Mecánica | 35 | 8.9 | 9.2 | 1.5 | 19.6 | 56 | No | 4 | 3 | 500030 | PM02 | PM - Indicador nivel solución LI5563 | 1003349 | 134.2 | 90
2026-W15 | 2026-04-14 | M02 | PASINS01 | Eléctrica | 24 | 4.3 | 5.1 | 0.4 | 9.8 | 40.8 | No | 5 | 4 | 500156 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 48.7 | 90
2026-W15 | 2026-04-14 | M02 | PASINS01 | Instrumentación | 20 | 4.9 | 2.1 | 0.9 | 7.9 | 39.5 | No | 4 | 3 | 500190 | PM01 | CM - Colector polvo horno fundición |  | 146.7 | 90
2026-W15 | 2026-04-14 | M02 | PAHMEC01 | Mecánica | 33 | 7.9 | 9.4 | 0.8 | 18.1 | 54.8 | No | 2 | 2 | 500163 | PM02 | PM - Válvula control salida precapa HV3102 | 1004137 | 69.5 | 90
2026-W15 | 2026-04-14 | M02 | PAHMEC01 | Eléctrica | 25 | 9.9 | 5.2 | 2.1 | 17.2 | 68.8 | No | 2 | 3 | 500051 | PM01 | CM - Tablero distribución UPS | 1005434 | 64.8 | 90
2026-W15 | 2026-04-14 | M02 | PAHMEC01 | Instrumentación | 27 | 4.1 | 4.7 | 2.3 | 11.1 | 41.1 | No | 2 | 3 | 500075 | PM02 | PM - Switch posición giro rastras ZS4377D |  | 76 | 90
2026-W15 | 2026-04-14 | M02 | PAHELE01 | Mecánica | 16 | 4.4 | 2.2 | 0.1 | 6.7 | 41.9 | No | 7 | 2 | 500176 | PM01 | CM - Válvula control succión nitrato plomo HV2962 | 1006417 | 148.3 | 90
2026-W15 | 2026-04-14 | M02 | PAHELE01 | Eléctrica | 30 | 12.2 | 2.4 | 0.7 | 15.3 | 51 | No | 6 | 4 | 500069 | PM02 | PM - Puerta Taller Camiones |  | 118.6 | 90
2026-W15 | 2026-04-14 | M02 | PAHELE01 | Instrumentación | 24 | 4.1 | 2.8 | 1 | 7.9 | 32.9 | No | 5 | 4 | 500094 | PM02 | PM - Switch baja presión descarga fluido térmico PSL3498 |  | 111.9 | 90
2026-W15 | 2026-04-14 | M02 | PAHINS01 | Mecánica | 19 | 6 | 4.9 | 1 | 11.9 | 62.6 | No | 7 | 4 | 500163 | PM02 | PM - Válvula control salida precapa HV3102 | 1002941 | 150.8 | 90
2026-W15 | 2026-04-14 | M02 | PAHINS01 | Eléctrica | 21 | 5.7 | 3.6 | 1 | 10.3 | 49 | No | 7 | 2 | 500016 | PM02 | PM - Lava ojos emergencia | 1004579 | 63.5 | 90
2026-W15 | 2026-04-14 | M02 | PAHINS01 | Instrumentación | 28 | 13.1 | 5.3 | 2.2 | 20.6 | 73.6 | No | 7 | 2 | 500168 | PM02 | PM - Gabinete RIO | 1001071 | 108.2 | 90
2026-W15 | 2026-04-14 | P01 | PASMEC01 | Mecánica | 24 | 10.2 | 6.2 | 1.2 | 17.6 | 73.3 | No | 3 | 3 | 500167 | PM02 | PM - Sensor temperatura TE0802 | 1005780 | 152.7 | 90
2026-W15 | 2026-04-14 | P01 | PASMEC01 | Eléctrica | 32 | 9.6 | 5.1 | 1.4 | 16.1 | 50.3 | No | 4 | 1 | 500124 | PM01 | CM - Extractor taller EMP |  | 173 | 90
2026-W15 | 2026-04-14 | P01 | PASMEC01 | Instrumentación | 20 | 8.1 | 5.8 | 1.4 | 15.3 | 76.5 | No | 5 | 1 | 500087 | PM02 | PM - Línea agua sell 3700-5476-AA1A-3"-WGS-ET | 1001603 | 70.2 | 90
2026-W15 | 2026-04-14 | P01 | PASELE01 | Mecánica | 34 | 9.1 | 8.1 | 1.3 | 18.5 | 54.4 | No | 4 | 3 | 500004 | PM02 | PM - Válvula control aceite XV0256D |  | 127.2 | 90
2026-W15 | 2026-04-14 | P01 | PASELE01 | Eléctrica | 37 | 7.4 | 11.1 | 3.5 | 22 | 59.5 | No | 6 | 2 | 500047 | PM01 | CM - Indicador presión agua PI0251 | 1020099 | 39 | 90
2026-W15 | 2026-04-14 | P01 | PASELE01 | Instrumentación | 26 | 12.2 | 3.6 | 2.1 | 17.9 | 68.8 | No | 7 | 1 | 500021 | PM02 | PM - Tornillo alimentador sulfato de cobre | 1003701 | 128.5 | 90
2026-W15 | 2026-04-14 | P01 | PASINS01 | Mecánica | 23 | 4.2 | 4.4 | 1.2 | 9.8 | 42.6 | No | 3 | 2 | 500181 | PM01 | CM - Bomba diafragma grasa PU0001 | 1006116 | 43.8 | 90
2026-W15 | 2026-04-14 | P01 | PASINS01 | Eléctrica | 21 | 5.1 | 3.8 | 1.7 | 10.6 | 50.5 | No | 6 | 3 | 500145 | PM02 | PM - Transmisor presion agua PT0404 |  | 77.2 | 90
2026-W15 | 2026-04-14 | P01 | PASINS01 | Instrumentación | 20 | 5.7 | 2.6 | 0.5 | 8.8 | 44 | No | 3 | 3 | 500099 | PM02 | PM - Indicador presión agua PI0251 | 1020115 | 113.5 | 90
2026-W15 | 2026-04-14 | P01 | PAHMEC01 | Mecánica | 30 | 14.4 | 3.4 | 1.9 | 19.7 | 65.7 | No | 3 | 2 | 500115 | PM01 | CM - Bomba vacío retorta |  | 120.8 | 90
2026-W15 | 2026-04-14 | P01 | PAHMEC01 | Eléctrica | 25 | 11.4 | 4 | 1.5 | 16.9 | 67.6 | No | 2 | 2 | 500151 | PM02 | PM - Válvula control flujo entrada agua rechazo FV3576 | 1001378 | 30.1 | 90
2026-W15 | 2026-04-14 | P01 | PAHMEC01 | Instrumentación | 27 | 6.1 | 6.3 | 2.1 | 14.5 | 53.7 | No | 4 | 2 | 500120 | PM01 | CM - Transmisor presión salida sol barren PIT3241 | 1000142 | 145.7 | 90
2026-W15 | 2026-04-14 | P01 | PAHELE01 | Mecánica | 28 | 10.5 | 4.7 | 1.2 | 16.4 | 58.6 | No | 3 | 3 | 500100 | PM02 | PM - Puerta enrollable Stockpile |  | 112.4 | 90
2026-W15 | 2026-04-14 | P01 | PAHELE01 | Eléctrica | 22 | 7.3 | 3.5 | 1.6 | 12.4 | 56.4 | No | 5 | 1 | 500190 | PM01 | CM - Colector polvo horno fundición | 1005662 | 184.6 | 90
2026-W15 | 2026-04-14 | P01 | PAHELE01 | Instrumentación | 28 | 13.6 | 5 | 1.2 | 19.8 | 70.7 | No | 4 | 1 | 500078 | PM02 | PM - Unidad aire acondicionado |  | 170.4 | 90
2026-W15 | 2026-04-14 | P01 | PAHINS01 | Mecánica | 32 | 5.3 | 7 | 1 | 13.3 | 41.6 | No | 7 | 1 | 500113 | PM01 | CM - Puerta enrollable Molienda | 1007000 | 57.2 | 90
2026-W15 | 2026-04-14 | P01 | PAHINS01 | Eléctrica | 34 | 7 | 8.1 | 1.8 | 16.9 | 49.7 | No | 2 | 3 | 500014 | PM02 | PM - Válvula control descarga agua filtrado HV4824 |  | 58.7 | 90
2026-W15 | 2026-04-14 | P01 | PAHINS01 | Instrumentación | 35 | 13.1 | 9.7 | 1.8 | 24.6 | 70.3 | No | 7 | 4 | 500150 | PM02 | PM - Válvula control entrada sol precipitado HV3185 |  | 101.2 | 90
2026-W15 | 2026-04-14 | P02 | PASMEC01 | Mecánica | 25 | 8.2 | 2.8 | 0.5 | 11.5 | 46 | No | 2 | 2 | 500083 | PM02 | PM - Válvula control descarga agua filtrado HV4824 |  | 95.9 | 90
2026-W15 | 2026-04-14 | P02 | PASMEC01 | Eléctrica | 28 | 8.8 | 2.1 | 2.1 | 13 | 46.4 | No | 5 | 1 | 500131 | PM01 | CM - Calefactor eléctrico estanque HE0012 |  | 149.3 | 90
2026-W15 | 2026-04-14 | P02 | PASMEC01 | Instrumentación | 29 | 5.4 | 5.5 | 2.3 | 13.2 | 45.5 | No | 7 | 1 | 500028 | PM02 | PM - Válvula control succión agua fresca HV7808 | 1003790 | 193.9 | 90
2026-W15 | 2026-04-14 | P02 | PASELE01 | Mecánica | 39 | 12.6 | 7.6 | 0.5 | 20.7 | 53.1 | No | 5 | 4 | 500063 | PM01 | CM - Válvula control entrada solucion barren FV2314 | 1005756 | 68.3 | 90
2026-W15 | 2026-04-14 | P02 | PASELE01 | Eléctrica | 27 | 7 | 7.1 | 1.2 | 15.3 | 56.7 | No | 4 | 1 | 500119 | PM01 | CM - Calefactor eléctrico HE0137 | 1004883 | 132 | 90
2026-W15 | 2026-04-14 | P02 | PASELE01 | Instrumentación | 18 | 7.2 | 2 | 0.1 | 9.3 | 51.7 | No | 5 | 3 | 500175 | PM01 | CM - Válvula control aceite XV0279 | 1001144 | 143.1 | 90
2026-W15 | 2026-04-14 | P02 | PASINS01 | Mecánica | 31 | 11.6 | 4.5 | 2.1 | 18.2 | 58.7 | No | 6 | 1 | 500166 | PM02 | PM - Bomba muestreo pulpa relaves PU0267 | 1002724 | 187.9 | 90
2026-W15 | 2026-04-14 | P02 | PASINS01 | Eléctrica | 20 | 7.9 | 3.4 | 1.6 | 12.9 | 64.5 | No | 4 | 4 | 500168 | PM02 | PM - Gabinete RIO |  | 197.3 | 90
2026-W15 | 2026-04-14 | P02 | PASINS01 | Instrumentación | 34 | 7.2 | 10.1 | 0.7 | 18 | 52.9 | No | 2 | 1 | 500009 | PM02 | PM - Estanque diesel dia regeneración carbón | 1003448 | 186.5 | 90
2026-W15 | 2026-04-14 | P02 | PAHMEC01 | Mecánica | 38 | 14.9 | 8.2 | 2.8 | 25.9 | 68.2 | No | 4 | 3 | 500052 | PM01 | CM - Tablero distribución instrumentación | 1005323 | 167.7 | 90
2026-W15 | 2026-04-14 | P02 | PAHMEC01 | Eléctrica | 21 | 8.9 | 3.1 | 1 | 13 | 61.9 | No | 2 | 3 | 500053 | PM01 | CM - Indicador presión aceite hidráulico PI4895E | 1002382 | 68.8 | 90
2026-W15 | 2026-04-14 | P02 | PAHMEC01 | Instrumentación | 36 | 9.9 | 9 | 1.7 | 20.6 | 57.2 | No | 7 | 3 | 500041 | PM02 | PM - Tecle bomba sumergible lixiviación | 1000068 | 26.3 | 90
2026-W15 | 2026-04-14 | P02 | PAHELE01 | Mecánica | 19 | 6 | 3.5 | 1.3 | 10.8 | 56.8 | No | 6 | 1 | 500008 | PM02 | PM - Bomba precipitado |  | 117.6 | 90
2026-W15 | 2026-04-14 | P02 | PAHELE01 | Eléctrica | 35 | 12.9 | 7.5 | 0.1 | 20.5 | 58.6 | No | 2 | 1 | 500125 | PM01 | CM - Transmisor presión aceite PIT4824 | 1004009 | 34.2 | 90
2026-W15 | 2026-04-14 | P02 | PAHELE01 | Instrumentación | 35 | 11 | 2.1 | 0.9 | 14 | 40 | No | 7 | 4 | 500120 | PM01 | CM - Transmisor presión salida sol barren PIT3241 | 1004791 | 123.2 | 90
2026-W15 | 2026-04-14 | P02 | PAHINS01 | Mecánica | 16 | 7.7 | 2.9 | 0.2 | 10.8 | 67.5 | No | 2 | 2 | 500016 | PM02 | PM - Lava ojos emergencia |  | 159.7 | 90
2026-W15 | 2026-04-14 | P02 | PAHINS01 | Eléctrica | 39 | 6 | 8.6 | 2.2 | 16.8 | 43.1 | No | 3 | 3 | 500113 | PM01 | CM - Puerta enrollable Molienda | 1002316 | 153 | 90
2026-W15 | 2026-04-14 | P02 | PAHINS01 | Instrumentación | 25 | 9 | 2.1 | 0.6 | 11.7 | 46.8 | No | 7 | 2 | 500035 | PM02 | PM - Agitador estanque filtración |  | 65.3 | 90
2026-W15 | 2026-04-15 | M01 | PASMEC01 | Mecánica | 25 | 11.5 | 6.2 | 0.1 | 17.8 | 71.2 | No | 3 | 4 | 500050 | PM01 | CM - Línea agua sell 3700-5476-AA1A-3"-WGS-ET | 1000661 | 69.4 | 90
2026-W15 | 2026-04-15 | M01 | PASMEC01 | Eléctrica | 30 | 11 | 7.3 | 2 | 20.3 | 67.7 | No | 4 | 1 | 500069 | PM02 | PM - Puerta Taller Camiones |  | 162.5 | 90
2026-W15 | 2026-04-15 | M01 | PASMEC01 | Instrumentación | 33 | 11.2 | 5.1 | 1.2 | 17.5 | 53 | No | 3 | 4 | 500101 | PM02 | PM - Subestación unitaria |  | 64.9 | 90
2026-W15 | 2026-04-15 | M01 | PASELE01 | Mecánica | 16 | 6.4 | 4.6 | 0.1 | 11.1 | 69.4 | No | 6 | 1 | 500161 | PM02 | PM - Unidad aire acondicionado |  | 162.1 | 90
2026-W15 | 2026-04-15 | M01 | PASELE01 | Eléctrica | 24 | 9.8 | 6.2 | 2.1 | 18.1 | 75.4 | No | 3 | 2 | 500189 | PM01 | CM - Switch gear SAG 630 A, 6.9 Kv, 31.5 kA | 1001059 | 72.9 | 90
2026-W15 | 2026-04-15 | M01 | PASELE01 | Instrumentación | 36 | 13.5 | 9 | 2.9 | 25.4 | 70.6 | No | 2 | 4 | 500065 | PM02 | PM - Muestreador alimentación filtros | 1000343 | 132.1 | 90
2026-W15 | 2026-04-15 | M01 | PASINS01 | Mecánica | 33 | 4.5 | 9.1 | 1.7 | 15.3 | 46.4 | No | 5 | 3 | 500175 | PM01 | CM - Válvula control aceite XV0279 | 1006582 | 170.9 | 90
2026-W15 | 2026-04-15 | M01 | PASINS01 | Eléctrica | 30 | 9.3 | 2.5 | 1.7 | 13.5 | 45 | No | 6 | 3 | 500076 | PM02 | PM - Cajón (Futuro) |  | 47.9 | 90
2026-W15 | 2026-04-15 | M01 | PASINS01 | Instrumentación | 20 | 6.2 | 4.2 | 1.3 | 11.7 | 58.5 | No | 3 | 2 | 500015 | PM02 | PM - Sensor temperatura aire TS4591 |  | 151.1 | 90
2026-W15 | 2026-04-15 | M01 | PAHMEC01 | Mecánica | 20 | 6.6 | 2.8 | 1.8 | 11.2 | 56 | No | 4 | 4 | 500026 | PM02 | PM - Estanque almacenamiento aceite hidráulico TK0088 | 1000406 | 56.9 | 90
2026-W15 | 2026-04-15 | M01 | PAHMEC01 | Eléctrica | 34 | 11.5 | 3.4 | 0.9 | 15.8 | 46.5 | No | 2 | 4 | 500021 | PM02 | PM - Tornillo alimentador sulfato de cobre |  | 87 | 90
2026-W15 | 2026-04-15 | M01 | PAHMEC01 | Instrumentación | 16 | 6.9 | 3.6 | 1.3 | 11.8 | 73.8 | No | 7 | 3 | 500020 | PM02 | PM - Cajón (Futuro) |  | 193.6 | 90
2026-W15 | 2026-04-15 | M01 | PAHELE01 | Mecánica | 31 | 4.6 | 6.9 | 2.8 | 14.3 | 46.1 | No | 5 | 3 | 500179 | PM01 | CM - Transmisor nivel atricción carbón LIT3627 | 1001479 | 53.1 | 90
2026-W15 | 2026-04-15 | M01 | PAHELE01 | Eléctrica | 38 | 7.2 | 3.9 | 3.8 | 14.9 | 39.2 | No | 4 | 4 | 500092 | PM02 | PM - Bomba precipitado | 1005526 | 154.7 | 90
2026-W15 | 2026-04-15 | M01 | PAHELE01 | Instrumentación | 35 | 5.4 | 8.1 | 2.4 | 15.9 | 45.4 | No | 5 | 1 | 500076 | PM02 | PM - Cajón (Futuro) |  | 27.5 | 90
2026-W15 | 2026-04-15 | M01 | PAHINS01 | Mecánica | 19 | 6.3 | 3.8 | 0.8 | 10.9 | 57.4 | No | 3 | 1 | 500086 | PM02 | PM - Sensor nivel refrigerante LE0177 |  | 81.8 | 90
2026-W15 | 2026-04-15 | M01 | PAHINS01 | Eléctrica | 18 | 8.2 | 2 | 0.3 | 10.5 | 58.3 | No | 5 | 4 | 500162 | PM02 | PM - Tecle bomba sumergible lixiviación |  | 79.1 | 90
2026-W15 | 2026-04-15 | M01 | PAHINS01 | Instrumentación | 32 | 5.5 | 7.7 | 1.5 | 14.7 | 45.9 | No | 3 | 2 | 500105 | PM02 | PM - Tablero SCI |  | 67.5 | 90
2026-W15 | 2026-04-15 | M02 | PASMEC01 | Mecánica | 27 | 6 | 2.2 | 1.2 | 9.4 | 34.8 | No | 6 | 1 | 500087 | PM02 | PM - Línea agua sell 3700-5476-AA1A-3"-WGS-ET |  | 23.7 | 90
2026-W15 | 2026-04-15 | M02 | PASMEC01 | Eléctrica | 16 | 6.5 | 3.5 | 0.1 | 10.1 | 63.1 | No | 5 | 2 | 500153 | PM02 | PM - Sistema Spray Grasa Engranaje - Molino SAG | 1006717 | 199.9 | 90
2026-W15 | 2026-04-15 | M02 | PASMEC01 | Instrumentación | 24 | 10.2 | 3.6 | 1.4 | 15.2 | 63.3 | No | 3 | 3 | 500012 | PM02 | PM - Gabinete PLC horno fundición 1 |  | 191.5 | 90
2026-W15 | 2026-04-15 | M02 | PASELE01 | Mecánica | 38 | 5.6 | 6.4 | 2.6 | 14.6 | 38.4 | No | 6 | 2 | 500027 | PM02 | PM - Válvula control aceite XV4883 | 1003452 | 188.9 | 90
2026-W15 | 2026-04-15 | M02 | PASELE01 | Eléctrica | 39 | 17 | 2.8 | 0.4 | 20.2 | 51.8 | No | 6 | 4 | 500106 | PM02 | PM - Válvula control succión ayuda filtrante HV3281 |  | 68.6 | 90
2026-W15 | 2026-04-15 | M02 | PASELE01 | Instrumentación | 33 | 9.5 | 6 | 2.2 | 17.7 | 53.6 | No | 3 | 4 | 500093 | PM02 | PM - Sensor temperatura horno TE3533 |  | 163.5 | 90
2026-W15 | 2026-04-15 | M02 | PASINS01 | Mecánica | 39 | 9.4 | 9.2 | 3 | 21.6 | 55.4 | No | 6 | 1 | 500099 | PM02 | PM - Indicador presión agua PI0251 | 1005411 | 62.1 | 90
2026-W15 | 2026-04-15 | M02 | PASINS01 | Eléctrica | 28 | 11.9 | 6.9 | 2.4 | 21.2 | 75.7 | No | 7 | 4 | 500176 | PM01 | CM - Válvula control succión nitrato plomo HV2962 | 1005944 | 121.8 | 90
2026-W15 | 2026-04-15 | M02 | PASINS01 | Instrumentación | 28 | 10 | 3.1 | 0.9 | 14 | 50 | No | 3 | 3 | 500177 | PM01 | CM - Intercambiador calor por aire CQ0007 | 1005094 | 122.2 | 90
2026-W15 | 2026-04-15 | M02 | PAHMEC01 | Mecánica | 17 | 8.2 | 4.3 | 1.4 | 13.9 | 81.8 | No | 3 | 3 | 500049 | PM01 | CM - Válvula control alimenta pulpa HV1501K | 1001214 | 90.2 | 90
2026-W15 | 2026-04-15 | M02 | PAHMEC01 | Eléctrica | 37 | 17.8 | 7.8 | 1.3 | 26.9 | 72.7 | No | 5 | 3 | 500136 | PM02 | PM - Calefactor eléctrico edificio | 1004988 | 76.2 | 90
2026-W15 | 2026-04-15 | M02 | PAHMEC01 | Instrumentación | 22 | 10.7 | 4.8 | 0.5 | 16 | 72.7 | No | 7 | 3 | 500097 | PM02 | PM - Gabinete RIO |  | 26 | 90
2026-W15 | 2026-04-15 | M02 | PAHELE01 | Mecánica | 29 | 4.8 | 5.9 | 2.7 | 13.4 | 46.2 | No | 6 | 2 | 500085 | PM02 | PM - Gabinete servidor core switch 1 y commun |  | 42.4 | 90
2026-W15 | 2026-04-15 | M02 | PAHELE01 | Eléctrica | 32 | 5.8 | 7.4 | 1.4 | 14.6 | 45.6 | No | 6 | 4 | 500192 | PM01 | CM - Calefactor eléctrico edificio | 1005483 | 143.6 | 90
2026-W15 | 2026-04-15 | M02 | PAHELE01 | Instrumentación | 19 | 5 | 5.4 | 1.4 | 11.8 | 62.1 | No | 4 | 3 | 500054 | PM01 | CM - Intercambiador calor calentamiento |  | 77.1 | 90
2026-W15 | 2026-04-15 | M02 | PAHINS01 | Mecánica | 21 | 8.2 | 5.3 | 1.6 | 15.1 | 71.9 | No | 4 | 2 | 500009 | PM02 | PM - Estanque diesel dia regeneración carbón |  | 151.2 | 90
2026-W15 | 2026-04-15 | M02 | PAHINS01 | Eléctrica | 23 | 7.7 | 2.2 | 1.4 | 11.3 | 49.1 | No | 7 | 4 | 500049 | PM01 | CM - Válvula control alimenta pulpa HV1501K | 1000856 | 63.2 | 90
2026-W15 | 2026-04-15 | M02 | PAHINS01 | Instrumentación | 36 | 17.5 | 7.3 | 2.7 | 27.5 | 76.4 | No | 5 | 4 | 500021 | PM02 | PM - Tornillo alimentador sulfato de cobre |  | 22.2 | 90
2026-W15 | 2026-04-15 | P01 | PASMEC01 | Mecánica | 31 | 14.5 | 8.5 | 2 | 25 | 80.6 | No | 7 | 4 | 500167 | PM02 | PM - Sensor temperatura TE0802 |  | 21 | 90
2026-W15 | 2026-04-15 | P01 | PASMEC01 | Eléctrica | 32 | 15.7 | 6.7 | 3 | 25.4 | 79.4 | No | 3 | 4 | 500039 | PM02 | PM - Chute carbónHO0068 |  | 57.5 | 90
2026-W15 | 2026-04-15 | P01 | PASMEC01 | Instrumentación | 20 | 5.7 | 4.3 | 0.2 | 10.2 | 51 | No | 6 | 1 | 500011 | PM02 | PM - Válvula control agua sello HV2723 | 1005003 | 45.3 | 90
2026-W15 | 2026-04-15 | P01 | PASELE01 | Mecánica | 18 | 5.5 | 4.1 | 0.8 | 10.4 | 57.8 | No | 7 | 4 | 500077 | PM02 | PM - Válvula control entrada solucion barren FV2314 |  | 86.2 | 90
2026-W15 | 2026-04-15 | P01 | PASELE01 | Eléctrica | 22 | 9.3 | 6.5 | 1.8 | 17.6 | 80 | No | 5 | 3 | 500045 | PM02 | PM - Transmisor presión agua potable PIT7025 |  | 182.7 | 90
2026-W15 | 2026-04-15 | P01 | PASELE01 | Instrumentación | 20 | 7.1 | 2.5 | 0.7 | 10.3 | 51.5 | No | 7 | 4 | 500108 | PM02 | PM - Motor eléctrico HY0036M1 |  | 167.8 | 90
2026-W15 | 2026-04-15 | P01 | PASINS01 | Mecánica | 34 | 8.1 | 4.1 | 0.1 | 12.3 | 36.2 | No | 6 | 2 | 500072 | PM02 | PM - Válvula control flujo entrada agua rechazo FV3576 |  | 61.4 | 90
2026-W15 | 2026-04-15 | P01 | PASINS01 | Eléctrica | 30 | 9 | 3.7 | 2.6 | 15.3 | 51 | No | 5 | 2 | 500109 | PM02 | PM - Variador frecuencia 3620PU0239M1VF |  | 182 | 90
2026-W15 | 2026-04-15 | P01 | PASINS01 | Instrumentación | 38 | 18 | 9.6 | 2.4 | 30 | 78.9 | No | 7 | 4 | 500161 | PM02 | PM - Unidad aire acondicionado |  | 196.9 | 90
2026-W15 | 2026-04-15 | P01 | PAHMEC01 | Mecánica | 38 | 11.8 | 8 | 2.2 | 22 | 57.9 | No | 2 | 2 | 500103 | PM02 | PM - Tablero SCI |  | 125.9 | 90
2026-W15 | 2026-04-15 | P01 | PAHMEC01 | Eléctrica | 30 | 11.9 | 7.4 | 1.2 | 20.5 | 68.3 | No | 7 | 2 | 500008 | PM02 | PM - Bomba precipitado |  | 131.2 | 90
2026-W15 | 2026-04-15 | P01 | PAHMEC01 | Instrumentación | 35 | 14.2 | 3.9 | 0.8 | 18.9 | 54 | No | 5 | 4 | 500174 | PM02 | PM - Bomba precipitado | 1003053 | 87 | 90
2026-W15 | 2026-04-15 | P01 | PAHELE01 | Mecánica | 24 | 11.8 | 7 | 1 | 19.8 | 82.5 | No | 2 | 1 | 500175 | PM01 | CM - Válvula control aceite XV0279 | 1005807 | 63.4 | 90
2026-W15 | 2026-04-15 | P01 | PAHELE01 | Eléctrica | 32 | 10.4 | 6.6 | 1.6 | 18.6 | 58.1 | No | 2 | 2 | 500084 | PM02 | PM - Motor eléctrico HY0001M1 |  | 146.5 | 90
2026-W15 | 2026-04-15 | P01 | PAHELE01 | Instrumentación | 37 | 8.9 | 6.9 | 2.5 | 18.3 | 49.5 | No | 3 | 1 | 500068 | PM02 | PM - Tecle eléctrico tolva carbon |  | 103.2 | 90
2026-W15 | 2026-04-15 | P01 | PAHINS01 | Mecánica | 28 | 4.4 | 6.5 | 1.4 | 12.3 | 43.9 | No | 7 | 2 | 500127 | PM01 | CM - Válvula control succión agua filtrado HV4810 | 1006629 | 50.9 | 90
2026-W15 | 2026-04-15 | P01 | PAHINS01 | Eléctrica | 33 | 13.3 | 9.2 | 3.2 | 25.7 | 77.9 | No | 5 | 3 | 500147 | PM02 | PM - Baliza YL3612 |  | 198.3 | 90
2026-W15 | 2026-04-15 | P01 | PAHINS01 | Instrumentación | 31 | 14.2 | 7.2 | 0.2 | 21.6 | 69.7 | No | 6 | 2 | 500168 | PM02 | PM - Gabinete RIO |  | 108.7 | 90
2026-W15 | 2026-04-15 | P02 | PASMEC01 | Mecánica | 29 | 4.2 | 6.3 | 1.3 | 11.8 | 40.7 | No | 3 | 4 | 500076 | PM02 | PM - Cajón (Futuro) | 1002703 | 39.4 | 90
2026-W15 | 2026-04-15 | P02 | PASMEC01 | Eléctrica | 38 | 10.9 | 2.4 | 0.1 | 13.4 | 35.3 | No | 7 | 4 | 500041 | PM02 | PM - Tecle bomba sumergible lixiviación |  | 136.8 | 90
2026-W15 | 2026-04-15 | P02 | PASMEC01 | Instrumentación | 39 | 5 | 5 | 1.1 | 11.1 | 28.5 | No | 6 | 4 | 500191 | PM01 | CM - Calefactor eléctrico estanque HE0112 | 1000202 | 86.6 | 90
2026-W15 | 2026-04-15 | P02 | PASELE01 | Mecánica | 35 | 14.5 | 8.7 | 1.8 | 25 | 71.4 | No | 2 | 4 | 500051 | PM01 | CM - Tablero distribución UPS | 1005386 | 90.4 | 90
2026-W15 | 2026-04-15 | P02 | PASELE01 | Eléctrica | 33 | 6.2 | 5.8 | 1.6 | 13.6 | 41.2 | No | 5 | 1 | 500142 | PM02 | PM - Calefactor eléctrico estanque HE0113 |  | 66.4 | 90
2026-W15 | 2026-04-15 | P02 | PASELE01 | Instrumentación | 37 | 7.4 | 10.2 | 3.1 | 20.7 | 55.9 | No | 5 | 1 | 500118 | PM01 | CM - Gabinete RIO | 1005660 | 130.9 | 90
2026-W15 | 2026-04-15 | P02 | PASINS01 | Mecánica | 27 | 7.9 | 5.2 | 0.1 | 13.2 | 48.9 | No | 2 | 4 | 500003 | PM02 | PM - Tablero de comunicación |  | 92.8 | 90
2026-W15 | 2026-04-15 | P02 | PASINS01 | Eléctrica | 17 | 6.2 | 3.4 | 0.9 | 10.5 | 61.8 | No | 4 | 1 | 500155 | PM02 | PM - Válvula control salida precapa HV3102 |  | 112.4 | 90
2026-W15 | 2026-04-15 | P02 | PASINS01 | Instrumentación | 21 | 6.8 | 5.7 | 1.1 | 13.6 | 64.8 | No | 3 | 3 | 500093 | PM02 | PM - Sensor temperatura horno TE3533 | 1006032 | 132.8 | 90
2026-W15 | 2026-04-15 | P02 | PAHMEC01 | Mecánica | 23 | 7.3 | 4 | 1.2 | 12.5 | 54.3 | No | 2 | 3 | 500094 | PM02 | PM - Switch baja presión descarga fluido térmico PSL3498 | 1005201 | 180.4 | 90
2026-W15 | 2026-04-15 | P02 | PAHMEC01 | Eléctrica | 22 | 7.5 | 5.9 | 1.9 | 15.3 | 69.5 | No | 2 | 1 | 500169 | PM02 | PM - Celosía XM0114 |  | 53.8 | 90
2026-W15 | 2026-04-15 | P02 | PAHMEC01 | Instrumentación | 36 | 8.2 | 2.2 | 3.2 | 13.6 | 37.8 | No | 6 | 3 | 500163 | PM02 | PM - Válvula control salida precapa HV3102 |  | 153.9 | 90
2026-W15 | 2026-04-15 | P02 | PAHELE01 | Mecánica | 36 | 14.7 | 3.8 | 0.8 | 19.3 | 53.6 | No | 4 | 3 | 500055 | PM01 | CM - Baliza YL3612 | 1007130 | 51 | 90
2026-W15 | 2026-04-15 | P02 | PAHELE01 | Eléctrica | 35 | 15.5 | 5.6 | 3.4 | 24.5 | 70 | No | 4 | 4 | 500101 | PM02 | PM - Subestación unitaria | 1004145 | 50.1 | 90
2026-W15 | 2026-04-15 | P02 | PAHELE01 | Instrumentación | 39 | 11.4 | 6.9 | 3.3 | 21.6 | 55.4 | No | 3 | 2 | 500127 | PM01 | CM - Válvula control succión agua filtrado HV4810 | 1020187 | 183.1 | 90
2026-W15 | 2026-04-15 | P02 | PAHINS01 | Mecánica | 38 | 14.5 | 6.7 | 0.6 | 21.8 | 57.4 | No | 6 | 2 | 500152 | PM02 | PM - Válvula control entrada pulpa HV1706 |  | 72.5 | 90
2026-W15 | 2026-04-15 | P02 | PAHINS01 | Eléctrica | 25 | 10.2 | 7.3 | 0.7 | 18.2 | 72.8 | No | 7 | 1 | 500028 | PM02 | PM - Válvula control succión agua fresca HV7808 |  | 118.2 | 90
2026-W15 | 2026-04-15 | P02 | PAHINS01 | Instrumentación | 24 | 9.4 | 5.2 | 1 | 15.6 | 65 | No | 5 | 4 | 500107 | PM02 | PM - Gabinete manguera y equipo contraincendios HH0105 |  | 88.9 | 90
2026-W15 | 2026-04-16 | M01 | PASMEC01 | Mecánica | 23 | 10.5 | 4.3 | 1.8 | 16.6 | 72.2 | No | 6 | 4 | 500099 | PM02 | PM - Indicador presión agua PI0251 | 1002121 | 159.2 | 90
2026-W15 | 2026-04-16 | M01 | PASMEC01 | Eléctrica | 33 | 9.2 | 2.1 | 1.2 | 12.5 | 37.9 | No | 3 | 1 | 500181 | PM01 | CM - Bomba diafragma grasa PU0001 |  | 111.1 | 90
2026-W15 | 2026-04-16 | M01 | PASMEC01 | Instrumentación | 26 | 6.9 | 3.5 | 2.5 | 12.9 | 49.6 | No | 5 | 2 | 500030 | PM02 | PM - Indicador nivel solución LI5563 |  | 161.7 | 90
2026-W15 | 2026-04-16 | M01 | PASELE01 | Mecánica | 28 | 12.4 | 8 | 0.9 | 21.3 | 76.1 | No | 6 | 4 | 500098 | PM02 | PM - Unidad presurización |  | 92.5 | 90
2026-W15 | 2026-04-16 | M01 | PASELE01 | Eléctrica | 24 | 4.1 | 5.1 | 1.2 | 10.4 | 43.3 | No | 4 | 3 | 500156 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 35.1 | 90
2026-W15 | 2026-04-16 | M01 | PASELE01 | Instrumentación | 19 | 5.7 | 3.9 | 1.4 | 11 | 57.9 | No | 4 | 2 | 500041 | PM02 | PM - Tecle bomba sumergible lixiviación |  | 35.9 | 90
2026-W15 | 2026-04-16 | M01 | PASINS01 | Mecánica | 27 | 8.5 | 4.4 | 0.8 | 13.7 | 50.7 | No | 7 | 2 | 500104 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 89.2 | 90
2026-W15 | 2026-04-16 | M01 | PASINS01 | Eléctrica | 25 | 10.6 | 6 | 1.2 | 17.8 | 71.2 | No | 5 | 2 | 500160 | PM02 | PM - Gabinete control Chancador Primario |  | 125.2 | 90
2026-W15 | 2026-04-16 | M01 | PASINS01 | Instrumentación | 32 | 14 | 4.7 | 1.4 | 20.1 | 62.8 | No | 3 | 2 | 500057 | PM01 | CM - Bomba rotativa aceite PU0510 | 1005500 | 87.5 | 90
2026-W15 | 2026-04-16 | M01 | PAHMEC01 | Mecánica | 32 | 13 | 7.1 | 3.2 | 23.3 | 72.8 | No | 6 | 2 | 500161 | PM02 | PM - Unidad aire acondicionado |  | 37.8 | 90
2026-W15 | 2026-04-16 | M01 | PAHMEC01 | Eléctrica | 29 | 5.5 | 5.5 | 0 | 11 | 37.9 | No | 6 | 3 | 500034 | PM02 | PM - Puerta enrollable Molienda | 1002981 | 141.9 | 90
2026-W15 | 2026-04-16 | M01 | PAHMEC01 | Instrumentación | 17 | 7.7 | 4.4 | 0.9 | 13 | 76.5 | No | 5 | 2 | 500007 | PM02 | PM - Transmisor vibración VT0020A | 1001592 | 65.2 | 90
2026-W15 | 2026-04-16 | M01 | PAHELE01 | Mecánica | 30 | 14 | 7.7 | 0.4 | 22.1 | 73.7 | No | 7 | 2 | 500065 | PM02 | PM - Muestreador alimentación filtros |  | 66.5 | 90
2026-W15 | 2026-04-16 | M01 | PAHELE01 | Eléctrica | 29 | 4 | 2.3 | 0 | 6.3 | 21.7 | No | 6 | 2 | 500148 | PM02 | PM - Válvula control descarga sol rica HV2810 |  | 95.1 | 90
2026-W15 | 2026-04-16 | M01 | PAHELE01 | Instrumentación | 33 | 7.5 | 9.5 | 0.2 | 17.2 | 52.1 | No | 4 | 4 | 500188 | PM01 | CM - Switch posición ZS1716 | 1001443 | 106 | 90
2026-W15 | 2026-04-16 | M01 | PAHINS01 | Mecánica | 27 | 4.8 | 6.8 | 1.1 | 12.7 | 47 | No | 6 | 1 | 500171 | PM02 | PM - Switch bajo nivel aceite LSL0253 |  | 65.7 | 90
2026-W15 | 2026-04-16 | M01 | PAHINS01 | Eléctrica | 31 | 4.3 | 3.5 | 0.8 | 8.6 | 27.7 | No | 3 | 1 | 500126 | PM01 | CM - Válvula control salida carbon descargado HV3394 | 1002929 | 61.9 | 90
2026-W15 | 2026-04-16 | M01 | PAHINS01 | Instrumentación | 30 | 10.1 | 4 | 1.8 | 15.9 | 53 | No | 6 | 4 | 500038 | PM02 | PM - Switch bajo flujo aire FSL1357A |  | 80.1 | 90
2026-W15 | 2026-04-16 | M02 | PASMEC01 | Mecánica | 34 | 6.2 | 8.4 | 0.9 | 15.5 | 45.6 | No | 7 | 4 | 500136 | PM02 | PM - Calefactor eléctrico edificio |  | 83.1 | 90
2026-W15 | 2026-04-16 | M02 | PASMEC01 | Eléctrica | 21 | 8.8 | 6.2 | 1 | 16 | 76.2 | No | 5 | 4 | 500116 | PM01 | CM - Transmisor nivel hidrox sodio LIT3467 | 1004929 | 195.5 | 90
2026-W15 | 2026-04-16 | M02 | PASMEC01 | Instrumentación | 31 | 9.6 | 8.8 | 1.6 | 20 | 64.5 | No | 3 | 4 | 500031 | PM02 | PM - Celosía XM0114 |  | 124.1 | 90
2026-W15 | 2026-04-16 | M02 | PASELE01 | Mecánica | 38 | 8.3 | 9.2 | 1.8 | 19.3 | 50.8 | No | 2 | 3 | 500109 | PM02 | PM - Variador frecuencia 3620PU0239M1VF |  | 132.1 | 90
2026-W15 | 2026-04-16 | M02 | PASELE01 | Eléctrica | 37 | 9.5 | 2.9 | 2.3 | 14.7 | 39.7 | No | 7 | 2 | 500158 | PM02 | PM - Válvula control flujo sol barren FV5601 | 1000443 | 179.8 | 90
2026-W15 | 2026-04-16 | M02 | PASELE01 | Instrumentación | 22 | 9.4 | 3.8 | 0.7 | 13.9 | 63.2 | No | 3 | 1 | 500067 | PM02 | PM - Indicador presión aceite hidráulico PI4895E |  | 82.3 | 90
2026-W15 | 2026-04-16 | M02 | PASINS01 | Mecánica | 19 | 7.3 | 4.2 | 0.7 | 12.2 | 64.2 | No | 2 | 2 | 500004 | PM02 | PM - Válvula control aceite XV0256D | 1006134 | 110.6 | 90
2026-W15 | 2026-04-16 | M02 | PASINS01 | Eléctrica | 30 | 5.4 | 6.1 | 1.9 | 13.4 | 44.7 | No | 3 | 1 | 500107 | PM02 | PM - Gabinete manguera y equipo contraincendios HH0105 |  | 63.7 | 90
2026-W15 | 2026-04-16 | M02 | PASINS01 | Instrumentación | 34 | 14.1 | 8.5 | 2.4 | 25 | 73.5 | No | 7 | 1 | 500051 | PM01 | CM - Tablero distribución UPS | 1005947 | 82.4 | 90
2026-W15 | 2026-04-16 | M02 | PAHMEC01 | Mecánica | 30 | 6.1 | 2.9 | 2.9 | 11.9 | 39.7 | No | 5 | 4 | 500125 | PM01 | CM - Transmisor presión aceite PIT4824 | 1004638 | 180.8 | 90
2026-W15 | 2026-04-16 | M02 | PAHMEC01 | Eléctrica | 20 | 7 | 5.2 | 0.9 | 13.1 | 65.5 | No | 5 | 4 | 500170 | PM02 | PM - Switch posición ZS0038A |  | 172.6 | 90
2026-W15 | 2026-04-16 | M02 | PAHMEC01 | Instrumentación | 34 | 10.6 | 7.3 | 1.7 | 19.6 | 57.6 | No | 2 | 2 | 500125 | PM01 | CM - Transmisor presión aceite PIT4824 | 1000124 | 70.2 | 90
2026-W15 | 2026-04-16 | M02 | PAHELE01 | Mecánica | 39 | 10.2 | 8.3 | 1.5 | 20 | 51.3 | No | 3 | 3 | 500101 | PM02 | PM - Subestación unitaria |  | 122.2 | 90
2026-W15 | 2026-04-16 | M02 | PAHELE01 | Eléctrica | 26 | 9.5 | 2.9 | 2.1 | 14.5 | 55.8 | No | 5 | 1 | 500134 | PM02 | PM - Intercambiador calor por aire CQ0007 |  | 62.7 | 90
2026-W15 | 2026-04-16 | M02 | PAHELE01 | Instrumentación | 35 | 8 | 3.6 | 1.9 | 13.5 | 38.6 | No | 5 | 2 | 500113 | PM01 | CM - Puerta enrollable Molienda | 1004155 | 48.3 | 90
2026-W15 | 2026-04-16 | M02 | PAHINS01 | Mecánica | 19 | 7.1 | 2.7 | 0.9 | 10.7 | 56.3 | No | 5 | 2 | 500175 | PM01 | CM - Válvula control aceite XV0279 | 1001937 | 78.9 | 90
2026-W15 | 2026-04-16 | M02 | PAHINS01 | Eléctrica | 24 | 6.3 | 3.8 | 1.8 | 11.9 | 49.6 | No | 3 | 4 | 500109 | PM02 | PM - Variador frecuencia 3620PU0239M1VF |  | 170.8 | 90
2026-W15 | 2026-04-16 | M02 | PAHINS01 | Instrumentación | 19 | 8.9 | 5.7 | 1.3 | 15.9 | 83.7 | No | 6 | 2 | 500022 | PM02 | PM - Unidad re-potabilizadora agua |  | 138.8 | 90
2026-W15 | 2026-04-16 | P01 | PASMEC01 | Mecánica | 39 | 8.5 | 6.9 | 1.8 | 17.2 | 44.1 | No | 6 | 4 | 500165 | PM02 | PM - Motor eléctrico HY0036M1 |  | 187.6 | 90
2026-W15 | 2026-04-16 | P01 | PASMEC01 | Eléctrica | 21 | 10.3 | 3.1 | 1.5 | 14.9 | 71 | No | 4 | 1 | 500141 | PM02 | PM - Lava ojos emergencia |  | 141.9 | 90
2026-W15 | 2026-04-16 | P01 | PASMEC01 | Instrumentación | 24 | 4.4 | 2 | 1.4 | 7.8 | 32.5 | No | 4 | 1 | 500086 | PM02 | PM - Sensor nivel refrigerante LE0177 |  | 178.5 | 90
2026-W15 | 2026-04-16 | P01 | PASELE01 | Mecánica | 25 | 10.9 | 4.5 | 0.6 | 16 | 64 | No | 6 | 2 | 500087 | PM02 | PM - Línea agua sell 3700-5476-AA1A-3"-WGS-ET |  | 23.6 | 90
2026-W15 | 2026-04-16 | P01 | PASELE01 | Eléctrica | 24 | 7.4 | 4.4 | 0 | 11.8 | 49.2 | No | 7 | 3 | 500042 | PM02 | PM - Válvula control salida precapa HV3102 |  | 86.4 | 90
2026-W15 | 2026-04-16 | P01 | PASELE01 | Instrumentación | 30 | 6 | 2.7 | 0.2 | 8.9 | 29.7 | No | 7 | 2 | 500109 | PM02 | PM - Variador frecuencia 3620PU0239M1VF | 1000341 | 132.2 | 90
2026-W15 | 2026-04-16 | P01 | PASINS01 | Mecánica | 29 | 12.5 | 2.9 | 2.1 | 17.5 | 60.3 | No | 4 | 2 | 500174 | PM02 | PM - Bomba precipitado |  | 73 | 90
2026-W15 | 2026-04-16 | P01 | PASINS01 | Eléctrica | 34 | 10.3 | 4.9 | 0.9 | 16.1 | 47.4 | No | 4 | 3 | 500021 | PM02 | PM - Tornillo alimentador sulfato de cobre |  | 158.5 | 90
2026-W15 | 2026-04-16 | P01 | PASINS01 | Instrumentación | 26 | 4.7 | 5.5 | 0.3 | 10.5 | 40.4 | No | 3 | 4 | 500103 | PM02 | PM - Tablero SCI |  | 133 | 90
2026-W15 | 2026-04-16 | P01 | PAHMEC01 | Mecánica | 33 | 7.1 | 2.1 | 0.8 | 10 | 30.3 | No | 6 | 3 | 500129 | PM01 | CM - Gabinete control Chancador Primario | 1001304 | 130.2 | 90
2026-W15 | 2026-04-16 | P01 | PAHMEC01 | Eléctrica | 30 | 9.6 | 7.2 | 1.4 | 18.2 | 60.7 | No | 4 | 2 | 500125 | PM01 | CM - Transmisor presión aceite PIT4824 | 1001135 | 26.7 | 90
2026-W15 | 2026-04-16 | P01 | PAHMEC01 | Instrumentación | 34 | 4.9 | 6.4 | 0.2 | 11.5 | 33.8 | No | 2 | 4 | 500098 | PM02 | PM - Unidad presurización |  | 149.5 | 90
2026-W15 | 2026-04-16 | P01 | PAHELE01 | Mecánica | 29 | 9.4 | 6.8 | 0.8 | 17 | 58.6 | No | 2 | 2 | 500179 | PM01 | CM - Transmisor nivel atricción carbón LIT3627 |  | 50.1 | 90
2026-W15 | 2026-04-16 | P01 | PAHELE01 | Eléctrica | 28 | 8.4 | 6.1 | 1.4 | 15.9 | 56.8 | No | 2 | 4 | 500099 | PM02 | PM - Indicador presión agua PI0251 |  | 175 | 90
2026-W15 | 2026-04-16 | P01 | PAHELE01 | Instrumentación | 28 | 11.1 | 5.4 | 1.9 | 18.4 | 65.7 | No | 7 | 4 | 500104 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 97.8 | 90
2026-W15 | 2026-04-16 | P01 | PAHINS01 | Mecánica | 33 | 14.8 | 5.5 | 2.4 | 22.7 | 68.8 | No | 7 | 1 | 500152 | PM02 | PM - Válvula control entrada pulpa HV1706 |  | 27.8 | 90
2026-W15 | 2026-04-16 | P01 | PAHINS01 | Eléctrica | 21 | 9.5 | 3.7 | 0.6 | 13.8 | 65.7 | No | 7 | 4 | 500165 | PM02 | PM - Motor eléctrico HY0036M1 |  | 80.4 | 90
2026-W15 | 2026-04-16 | P01 | PAHINS01 | Instrumentación | 24 | 4.7 | 4.9 | 1.1 | 10.7 | 44.6 | No | 7 | 4 | 500008 | PM02 | PM - Bomba precipitado | 1000657 | 130.2 | 90
2026-W15 | 2026-04-16 | P02 | PASMEC01 | Mecánica | 35 | 6.3 | 4.6 | 1.1 | 12 | 34.3 | No | 6 | 3 | 500101 | PM02 | PM - Subestación unitaria |  | 109 | 90
2026-W15 | 2026-04-16 | P02 | PASMEC01 | Eléctrica | 34 | 6.1 | 5.6 | 1.4 | 13.1 | 38.5 | No | 7 | 3 | 500147 | PM02 | PM - Baliza YL3612 | 1003163 | 125 | 90
2026-W15 | 2026-04-16 | P02 | PASMEC01 | Instrumentación | 22 | 4.5 | 3.7 | 1.6 | 9.8 | 44.5 | No | 2 | 4 | 500117 | PM01 | CM - Válvula control agua filtrada HV4568B | 1001846 | 122.6 | 90
2026-W15 | 2026-04-16 | P02 | PASELE01 | Mecánica | 33 | 5.5 | 9.6 | 0.3 | 15.4 | 46.7 | No | 7 | 2 | 500173 | PM02 | PM - Bomba agua sello |  | 28.4 | 90
2026-W15 | 2026-04-16 | P02 | PASELE01 | Eléctrica | 24 | 8.2 | 4.8 | 0.9 | 13.9 | 57.9 | No | 7 | 4 | 500149 | PM02 | PM - Indicador presión aceite PI1315 |  | 65.3 | 90
2026-W15 | 2026-04-16 | P02 | PASELE01 | Instrumentación | 29 | 8.8 | 3.3 | 0.7 | 12.8 | 44.1 | No | 7 | 3 | 500005 | PM02 | PM - Válvula control succión agua fresca HV7808 |  | 195.8 | 90
2026-W15 | 2026-04-16 | P02 | PASINS01 | Mecánica | 29 | 13 | 3.9 | 0.5 | 17.4 | 60 | No | 5 | 3 | 500020 | PM02 | PM - Cajón (Futuro) |  | 181 | 90
2026-W15 | 2026-04-16 | P02 | PASINS01 | Eléctrica | 17 | 6.5 | 3.6 | 0.5 | 10.6 | 62.4 | No | 2 | 1 | 500012 | PM02 | PM - Gabinete PLC horno fundición 1 |  | 181.2 | 90
2026-W15 | 2026-04-16 | P02 | PASINS01 | Instrumentación | 30 | 5.5 | 7.4 | 1.9 | 14.8 | 49.3 | No | 4 | 2 | 500115 | PM01 | CM - Bomba vacío retorta | 1002668 | 65.7 | 90
2026-W15 | 2026-04-16 | P02 | PAHMEC01 | Mecánica | 21 | 4.1 | 3.4 | 0.4 | 7.9 | 37.6 | No | 5 | 2 | 500052 | PM01 | CM - Tablero distribución instrumentación |  | 30.2 | 90
2026-W15 | 2026-04-16 | P02 | PAHMEC01 | Eléctrica | 23 | 5.5 | 3 | 1.5 | 10 | 43.5 | No | 6 | 2 | 500183 | PM01 | CM - Estanque separador TK0054 | 1020010 | 92.7 | 90
2026-W15 | 2026-04-16 | P02 | PAHMEC01 | Instrumentación | 17 | 5.9 | 5 | 0 | 10.9 | 64.1 | No | 7 | 4 | 500075 | PM02 | PM - Switch posición giro rastras ZS4377D |  | 139.9 | 90
2026-W15 | 2026-04-16 | P02 | PAHELE01 | Mecánica | 30 | 12.3 | 3 | 1 | 16.3 | 54.3 | No | 4 | 4 | 500151 | PM02 | PM - Válvula control flujo entrada agua rechazo FV3576 |  | 112 | 90
2026-W15 | 2026-04-16 | P02 | PAHELE01 | Eléctrica | 39 | 7.3 | 10.8 | 3.6 | 21.7 | 55.6 | No | 4 | 4 | 500192 | PM01 | CM - Calefactor eléctrico edificio | 1003826 | 21.2 | 90
2026-W15 | 2026-04-16 | P02 | PAHELE01 | Instrumentación | 23 | 8.3 | 2.1 | 0.9 | 11.3 | 49.1 | No | 2 | 4 | 500179 | PM01 | CM - Transmisor nivel atricción carbón LIT3627 |  | 148.6 | 90
2026-W15 | 2026-04-16 | P02 | PAHINS01 | Mecánica | 37 | 7 | 6.8 | 2.1 | 15.9 | 43 | No | 6 | 4 | 500082 | PM02 | PM - Válvula control agua filtrada HV4568B |  | 86.3 | 90
2026-W15 | 2026-04-16 | P02 | PAHINS01 | Eléctrica | 35 | 17 | 5.8 | 2.6 | 25.4 | 72.6 | No | 2 | 4 | 500175 | PM01 | CM - Válvula control aceite XV0279 |  | 67.8 | 90
2026-W15 | 2026-04-16 | P02 | PAHINS01 | Instrumentación | 16 | 5.7 | 3.4 | 0.4 | 9.5 | 59.4 | No | 3 | 4 | 500004 | PM02 | PM - Válvula control aceite XV0256D |  | 72.3 | 90
2026-W15 | 2026-04-17 | M01 | PASMEC01 | Mecánica | 37 | 16.9 | 9.7 | 3.7 | 30.3 | 81.9 | No | 6 | 3 | 500163 | PM02 | PM - Válvula control salida precapa HV3102 |  | 188.6 | 90
2026-W15 | 2026-04-17 | M01 | PASMEC01 | Eléctrica | 25 | 11.2 | 5.1 | 1 | 17.3 | 69.2 | No | 5 | 4 | 500073 | PM02 | PM - Válvula control sol barren a estanque HV3266 | 1007085 | 97.8 | 90
2026-W15 | 2026-04-17 | M01 | PASMEC01 | Instrumentación | 25 | 6.3 | 6 | 2.1 | 14.4 | 57.6 | No | 3 | 2 | 500081 | PM02 | PM - Transmisor nivel lechada cal LIT5271 |  | 151.4 | 90
2026-W15 | 2026-04-17 | M01 | PASELE01 | Mecánica | 29 | 8.7 | 5.9 | 0.4 | 15 | 51.7 | No | 3 | 4 | 500096 | PM02 | PM - Válvula control descarga agua fresca HV7819 |  | 32.6 | 90
2026-W15 | 2026-04-17 | M01 | PASELE01 | Eléctrica | 37 | 5.4 | 10.3 | 0.8 | 16.5 | 44.6 | No | 6 | 1 | 500063 | PM01 | CM - Válvula control entrada solucion barren FV2314 |  | 52.7 | 90
2026-W15 | 2026-04-17 | M01 | PASELE01 | Instrumentación | 26 | 10.7 | 4.5 | 1.8 | 17 | 65.4 | No | 5 | 3 | 500187 | PM01 | CM - Pesómetro SC0001 | 1000943 | 191.1 | 90
2026-W15 | 2026-04-17 | M01 | PASINS01 | Mecánica | 21 | 7.1 | 6.1 | 0.5 | 13.7 | 65.2 | No | 7 | 1 | 500189 | PM01 | CM - Switch gear SAG 630 A, 6.9 Kv, 31.5 kA |  | 99.1 | 90
2026-W15 | 2026-04-17 | M01 | PASINS01 | Eléctrica | 37 | 9.6 | 4.1 | 3.1 | 16.8 | 45.4 | No | 5 | 2 | 500114 | PM01 | CM - Transmisor vibración VT0020A | 1003421 | 27 | 90
2026-W15 | 2026-04-17 | M01 | PASINS01 | Instrumentación | 17 | 8.3 | 2.6 | 1.5 | 12.4 | 72.9 | No | 6 | 4 | 500171 | PM02 | PM - Switch bajo nivel aceite LSL0253 |  | 194.2 | 90
2026-W15 | 2026-04-17 | M01 | PAHMEC01 | Mecánica | 38 | 14.9 | 5.5 | 0.7 | 21.1 | 55.5 | No | 3 | 3 | 500138 | PM02 | PM - Motor eléctrico HY0036M1 | 1004222 | 49.8 | 90
2026-W15 | 2026-04-17 | M01 | PAHMEC01 | Eléctrica | 22 | 4.5 | 3.7 | 1.8 | 10 | 45.5 | No | 7 | 2 | 500021 | PM02 | PM - Tornillo alimentador sulfato de cobre |  | 151 | 90
2026-W15 | 2026-04-17 | M01 | PAHMEC01 | Instrumentación | 31 | 5.3 | 6.1 | 0.9 | 12.3 | 39.7 | No | 7 | 2 | 500169 | PM02 | PM - Celosía XM0114 |  | 157.2 | 90
2026-W15 | 2026-04-17 | M01 | PAHELE01 | Mecánica | 39 | 4.6 | 4.8 | 0.8 | 10.2 | 26.2 | No | 3 | 2 | 500184 | PM01 | CM - Válvula control descarga agua filtrado HV4812 | 1020211 | 79.2 | 90
2026-W15 | 2026-04-17 | M01 | PAHELE01 | Eléctrica | 25 | 8.3 | 6.9 | 1.7 | 16.9 | 67.6 | No | 3 | 1 | 500163 | PM02 | PM - Válvula control salida precapa HV3102 |  | 87 | 90
2026-W15 | 2026-04-17 | M01 | PAHELE01 | Instrumentación | 23 | 7.9 | 6.8 | 1.3 | 16 | 69.6 | No | 6 | 2 | 500008 | PM02 | PM - Bomba precipitado |  | 156.2 | 90
2026-W15 | 2026-04-17 | M01 | PAHINS01 | Mecánica | 26 | 11.2 | 7 | 1.3 | 19.5 | 75 | No | 4 | 4 | 500071 | PM02 | PM - Calefactor eléctrico estanque HE0112 | 1004675 | 60.5 | 90
2026-W15 | 2026-04-17 | M01 | PAHINS01 | Eléctrica | 20 | 6.4 | 4.4 | 0.1 | 10.9 | 54.5 | No | 6 | 4 | 500065 | PM02 | PM - Muestreador alimentación filtros |  | 124.3 | 90
2026-W15 | 2026-04-17 | M01 | PAHINS01 | Instrumentación | 27 | 11.9 | 3.1 | 1.4 | 16.4 | 60.7 | No | 7 | 2 | 500037 | PM02 | PM - Sirena YA1151 |  | 129.1 | 90
2026-W15 | 2026-04-17 | M02 | PASMEC01 | Mecánica | 25 | 10.2 | 3.6 | 1.9 | 15.7 | 62.8 | No | 3 | 1 | 500037 | PM02 | PM - Sirena YA1151 | 1004744 | 71 | 90
2026-W15 | 2026-04-17 | M02 | PASMEC01 | Eléctrica | 34 | 8.4 | 7.8 | 0.2 | 16.4 | 48.2 | No | 6 | 1 | 500133 | PM02 | PM - Calefactor eléctrico HE0135 |  | 146.9 | 90
2026-W15 | 2026-04-17 | M02 | PASMEC01 | Instrumentación | 28 | 6.5 | 3.7 | 1.8 | 12 | 42.9 | No | 6 | 1 | 500127 | PM01 | CM - Válvula control succión agua filtrado HV4810 |  | 190.7 | 90
2026-W15 | 2026-04-17 | M02 | PASELE01 | Mecánica | 17 | 6.7 | 3.5 | 1.2 | 11.4 | 67.1 | No | 6 | 3 | 500035 | PM02 | PM - Agitador estanque filtración |  | 56.4 | 90
2026-W15 | 2026-04-17 | M02 | PASELE01 | Eléctrica | 31 | 4.1 | 4.2 | 2.3 | 10.6 | 34.2 | No | 6 | 4 | 500104 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 56.4 | 90
2026-W15 | 2026-04-17 | M02 | PASELE01 | Instrumentación | 17 | 6.3 | 4.8 | 1.2 | 12.3 | 72.4 | No | 2 | 2 | 500034 | PM02 | PM - Puerta enrollable Molienda | 1020168 | 35.3 | 90
2026-W15 | 2026-04-17 | M02 | PASINS01 | Mecánica | 29 | 6.4 | 8 | 2.5 | 16.9 | 58.3 | No | 6 | 3 | 500158 | PM02 | PM - Válvula control flujo sol barren FV5601 | 1001099 | 98 | 90
2026-W15 | 2026-04-17 | M02 | PASINS01 | Eléctrica | 20 | 8.2 | 4.7 | 0.4 | 13.3 | 66.5 | No | 3 | 2 | 500099 | PM02 | PM - Indicador presión agua PI0251 |  | 65.4 | 90
2026-W15 | 2026-04-17 | M02 | PASINS01 | Instrumentación | 29 | 11.3 | 6.3 | 1.2 | 18.8 | 64.8 | No | 4 | 2 | 500142 | PM02 | PM - Calefactor eléctrico estanque HE0113 |  | 127.1 | 90
2026-W15 | 2026-04-17 | M02 | PAHMEC01 | Mecánica | 38 | 5.3 | 4.7 | 1.4 | 11.4 | 30 | No | 7 | 3 | 500173 | PM02 | PM - Bomba agua sello |  | 127.3 | 90
2026-W15 | 2026-04-17 | M02 | PAHMEC01 | Eléctrica | 20 | 5.9 | 3.4 | 0.5 | 9.8 | 49 | No | 6 | 2 | 500045 | PM02 | PM - Transmisor presión agua potable PIT7025 |  | 190.8 | 90
2026-W15 | 2026-04-17 | M02 | PAHMEC01 | Instrumentación | 18 | 4.8 | 4.5 | 1.3 | 10.6 | 58.9 | No | 3 | 2 | 500123 | PM01 | CM - Válvula control flujo sol barren FV5601 |  | 44.2 | 90
2026-W15 | 2026-04-17 | M02 | PAHELE01 | Mecánica | 34 | 16.4 | 3.1 | 2.4 | 21.9 | 64.4 | No | 7 | 1 | 500066 | PM02 | PM - Hidrante/ Grifos FH0137 | 1002423 | 24.6 | 90
2026-W15 | 2026-04-17 | M02 | PAHELE01 | Eléctrica | 28 | 12.5 | 5.4 | 0.6 | 18.5 | 66.1 | No | 6 | 3 | 500162 | PM02 | PM - Tecle bomba sumergible lixiviación |  | 85.4 | 90
2026-W15 | 2026-04-17 | M02 | PAHELE01 | Instrumentación | 36 | 11.7 | 9 | 0.2 | 20.9 | 58.1 | No | 7 | 2 | 500144 | PM02 | PM - Motor eléctrico PU0516M1 |  | 137.2 | 90
2026-W15 | 2026-04-17 | M02 | PAHINS01 | Mecánica | 35 | 4.5 | 5.4 | 2.8 | 12.7 | 36.3 | No | 2 | 3 | 500066 | PM02 | PM - Hidrante/ Grifos FH0137 | 1005133 | 119 | 90
2026-W15 | 2026-04-17 | M02 | PAHINS01 | Eléctrica | 37 | 16.4 | 7.3 | 3.3 | 27 | 73 | No | 3 | 3 | 500184 | PM01 | CM - Válvula control descarga agua filtrado HV4812 | 1002556 | 29.7 | 90
2026-W15 | 2026-04-17 | M02 | PAHINS01 | Instrumentación | 33 | 10.2 | 8.8 | 0.3 | 19.3 | 58.5 | No | 6 | 4 | 500034 | PM02 | PM - Puerta enrollable Molienda |  | 71.7 | 90
2026-W15 | 2026-04-17 | P01 | PASMEC01 | Mecánica | 20 | 8.3 | 2.5 | 1.6 | 12.4 | 62 | No | 7 | 2 | 500136 | PM02 | PM - Calefactor eléctrico edificio |  | 102.9 | 90
2026-W15 | 2026-04-17 | P01 | PASMEC01 | Eléctrica | 27 | 5 | 5.1 | 0.2 | 10.3 | 38.1 | No | 2 | 2 | 500120 | PM01 | CM - Transmisor presión salida sol barren PIT3241 | 1001051 | 27 | 90
2026-W15 | 2026-04-17 | P01 | PASMEC01 | Instrumentación | 28 | 10.5 | 7.4 | 1.3 | 19.2 | 68.6 | No | 3 | 4 | 500118 | PM01 | CM - Gabinete RIO | 1001589 | 199.9 | 90
2026-W15 | 2026-04-17 | P01 | PASELE01 | Mecánica | 22 | 6 | 6.2 | 0.7 | 12.9 | 58.6 | No | 4 | 1 | 500039 | PM02 | PM - Chute carbónHO0068 |  | 117.9 | 90
2026-W15 | 2026-04-17 | P01 | PASELE01 | Eléctrica | 21 | 10.3 | 2.4 | 0.9 | 13.6 | 64.8 | No | 4 | 4 | 500158 | PM02 | PM - Válvula control flujo sol barren FV5601 |  | 92.9 | 90
2026-W15 | 2026-04-17 | P01 | PASELE01 | Instrumentación | 35 | 10.9 | 7.9 | 0.2 | 19 | 54.3 | No | 5 | 1 | 500021 | PM02 | PM - Tornillo alimentador sulfato de cobre |  | 167.5 | 90
2026-W15 | 2026-04-17 | P01 | PASINS01 | Mecánica | 28 | 4.9 | 7.3 | 1 | 13.2 | 47.1 | No | 5 | 1 | 500019 | PM02 | PM - Transmisor nivel lechada cal LIT5314 |  | 74.5 | 90
2026-W15 | 2026-04-17 | P01 | PASINS01 | Eléctrica | 25 | 5.8 | 2.7 | 0.8 | 9.3 | 37.2 | No | 2 | 2 | 500031 | PM02 | PM - Celosía XM0114 |  | 162.2 | 90
2026-W15 | 2026-04-17 | P01 | PASINS01 | Instrumentación | 35 | 10.7 | 4.5 | 0.6 | 15.8 | 45.1 | No | 6 | 1 | 500023 | PM02 | PM - Válvula control entrada aire FV1804 |  | 47.7 | 90
2026-W15 | 2026-04-17 | P01 | PAHMEC01 | Mecánica | 38 | 4.1 | 8.1 | 0.8 | 13 | 34.2 | No | 7 | 2 | 500074 | PM02 | PM - Transmisor presión agua potable PIT7025 |  | 131.6 | 90
2026-W15 | 2026-04-17 | P01 | PAHMEC01 | Eléctrica | 27 | 5 | 5 | 1.6 | 11.6 | 43 | No | 7 | 3 | 500054 | PM01 | CM - Intercambiador calor calentamiento | 1000160 | 149 | 90
2026-W15 | 2026-04-17 | P01 | PAHMEC01 | Instrumentación | 33 | 4.1 | 5.8 | 1.4 | 11.3 | 34.2 | No | 3 | 3 | 500114 | PM01 | CM - Transmisor vibración VT0020A | 1006556 | 186.2 | 90
2026-W15 | 2026-04-17 | P01 | PAHELE01 | Mecánica | 16 | 6.3 | 4.4 | 1.4 | 12.1 | 75.6 | No | 4 | 4 | 500110 | PM02 | PM - Válvula control entrada pulpa HV1706 |  | 125.2 | 90
2026-W15 | 2026-04-17 | P01 | PAHELE01 | Eléctrica | 22 | 4.4 | 4.7 | 1.9 | 11 | 50 | No | 5 | 4 | 500152 | PM02 | PM - Válvula control entrada pulpa HV1706 |  | 20.5 | 90
2026-W15 | 2026-04-17 | P01 | PAHELE01 | Instrumentación | 36 | 13.3 | 4.7 | 1.2 | 19.2 | 53.3 | No | 2 | 2 | 500030 | PM02 | PM - Indicador nivel solución LI5563 |  | 142.4 | 90
2026-W15 | 2026-04-17 | P01 | PAHINS01 | Mecánica | 33 | 8.4 | 9.2 | 3.2 | 20.8 | 63 | No | 5 | 2 | 500059 | PM01 | CM - Mezclador floculante |  | 158.9 | 90
2026-W15 | 2026-04-17 | P01 | PAHINS01 | Eléctrica | 35 | 5.1 | 9.4 | 3 | 17.5 | 50 | No | 4 | 1 | 500012 | PM02 | PM - Gabinete PLC horno fundición 1 |  | 146.4 | 90
2026-W15 | 2026-04-17 | P01 | PAHINS01 | Instrumentación | 29 | 12.7 | 6.4 | 1.1 | 20.2 | 69.7 | No | 6 | 4 | 500034 | PM02 | PM - Puerta enrollable Molienda | 1004450 | 181.5 | 90
2026-W15 | 2026-04-17 | P02 | PASMEC01 | Mecánica | 26 | 12 | 3 | 0.4 | 15.4 | 59.2 | No | 7 | 2 | 500127 | PM01 | CM - Válvula control succión agua filtrado HV4810 | 1005836 | 138.3 | 90
2026-W15 | 2026-04-17 | P02 | PASMEC01 | Eléctrica | 25 | 5.2 | 4.1 | 1 | 10.3 | 41.2 | No | 2 | 4 | 500049 | PM01 | CM - Válvula control alimenta pulpa HV1501K | 1005087 | 186.1 | 90
2026-W15 | 2026-04-17 | P02 | PASMEC01 | Instrumentación | 39 | 17.9 | 10.6 | 1.2 | 29.7 | 76.2 | No | 7 | 2 | 500093 | PM02 | PM - Sensor temperatura horno TE3533 | 1003168 | 65.5 | 90
2026-W15 | 2026-04-17 | P02 | PASELE01 | Mecánica | 24 | 8.5 | 3.6 | 1 | 13.1 | 54.6 | No | 5 | 3 | 500038 | PM02 | PM - Switch bajo flujo aire FSL1357A |  | 27.7 | 90
2026-W15 | 2026-04-17 | P02 | PASELE01 | Eléctrica | 20 | 8.8 | 2.3 | 1.4 | 12.5 | 62.5 | No | 5 | 1 | 500088 | PM02 | PM - Transmisor presión entrada sol precipitado PIT3017 |  | 176.7 | 90
2026-W15 | 2026-04-17 | P02 | PASELE01 | Instrumentación | 23 | 11 | 5.4 | 0.6 | 17 | 73.9 | No | 7 | 3 | 500169 | PM02 | PM - Celosía XM0114 |  | 115.9 | 90
2026-W15 | 2026-04-17 | P02 | PASINS01 | Mecánica | 32 | 11.1 | 4.4 | 0.2 | 15.7 | 49.1 | No | 3 | 3 | 500172 | PM02 | PM - Tablero de comunicación |  | 176.5 | 90
2026-W15 | 2026-04-17 | P02 | PASINS01 | Eléctrica | 18 | 9 | 2.3 | 0.4 | 11.7 | 65 | No | 7 | 2 | 500157 | PM02 | PM - Tablero distribución instrumentación |  | 91.1 | 90
2026-W15 | 2026-04-17 | P02 | PASINS01 | Instrumentación | 22 | 10.1 | 6.3 | 1.5 | 17.9 | 81.4 | No | 3 | 1 | 500121 | PM01 | CM - Calefactor eléctrico edificio | 1004233 | 191.5 | 90
2026-W15 | 2026-04-17 | P02 | PAHMEC01 | Mecánica | 33 | 4.6 | 7.3 | 0.2 | 12.1 | 36.7 | No | 4 | 1 | 500155 | PM02 | PM - Válvula control salida precapa HV3102 |  | 26.1 | 90
2026-W15 | 2026-04-17 | P02 | PAHMEC01 | Eléctrica | 19 | 4.8 | 3.7 | 1.6 | 10.1 | 53.2 | No | 4 | 4 | 500100 | PM02 | PM - Puerta enrollable Stockpile |  | 69.1 | 90
2026-W15 | 2026-04-17 | P02 | PAHMEC01 | Instrumentación | 22 | 4.1 | 3.9 | 0.2 | 8.2 | 37.3 | No | 6 | 4 | 500051 | PM01 | CM - Tablero distribución UPS | 1002225 | 68.1 | 90
2026-W15 | 2026-04-17 | P02 | PAHELE01 | Mecánica | 27 | 12.8 | 6.7 | 1.6 | 21.1 | 78.1 | No | 5 | 4 | 500112 | PM02 | PM - Hidrante/ Grifos FH0129 |  | 186.4 | 90
2026-W15 | 2026-04-17 | P02 | PAHELE01 | Eléctrica | 39 | 18.6 | 6.5 | 1.2 | 26.3 | 67.4 | No | 6 | 1 | 500179 | PM01 | CM - Transmisor nivel atricción carbón LIT3627 | 1000471 | 159.1 | 90
2026-W15 | 2026-04-17 | P02 | PAHELE01 | Instrumentación | 23 | 9.8 | 5.7 | 1.2 | 16.7 | 72.6 | No | 6 | 2 | 500157 | PM02 | PM - Tablero distribución instrumentación |  | 43.8 | 90
2026-W15 | 2026-04-17 | P02 | PAHINS01 | Mecánica | 25 | 7.8 | 4.3 | 0.6 | 12.7 | 50.8 | No | 3 | 4 | 500120 | PM01 | CM - Transmisor presión salida sol barren PIT3241 | 1006319 | 39.5 | 90
2026-W15 | 2026-04-17 | P02 | PAHINS01 | Eléctrica | 22 | 4.6 | 6 | 1.8 | 12.4 | 56.4 | No | 6 | 3 | 500023 | PM02 | PM - Válvula control entrada aire FV1804 |  | 36.4 | 90
2026-W15 | 2026-04-17 | P02 | PAHINS01 | Instrumentación | 36 | 8.7 | 6.5 | 1.9 | 17.1 | 47.5 | No | 6 | 4 | 500013 | PM02 | PM - Válvula control drenaje pulpa HV1006 | 1003608 | 193.9 | 90
2026-W15 | 2026-04-18 | M01 | PASMEC01 | Mecánica | 17 | 4.2 | 2.9 | 0.9 | 8 | 47.1 | No | 5 | 3 | 500108 | PM02 | PM - Motor eléctrico HY0036M1 | 1003524 | 69.3 | 90
2026-W15 | 2026-04-18 | M01 | PASMEC01 | Eléctrica | 28 | 12.2 | 8.4 | 0.9 | 21.5 | 76.8 | No | 7 | 4 | 500175 | PM01 | CM - Válvula control aceite XV0279 |  | 131.2 | 90
2026-W15 | 2026-04-18 | M01 | PASMEC01 | Instrumentación | 38 | 10.6 | 6.4 | 2.9 | 19.9 | 52.4 | No | 4 | 4 | 500021 | PM02 | PM - Tornillo alimentador sulfato de cobre |  | 158.4 | 90
2026-W15 | 2026-04-18 | M01 | PASELE01 | Mecánica | 32 | 15.4 | 8 | 0.1 | 23.5 | 73.4 | No | 7 | 3 | 500140 | PM02 | PM - Correa retorno pebbles |  | 104.7 | 90
2026-W15 | 2026-04-18 | M01 | PASELE01 | Eléctrica | 34 | 16.5 | 6.8 | 0 | 23.3 | 68.5 | No | 4 | 3 | 500145 | PM02 | PM - Transmisor presion agua PT0404 |  | 198.7 | 90
2026-W15 | 2026-04-18 | M01 | PASELE01 | Instrumentación | 31 | 14.1 | 7.6 | 1.1 | 22.8 | 73.5 | No | 7 | 3 | 500048 | PM01 | CM - Válvula control flujo aire secado FV4662 | 1001024 | 38.7 | 90
2026-W15 | 2026-04-18 | M01 | PASINS01 | Mecánica | 18 | 7.2 | 2.1 | 1.6 | 10.9 | 60.6 | No | 4 | 2 | 500041 | PM02 | PM - Tecle bomba sumergible lixiviación |  | 174.9 | 90
2026-W15 | 2026-04-18 | M01 | PASINS01 | Eléctrica | 18 | 6.2 | 3.9 | 1.6 | 11.7 | 65 | No | 5 | 1 | 500146 | PM02 | PM - Válvula control alimenta pulpa HV1501C |  | 115.2 | 90
2026-W15 | 2026-04-18 | M01 | PASINS01 | Instrumentación | 28 | 8.4 | 6.8 | 0.6 | 15.8 | 56.4 | No | 4 | 1 | 500105 | PM02 | PM - Tablero SCI | 1004073 | 134.2 | 90
2026-W15 | 2026-04-18 | M01 | PAHMEC01 | Mecánica | 36 | 16.4 | 7.6 | 2.3 | 26.3 | 73.1 | No | 5 | 2 | 500013 | PM02 | PM - Válvula control drenaje pulpa HV1006 |  | 111.5 | 90
2026-W15 | 2026-04-18 | M01 | PAHMEC01 | Eléctrica | 16 | 7.1 | 2.8 | 0.5 | 10.4 | 65 | No | 7 | 2 | 500141 | PM02 | PM - Lava ojos emergencia |  | 121.4 | 90
2026-W15 | 2026-04-18 | M01 | PAHMEC01 | Instrumentación | 35 | 10 | 4.2 | 2.3 | 16.5 | 47.1 | No | 3 | 3 | 500130 | PM01 | CM - Tablero de enchufes | 1004425 | 158.1 | 90
2026-W15 | 2026-04-18 | M01 | PAHELE01 | Mecánica | 38 | 5.7 | 3.9 | 0.3 | 9.9 | 26.1 | No | 2 | 2 | 500166 | PM02 | PM - Bomba muestreo pulpa relaves PU0267 |  | 48.8 | 90
2026-W15 | 2026-04-18 | M01 | PAHELE01 | Eléctrica | 34 | 15.2 | 9 | 0.1 | 24.3 | 71.5 | No | 5 | 3 | 500184 | PM01 | CM - Válvula control descarga agua filtrado HV4812 | 1003172 | 86.2 | 90
2026-W15 | 2026-04-18 | M01 | PAHELE01 | Instrumentación | 33 | 7 | 6.9 | 0.6 | 14.5 | 43.9 | No | 6 | 2 | 500109 | PM02 | PM - Variador frecuencia 3620PU0239M1VF |  | 139.3 | 90
2026-W15 | 2026-04-18 | M01 | PAHINS01 | Mecánica | 32 | 4.9 | 6.4 | 2.9 | 14.2 | 44.4 | No | 4 | 4 | 500162 | PM02 | PM - Tecle bomba sumergible lixiviación |  | 109.7 | 90
2026-W15 | 2026-04-18 | M01 | PAHINS01 | Eléctrica | 21 | 7.5 | 2.3 | 0.4 | 10.2 | 48.6 | No | 3 | 3 | 500008 | PM02 | PM - Bomba precipitado |  | 132 | 90
2026-W15 | 2026-04-18 | M01 | PAHINS01 | Instrumentación | 38 | 18.2 | 8.5 | 3.6 | 30.3 | 79.7 | No | 5 | 1 | 500018 | PM02 | PM - Transmisor presión aceite PIT4875 |  | 128 | 90
2026-W15 | 2026-04-18 | M02 | PASMEC01 | Mecánica | 37 | 8 | 3.6 | 1.2 | 12.8 | 34.6 | No | 2 | 4 | 500070 | PM02 | PM - Transmisor nivel hidrox sodio LIT3467 |  | 163.2 | 90
2026-W15 | 2026-04-18 | M02 | PASMEC01 | Eléctrica | 37 | 9.5 | 5 | 0.9 | 15.4 | 41.6 | No | 7 | 2 | 500149 | PM02 | PM - Indicador presión aceite PI1315 |  | 71 | 90
2026-W15 | 2026-04-18 | M02 | PASMEC01 | Instrumentación | 24 | 10 | 6.3 | 0.8 | 17.1 | 71.2 | No | 5 | 1 | 500054 | PM01 | CM - Intercambiador calor calentamiento | 1000356 | 132.1 | 90
2026-W15 | 2026-04-18 | M02 | PASELE01 | Mecánica | 21 | 7.7 | 5.2 | 1.6 | 14.5 | 69 | No | 3 | 4 | 500021 | PM02 | PM - Tornillo alimentador sulfato de cobre |  | 131.8 | 90
2026-W15 | 2026-04-18 | M02 | PASELE01 | Eléctrica | 20 | 7.6 | 5 | 1.8 | 14.4 | 72 | No | 7 | 3 | 500013 | PM02 | PM - Válvula control drenaje pulpa HV1006 | 1004214 | 66.1 | 90
2026-W15 | 2026-04-18 | M02 | PASELE01 | Instrumentación | 31 | 15.5 | 3.3 | 0.1 | 18.9 | 61 | No | 6 | 4 | 500054 | PM01 | CM - Intercambiador calor calentamiento | 1005164 | 170.6 | 90
2026-W15 | 2026-04-18 | M02 | PASINS01 | Mecánica | 32 | 9.2 | 7.1 | 1.4 | 17.7 | 55.3 | No | 4 | 1 | 500047 | PM01 | CM - Indicador presión agua PI0251 |  | 96.9 | 90
2026-W15 | 2026-04-18 | M02 | PASINS01 | Eléctrica | 38 | 17.7 | 5.9 | 1.6 | 25.2 | 66.3 | No | 6 | 4 | 500046 | PM02 | PM - Gabinete servidor core switch 1 y commun |  | 189.7 | 90
2026-W15 | 2026-04-18 | M02 | PASINS01 | Instrumentación | 38 | 10.6 | 9.5 | 2.3 | 22.4 | 58.9 | No | 6 | 3 | 500102 | PM02 | PM - Ciclo convertidor potencia MI0001SE |  | 120.5 | 90
2026-W15 | 2026-04-18 | M02 | PAHMEC01 | Mecánica | 34 | 10.6 | 6.3 | 3 | 19.9 | 58.5 | No | 3 | 4 | 500081 | PM02 | PM - Transmisor nivel lechada cal LIT5271 | 1020046 | 70.3 | 90
2026-W15 | 2026-04-18 | M02 | PAHMEC01 | Eléctrica | 18 | 6.5 | 4 | 0.6 | 11.1 | 61.7 | No | 5 | 3 | 500163 | PM02 | PM - Válvula control salida precapa HV3102 |  | 61.1 | 90
2026-W15 | 2026-04-18 | M02 | PAHMEC01 | Instrumentación | 21 | 7.1 | 3.5 | 0.8 | 11.4 | 54.3 | No | 7 | 2 | 500111 | PM02 | PM - Servidor secundario |  | 119.7 | 90
2026-W15 | 2026-04-18 | M02 | PAHELE01 | Mecánica | 30 | 14.8 | 6.1 | 0 | 20.9 | 69.7 | No | 7 | 1 | 500012 | PM02 | PM - Gabinete PLC horno fundición 1 |  | 24.5 | 90
2026-W15 | 2026-04-18 | M02 | PAHELE01 | Eléctrica | 23 | 6.1 | 3.3 | 0.7 | 10.1 | 43.9 | No | 5 | 3 | 500024 | PM02 | PM - Válvula alivio presión aceite PRV0664 |  | 98.9 | 90
2026-W15 | 2026-04-18 | M02 | PAHELE01 | Instrumentación | 30 | 10.5 | 3.5 | 1 | 15 | 50 | No | 6 | 2 | 500153 | PM02 | PM - Sistema Spray Grasa Engranaje - Molino SAG |  | 178.7 | 90
2026-W15 | 2026-04-18 | M02 | PAHINS01 | Mecánica | 22 | 5 | 2.4 | 1.2 | 8.6 | 39.1 | No | 4 | 1 | 500188 | PM01 | CM - Switch posición ZS1716 | 1003905 | 98.5 | 90
2026-W15 | 2026-04-18 | M02 | PAHINS01 | Eléctrica | 18 | 7 | 4.8 | 1.4 | 13.2 | 73.3 | No | 7 | 2 | 500084 | PM02 | PM - Motor eléctrico HY0001M1 |  | 64.2 | 90
2026-W15 | 2026-04-18 | M02 | PAHINS01 | Instrumentación | 35 | 16.1 | 7.4 | 0.8 | 24.3 | 69.4 | No | 3 | 3 | 500016 | PM02 | PM - Lava ojos emergencia |  | 130.7 | 90
2026-W15 | 2026-04-18 | P01 | PASMEC01 | Mecánica | 33 | 9.5 | 7.6 | 1.9 | 19 | 57.6 | No | 6 | 2 | 500104 | PM02 | PM - Hidrante/ Grifos FH0138 | 1006092 | 119.7 | 90
2026-W15 | 2026-04-18 | P01 | PASMEC01 | Eléctrica | 26 | 11.7 | 3.5 | 0.8 | 16 | 61.5 | No | 2 | 1 | 500027 | PM02 | PM - Válvula control aceite XV4883 |  | 75.6 | 90
2026-W15 | 2026-04-18 | P01 | PASMEC01 | Instrumentación | 37 | 7.1 | 5.9 | 0.7 | 13.7 | 37 | No | 3 | 4 | 500170 | PM02 | PM - Switch posición ZS0038A |  | 40.9 | 90
2026-W15 | 2026-04-18 | P01 | PASELE01 | Mecánica | 29 | 4.5 | 8.4 | 0.4 | 13.3 | 45.9 | No | 7 | 1 | 500162 | PM02 | PM - Tecle bomba sumergible lixiviación | 1003463 | 164.4 | 90
2026-W15 | 2026-04-18 | P01 | PASELE01 | Eléctrica | 23 | 7.8 | 4.3 | 2.2 | 14.3 | 62.2 | No | 2 | 2 | 500153 | PM02 | PM - Sistema Spray Grasa Engranaje - Molino SAG |  | 151.6 | 90
2026-W15 | 2026-04-18 | P01 | PASELE01 | Instrumentación | 35 | 10.1 | 5 | 3.3 | 18.4 | 52.6 | No | 3 | 1 | 500186 | PM01 | CM - Tablero distribución instrumentación | 1003897 | 124.2 | 90
2026-W15 | 2026-04-18 | P01 | PASINS01 | Mecánica | 20 | 4.1 | 4.8 | 1.3 | 10.2 | 51 | No | 4 | 3 | 500126 | PM01 | CM - Válvula control salida carbon descargado HV3394 | 1000720 | 157.9 | 90
2026-W15 | 2026-04-18 | P01 | PASINS01 | Eléctrica | 29 | 4.3 | 7.6 | 0.4 | 12.3 | 42.4 | No | 6 | 4 | 500043 | PM02 | PM - Sirena YA3453 |  | 151.4 | 90
2026-W15 | 2026-04-18 | P01 | PASINS01 | Instrumentación | 32 | 10 | 5.5 | 0.5 | 16 | 50 | No | 3 | 3 | 500135 | PM02 | PM - Compresor de aire neumático |  | 153.7 | 90
2026-W15 | 2026-04-18 | P01 | PAHMEC01 | Mecánica | 31 | 8.6 | 3.2 | 1.2 | 13 | 41.9 | No | 5 | 3 | 500051 | PM01 | CM - Tablero distribución UPS | 1004427 | 85.4 | 90
2026-W15 | 2026-04-18 | P01 | PAHMEC01 | Eléctrica | 16 | 4.5 | 3.2 | 1.3 | 9 | 56.2 | No | 6 | 2 | 500008 | PM02 | PM - Bomba precipitado |  | 150.4 | 90
2026-W15 | 2026-04-18 | P01 | PAHMEC01 | Instrumentación | 25 | 4 | 3.5 | 1.5 | 9 | 36 | No | 5 | 4 | 500045 | PM02 | PM - Transmisor presión agua potable PIT7025 |  | 42.9 | 90
2026-W15 | 2026-04-18 | P01 | PAHELE01 | Mecánica | 22 | 9.3 | 4.7 | 1.7 | 15.7 | 71.4 | No | 3 | 4 | 500132 | PM02 | PM - Válvula control agua sello HV2723 |  | 156.5 | 90
2026-W15 | 2026-04-18 | P01 | PAHELE01 | Eléctrica | 37 | 14.9 | 10.5 | 0.3 | 25.7 | 69.5 | No | 7 | 4 | 500157 | PM02 | PM - Tablero distribución instrumentación |  | 65.7 | 90
2026-W15 | 2026-04-18 | P01 | PAHELE01 | Instrumentación | 32 | 15.1 | 9.1 | 0.8 | 25 | 78.1 | No | 3 | 1 | 500098 | PM02 | PM - Unidad presurización |  | 98 | 90
2026-W15 | 2026-04-18 | P01 | PAHINS01 | Mecánica | 27 | 6.6 | 3.2 | 2.4 | 12.2 | 45.2 | No | 5 | 4 | 500079 | PM02 | PM - Gabinete RIO | 1001242 | 176.3 | 90
2026-W15 | 2026-04-18 | P01 | PAHINS01 | Eléctrica | 17 | 5.9 | 4.3 | 1 | 11.2 | 65.9 | No | 4 | 2 | 500004 | PM02 | PM - Válvula control aceite XV0256D |  | 70.8 | 90
2026-W15 | 2026-04-18 | P01 | PAHINS01 | Instrumentación | 39 | 8.9 | 7.8 | 1.7 | 18.4 | 47.2 | No | 3 | 3 | 500137 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 130.5 | 90
2026-W15 | 2026-04-18 | P02 | PASMEC01 | Mecánica | 25 | 9.5 | 5.4 | 2 | 16.9 | 67.6 | No | 5 | 3 | 500056 | PM01 | CM - Gabinete control Merril Crowe & Refinación |  | 157.5 | 90
2026-W15 | 2026-04-18 | P02 | PASMEC01 | Eléctrica | 18 | 5.3 | 3.5 | 1.6 | 10.4 | 57.8 | No | 3 | 1 | 500178 | PM01 | CM - Sensor temperatura TE0802 | 1003872 | 95.8 | 90
2026-W15 | 2026-04-18 | P02 | PASMEC01 | Instrumentación | 19 | 8.7 | 4.3 | 0.9 | 13.9 | 73.2 | No | 2 | 3 | 500028 | PM02 | PM - Válvula control succión agua fresca HV7808 |  | 172.2 | 90
2026-W15 | 2026-04-18 | P02 | PASELE01 | Mecánica | 25 | 5 | 4.3 | 0.2 | 9.5 | 38 | No | 2 | 1 | 500017 | PM02 | PM - Indicador presión agua PI0423 |  | 94.9 | 90
2026-W15 | 2026-04-18 | P02 | PASELE01 | Eléctrica | 39 | 14.6 | 7.6 | 2.3 | 24.5 | 62.8 | No | 5 | 1 | 500106 | PM02 | PM - Válvula control succión ayuda filtrante HV3281 |  | 68 | 90
2026-W15 | 2026-04-18 | P02 | PASELE01 | Instrumentación | 36 | 7.6 | 10.3 | 1.9 | 19.8 | 55 | No | 3 | 1 | 500025 | PM02 | PM - Válvula control succión agua filtrada HV4771A |  | 85.7 | 90
2026-W15 | 2026-04-18 | P02 | PASINS01 | Mecánica | 16 | 6.4 | 3.9 | 0.6 | 10.9 | 68.1 | No | 7 | 4 | 500045 | PM02 | PM - Transmisor presión agua potable PIT7025 |  | 79.4 | 90
2026-W15 | 2026-04-18 | P02 | PASINS01 | Eléctrica | 24 | 11.8 | 4.4 | 2 | 18.2 | 75.8 | No | 7 | 4 | 500181 | PM01 | CM - Bomba diafragma grasa PU0001 | 1005188 | 109.3 | 90
2026-W15 | 2026-04-18 | P02 | PASINS01 | Instrumentación | 17 | 5.5 | 4.8 | 0.2 | 10.5 | 61.8 | No | 7 | 3 | 500095 | PM02 | PM - Bomba sumidero lixiviación |  | 73.9 | 90
2026-W15 | 2026-04-18 | P02 | PAHMEC01 | Mecánica | 22 | 7.1 | 4.2 | 1.8 | 13.1 | 59.5 | No | 6 | 3 | 500065 | PM02 | PM - Muestreador alimentación filtros |  | 94.6 | 90
2026-W15 | 2026-04-18 | P02 | PAHMEC01 | Eléctrica | 18 | 6 | 4.8 | 0.5 | 11.3 | 62.8 | No | 2 | 1 | 500052 | PM01 | CM - Tablero distribución instrumentación | 1001724 | 97.5 | 90
2026-W15 | 2026-04-18 | P02 | PAHMEC01 | Instrumentación | 29 | 5.1 | 4.8 | 0.9 | 10.8 | 37.2 | No | 3 | 1 | 500057 | PM01 | CM - Bomba rotativa aceite PU0510 |  | 176.5 | 90
2026-W15 | 2026-04-18 | P02 | PAHELE01 | Mecánica | 35 | 11.5 | 4.7 | 1.4 | 17.6 | 50.3 | No | 5 | 2 | 500174 | PM02 | PM - Bomba precipitado | 1001777 | 187.7 | 90
2026-W15 | 2026-04-18 | P02 | PAHELE01 | Eléctrica | 36 | 5.9 | 8 | 0.8 | 14.7 | 40.8 | No | 4 | 2 | 500114 | PM01 | CM - Transmisor vibración VT0020A | 1005940 | 169.4 | 90
2026-W15 | 2026-04-18 | P02 | PAHELE01 | Instrumentación | 24 | 7.5 | 5.7 | 0.4 | 13.6 | 56.7 | No | 6 | 1 | 500105 | PM02 | PM - Tablero SCI |  | 150.7 | 90
2026-W15 | 2026-04-18 | P02 | PAHINS01 | Mecánica | 21 | 7.7 | 2.5 | 0.9 | 11.1 | 52.9 | No | 7 | 1 | 500054 | PM01 | CM - Intercambiador calor calentamiento | 1002470 | 123.8 | 90
2026-W15 | 2026-04-18 | P02 | PAHINS01 | Eléctrica | 19 | 6.2 | 3.3 | 0.8 | 10.3 | 54.2 | No | 6 | 4 | 500155 | PM02 | PM - Válvula control salida precapa HV3102 |  | 106.9 | 90
2026-W15 | 2026-04-18 | P02 | PAHINS01 | Instrumentación | 36 | 13.7 | 10.5 | 2.9 | 27.1 | 75.3 | No | 4 | 2 | 500061 | PM01 | CM - Transmisor presión aceite PIT4875 |  | 82.6 | 90
2026-W15 | 2026-04-19 | M01 | PASMEC01 | Mecánica | 34 | 9.2 | 4.2 | 3.4 | 16.8 | 49.4 | No | 2 | 1 | 500046 | PM02 | PM - Gabinete servidor core switch 1 y commun | 1020202 | 179.2 | 90
2026-W15 | 2026-04-19 | M01 | PASMEC01 | Eléctrica | 30 | 7.8 | 5.8 | 2.5 | 16.1 | 53.7 | No | 7 | 2 | 500062 | PM01 | CM - Transmisor nivel lechada cal LIT5271 |  | 48.9 | 90
2026-W15 | 2026-04-19 | M01 | PASMEC01 | Instrumentación | 24 | 8 | 5.2 | 0 | 13.2 | 55 | No | 3 | 2 | 500078 | PM02 | PM - Unidad aire acondicionado |  | 85.1 | 90
2026-W15 | 2026-04-19 | M01 | PASELE01 | Mecánica | 35 | 6.4 | 5.2 | 2.8 | 14.4 | 41.1 | No | 6 | 3 | 500141 | PM02 | PM - Lava ojos emergencia |  | 188.4 | 90
2026-W15 | 2026-04-19 | M01 | PASELE01 | Eléctrica | 19 | 7.9 | 3.9 | 1.5 | 13.3 | 70 | No | 3 | 1 | 500003 | PM02 | PM - Tablero de comunicación | 1001117 | 86.2 | 90
2026-W15 | 2026-04-19 | M01 | PASELE01 | Instrumentación | 23 | 5.9 | 4.8 | 2.2 | 12.9 | 56.1 | No | 2 | 4 | 500008 | PM02 | PM - Bomba precipitado |  | 37.1 | 90
2026-W15 | 2026-04-19 | M01 | PASINS01 | Mecánica | 21 | 9.9 | 2.5 | 0.8 | 13.2 | 62.9 | No | 7 | 2 | 500108 | PM02 | PM - Motor eléctrico HY0036M1 |  | 183.1 | 90
2026-W15 | 2026-04-19 | M01 | PASINS01 | Eléctrica | 33 | 10.8 | 7.9 | 1.1 | 19.8 | 60 | No | 2 | 4 | 500075 | PM02 | PM - Switch posición giro rastras ZS4377D |  | 38.4 | 90
2026-W15 | 2026-04-19 | M01 | PASINS01 | Instrumentación | 30 | 9.1 | 4.1 | 1.8 | 15 | 50 | No | 6 | 3 | 500011 | PM02 | PM - Válvula control agua sello HV2723 |  | 41.9 | 90
2026-W15 | 2026-04-19 | M01 | PAHMEC01 | Mecánica | 32 | 10.8 | 7.4 | 2.7 | 20.9 | 65.3 | No | 5 | 2 | 500070 | PM02 | PM - Transmisor nivel hidrox sodio LIT3467 | 1004676 | 157 | 90
2026-W15 | 2026-04-19 | M01 | PAHMEC01 | Eléctrica | 24 | 8.5 | 6.5 | 2 | 17 | 70.8 | No | 6 | 1 | 500099 | PM02 | PM - Indicador presión agua PI0251 |  | 80.7 | 90
2026-W15 | 2026-04-19 | M01 | PAHMEC01 | Instrumentación | 37 | 4.7 | 3 | 1.3 | 9 | 24.3 | No | 2 | 4 | 500184 | PM01 | CM - Válvula control descarga agua filtrado HV4812 |  | 53.9 | 90
2026-W15 | 2026-04-19 | M01 | PAHELE01 | Mecánica | 30 | 12.3 | 3.9 | 1.3 | 17.5 | 58.3 | No | 4 | 3 | 500090 | PM02 | PM - Válvula control succión sol rica HV2807 |  | 26.6 | 90
2026-W15 | 2026-04-19 | M01 | PAHELE01 | Eléctrica | 18 | 4.6 | 5.2 | 1 | 10.8 | 60 | No | 7 | 2 | 500076 | PM02 | PM - Cajón (Futuro) |  | 109.2 | 90
2026-W15 | 2026-04-19 | M01 | PAHELE01 | Instrumentación | 22 | 6.5 | 5.4 | 1.1 | 13 | 59.1 | No | 5 | 2 | 500089 | PM02 | PM - Transmisor presión salida sol barren PIT3241 |  | 28 | 90
2026-W15 | 2026-04-19 | M01 | PAHINS01 | Mecánica | 19 | 6.9 | 4 | 1.8 | 12.7 | 66.8 | No | 7 | 4 | 500055 | PM01 | CM - Baliza YL3612 | 1002002 | 106.3 | 90
2026-W15 | 2026-04-19 | M01 | PAHINS01 | Eléctrica | 20 | 9.2 | 5.2 | 1 | 15.4 | 77 | No | 2 | 2 | 500154 | PM02 | PM - Lava ojos emergencia | 1000620 | 58.7 | 90
2026-W15 | 2026-04-19 | M01 | PAHINS01 | Instrumentación | 38 | 17.8 | 3.2 | 1.2 | 22.2 | 58.4 | No | 4 | 2 | 500115 | PM01 | CM - Bomba vacío retorta |  | 146.6 | 90
2026-W15 | 2026-04-19 | M02 | PASMEC01 | Mecánica | 19 | 8.3 | 3.3 | 0.3 | 11.9 | 62.6 | No | 4 | 2 | 500125 | PM01 | CM - Transmisor presión aceite PIT4824 |  | 89.4 | 90
2026-W15 | 2026-04-19 | M02 | PASMEC01 | Eléctrica | 21 | 9.6 | 5.6 | 1.7 | 16.9 | 80.5 | No | 4 | 2 | 500107 | PM02 | PM - Gabinete manguera y equipo contraincendios HH0105 |  | 161.4 | 90
2026-W15 | 2026-04-19 | M02 | PASMEC01 | Instrumentación | 37 | 4.5 | 10.4 | 0.5 | 15.4 | 41.6 | No | 2 | 3 | 500080 | PM02 | PM - Válvula control aire soplado HV4658 |  | 32.6 | 90
2026-W15 | 2026-04-19 | M02 | PASELE01 | Mecánica | 39 | 4.8 | 3.1 | 0.3 | 8.2 | 21 | No | 3 | 4 | 500008 | PM02 | PM - Bomba precipitado | 1000008 | 103.5 | 90
2026-W15 | 2026-04-19 | M02 | PASELE01 | Eléctrica | 31 | 10.7 | 4.1 | 0.2 | 15 | 48.4 | No | 4 | 2 | 500096 | PM02 | PM - Válvula control descarga agua fresca HV7819 |  | 77.5 | 90
2026-W15 | 2026-04-19 | M02 | PASELE01 | Instrumentación | 27 | 10.6 | 6.7 | 2.3 | 19.6 | 72.6 | No | 2 | 4 | 500094 | PM02 | PM - Switch baja presión descarga fluido térmico PSL3498 |  | 168 | 90
2026-W15 | 2026-04-19 | M02 | PASINS01 | Mecánica | 23 | 7.3 | 5.6 | 0.6 | 13.5 | 58.7 | No | 3 | 4 | 500039 | PM02 | PM - Chute carbónHO0068 |  | 142.1 | 90
2026-W15 | 2026-04-19 | M02 | PASINS01 | Eléctrica | 33 | 14.2 | 4.8 | 1.9 | 20.9 | 63.3 | No | 3 | 1 | 500084 | PM02 | PM - Motor eléctrico HY0001M1 |  | 180.1 | 90
2026-W15 | 2026-04-19 | M02 | PASINS01 | Instrumentación | 33 | 4.7 | 3.3 | 1.5 | 9.5 | 28.8 | No | 2 | 3 | 500086 | PM02 | PM - Sensor nivel refrigerante LE0177 |  | 88.5 | 90
2026-W15 | 2026-04-19 | M02 | PAHMEC01 | Mecánica | 36 | 16.5 | 10 | 0.8 | 27.3 | 75.8 | No | 5 | 2 | 500044 | PM02 | PM - Válvula control entrada sol precipitado HV3185 | 1006218 | 75 | 90
2026-W15 | 2026-04-19 | M02 | PAHMEC01 | Eléctrica | 19 | 8.6 | 4.5 | 0 | 13.1 | 68.9 | No | 2 | 1 | 500036 | PM02 | PM - Colector polvo horno fundición |  | 46 | 90
2026-W15 | 2026-04-19 | M02 | PAHMEC01 | Instrumentación | 16 | 8 | 3.1 | 0.7 | 11.8 | 73.8 | No | 7 | 3 | 500156 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 40.9 | 90
2026-W15 | 2026-04-19 | M02 | PAHELE01 | Mecánica | 18 | 6.7 | 2.7 | 0.3 | 9.7 | 53.9 | No | 3 | 3 | 500171 | PM02 | PM - Switch bajo nivel aceite LSL0253 | 1002218 | 110.5 | 90
2026-W15 | 2026-04-19 | M02 | PAHELE01 | Eléctrica | 35 | 7.8 | 8.9 | 0.4 | 17.1 | 48.9 | No | 5 | 1 | 500104 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 37.7 | 90
2026-W15 | 2026-04-19 | M02 | PAHELE01 | Instrumentación | 27 | 11 | 3.1 | 0.8 | 14.9 | 55.2 | No | 3 | 4 | 500176 | PM01 | CM - Válvula control succión nitrato plomo HV2962 | 1002661 | 67 | 90
2026-W15 | 2026-04-19 | M02 | PAHINS01 | Mecánica | 22 | 5.2 | 2.5 | 0.4 | 8.1 | 36.8 | No | 4 | 2 | 500155 | PM02 | PM - Válvula control salida precapa HV3102 | 1003948 | 119.3 | 90
2026-W15 | 2026-04-19 | M02 | PAHINS01 | Eléctrica | 18 | 6.5 | 2.4 | 0.6 | 9.5 | 52.8 | No | 7 | 2 | 500141 | PM02 | PM - Lava ojos emergencia | 1002788 | 88.8 | 90
2026-W15 | 2026-04-19 | M02 | PAHINS01 | Instrumentación | 19 | 9.5 | 3.4 | 1.1 | 14 | 73.7 | No | 5 | 3 | 500009 | PM02 | PM - Estanque diesel dia regeneración carbón | 1003319 | 41.1 | 90
2026-W15 | 2026-04-19 | P01 | PASMEC01 | Mecánica | 29 | 9.9 | 4.6 | 0.8 | 15.3 | 52.8 | No | 2 | 3 | 500155 | PM02 | PM - Válvula control salida precapa HV3102 |  | 44.2 | 90
2026-W15 | 2026-04-19 | P01 | PASMEC01 | Eléctrica | 36 | 7.5 | 4.7 | 0.4 | 12.6 | 35 | No | 6 | 4 | 500129 | PM01 | CM - Gabinete control Chancador Primario | 1002653 | 108.8 | 90
2026-W15 | 2026-04-19 | P01 | PASMEC01 | Instrumentación | 25 | 4.2 | 7.4 | 0.5 | 12.1 | 48.4 | No | 4 | 3 | 500071 | PM02 | PM - Calefactor eléctrico estanque HE0112 |  | 121.1 | 90
2026-W15 | 2026-04-19 | P01 | PASELE01 | Mecánica | 16 | 4.4 | 4 | 0.3 | 8.7 | 54.4 | No | 6 | 1 | 500148 | PM02 | PM - Válvula control descarga sol rica HV2810 |  | 105.5 | 90
2026-W15 | 2026-04-19 | P01 | PASELE01 | Eléctrica | 36 | 15.3 | 4.4 | 3.2 | 22.9 | 63.6 | No | 2 | 4 | 500163 | PM02 | PM - Válvula control salida precapa HV3102 | 1003431 | 187.2 | 90
2026-W15 | 2026-04-19 | P01 | PASELE01 | Instrumentación | 34 | 11.7 | 4.5 | 3.4 | 19.6 | 57.6 | No | 2 | 1 | 500091 | PM02 | PM - Estanque diesel dia regeneración carbón |  | 21 | 90
2026-W15 | 2026-04-19 | P01 | PASINS01 | Mecánica | 33 | 4.8 | 9 | 2.4 | 16.2 | 49.1 | No | 5 | 1 | 500017 | PM02 | PM - Indicador presión agua PI0423 |  | 97.3 | 90
2026-W15 | 2026-04-19 | P01 | PASINS01 | Eléctrica | 36 | 7 | 5.5 | 1.8 | 14.3 | 39.7 | No | 3 | 2 | 500116 | PM01 | CM - Transmisor nivel hidrox sodio LIT3467 | 1000693 | 171 | 90
2026-W15 | 2026-04-19 | P01 | PASINS01 | Instrumentación | 21 | 10.1 | 4.2 | 0.2 | 14.5 | 69 | No | 4 | 1 | 500091 | PM02 | PM - Estanque diesel dia regeneración carbón |  | 176.3 | 90
2026-W15 | 2026-04-19 | P01 | PAHMEC01 | Mecánica | 23 | 7.2 | 5.1 | 0.6 | 12.9 | 56.1 | No | 5 | 3 | 500114 | PM01 | CM - Transmisor vibración VT0020A |  | 21.8 | 90
2026-W15 | 2026-04-19 | P01 | PAHMEC01 | Eléctrica | 32 | 10.2 | 8.1 | 3.1 | 21.4 | 66.9 | No | 3 | 4 | 500154 | PM02 | PM - Lava ojos emergencia |  | 23.3 | 90
2026-W15 | 2026-04-19 | P01 | PAHMEC01 | Instrumentación | 30 | 7.4 | 2.9 | 1.6 | 11.9 | 39.7 | No | 3 | 2 | 500116 | PM01 | CM - Transmisor nivel hidrox sodio LIT3467 | 1004411 | 142.1 | 90
2026-W15 | 2026-04-19 | P01 | PAHELE01 | Mecánica | 28 | 9.6 | 6.6 | 2 | 18.2 | 65 | No | 2 | 1 | 500041 | PM02 | PM - Tecle bomba sumergible lixiviación | 1001914 | 176.7 | 90
2026-W15 | 2026-04-19 | P01 | PAHELE01 | Eléctrica | 16 | 7 | 3.8 | 0.4 | 11.2 | 70 | No | 2 | 1 | 500145 | PM02 | PM - Transmisor presion agua PT0404 | 1007160 | 172.3 | 90
2026-W15 | 2026-04-19 | P01 | PAHELE01 | Instrumentación | 19 | 9.5 | 2.7 | 0.9 | 13.1 | 68.9 | No | 5 | 4 | 500169 | PM02 | PM - Celosía XM0114 |  | 60.5 | 90
2026-W15 | 2026-04-19 | P01 | PAHINS01 | Mecánica | 25 | 9.7 | 7.5 | 2 | 19.2 | 76.8 | No | 5 | 2 | 500139 | PM02 | PM - Hidrante/ Grifos FH0136 |  | 70 | 90
2026-W15 | 2026-04-19 | P01 | PAHINS01 | Eléctrica | 29 | 14.4 | 8.7 | 0.3 | 23.4 | 80.7 | No | 4 | 3 | 500149 | PM02 | PM - Indicador presión aceite PI1315 |  | 29.3 | 90
2026-W15 | 2026-04-19 | P01 | PAHINS01 | Instrumentación | 19 | 7.9 | 5.6 | 0.6 | 14.1 | 74.2 | No | 7 | 3 | 500026 | PM02 | PM - Estanque almacenamiento aceite hidráulico TK0088 |  | 98.1 | 90
2026-W15 | 2026-04-19 | P02 | PASMEC01 | Mecánica | 35 | 7.2 | 6.4 | 2 | 15.6 | 44.6 | No | 6 | 3 | 500109 | PM02 | PM - Variador frecuencia 3620PU0239M1VF |  | 156.2 | 90
2026-W15 | 2026-04-19 | P02 | PASMEC01 | Eléctrica | 19 | 4.5 | 3.6 | 1.1 | 9.2 | 48.4 | No | 6 | 1 | 500047 | PM01 | CM - Indicador presión agua PI0251 |  | 72.3 | 90
2026-W15 | 2026-04-19 | P02 | PASMEC01 | Instrumentación | 23 | 11 | 2.8 | 0.1 | 13.9 | 60.4 | No | 3 | 2 | 500154 | PM02 | PM - Lava ojos emergencia |  | 164.2 | 90
2026-W15 | 2026-04-19 | P02 | PASELE01 | Mecánica | 25 | 12.5 | 6.6 | 1.8 | 20.9 | 83.6 | No | 6 | 1 | 500149 | PM02 | PM - Indicador presión aceite PI1315 |  | 171.9 | 90
2026-W15 | 2026-04-19 | P02 | PASELE01 | Eléctrica | 28 | 5.7 | 2.1 | 1.7 | 9.5 | 33.9 | No | 7 | 3 | 500023 | PM02 | PM - Válvula control entrada aire FV1804 |  | 140.7 | 90
2026-W15 | 2026-04-19 | P02 | PASELE01 | Instrumentación | 31 | 8.2 | 6.6 | 0.1 | 14.9 | 48.1 | No | 7 | 2 | 500143 | PM02 | PM - Transmisor nivel solución barren LIT2787 |  | 186.4 | 90
2026-W15 | 2026-04-19 | P02 | PASINS01 | Mecánica | 23 | 6.2 | 6.4 | 2 | 14.6 | 63.5 | No | 3 | 4 | 500109 | PM02 | PM - Variador frecuencia 3620PU0239M1VF |  | 121.4 | 90
2026-W15 | 2026-04-19 | P02 | PASINS01 | Eléctrica | 28 | 8.1 | 5.6 | 2.2 | 15.9 | 56.8 | No | 7 | 4 | 500041 | PM02 | PM - Tecle bomba sumergible lixiviación |  | 132.8 | 90
2026-W15 | 2026-04-19 | P02 | PASINS01 | Instrumentación | 16 | 4.1 | 4.3 | 1.5 | 9.9 | 61.9 | No | 4 | 4 | 500112 | PM02 | PM - Hidrante/ Grifos FH0129 |  | 161.4 | 90
2026-W15 | 2026-04-19 | P02 | PAHMEC01 | Mecánica | 17 | 7.2 | 4.2 | 0.8 | 12.2 | 71.8 | No | 2 | 1 | 500156 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 104.2 | 90
2026-W15 | 2026-04-19 | P02 | PAHMEC01 | Eléctrica | 27 | 11.8 | 7.7 | 2.2 | 21.7 | 80.4 | No | 2 | 2 | 500068 | PM02 | PM - Tecle eléctrico tolva carbon |  | 174.1 | 90
2026-W15 | 2026-04-19 | P02 | PAHMEC01 | Instrumentación | 24 | 5.7 | 2.9 | 0 | 8.6 | 35.8 | No | 4 | 1 | 500165 | PM02 | PM - Motor eléctrico HY0036M1 |  | 40 | 90
2026-W15 | 2026-04-19 | P02 | PAHELE01 | Mecánica | 16 | 7.8 | 3.2 | 1 | 12 | 75 | No | 4 | 1 | 500111 | PM02 | PM - Servidor secundario |  | 83 | 90
2026-W15 | 2026-04-19 | P02 | PAHELE01 | Eléctrica | 18 | 4.6 | 3.7 | 0.6 | 8.9 | 49.4 | No | 5 | 1 | 500040 | PM02 | PM - Mesa rodillos | 1020072 | 32.1 | 90
2026-W15 | 2026-04-19 | P02 | PAHELE01 | Instrumentación | 19 | 7.1 | 5 | 1.3 | 13.4 | 70.5 | No | 4 | 2 | 500024 | PM02 | PM - Válvula alivio presión aceite PRV0664 |  | 114.8 | 90
2026-W15 | 2026-04-19 | P02 | PAHINS01 | Mecánica | 27 | 7.8 | 7.8 | 2.7 | 18.3 | 67.8 | No | 5 | 2 | 500004 | PM02 | PM - Válvula control aceite XV0256D | 1002481 | 61 | 90
2026-W15 | 2026-04-19 | P02 | PAHINS01 | Eléctrica | 39 | 4.2 | 11 | 2.4 | 17.6 | 45.1 | No | 5 | 1 | 500181 | PM01 | CM - Bomba diafragma grasa PU0001 | 1000279 | 185.5 | 90
2026-W15 | 2026-04-19 | P02 | PAHINS01 | Instrumentación | 33 | 16.4 | 8.9 | 3.3 | 28.6 | 86.7 | No | 5 | 3 | 500109 | PM02 | PM - Variador frecuencia 3620PU0239M1VF | 1000254 | 171.6 | 90
2026-W16 | 2026-04-20 | M01 | PASMEC01 | Mecánica | 21 | 5.5 | 2.4 | 2.1 | 10 | 47.6 | No | 7 | 1 | 500181 | PM01 | CM - Bomba diafragma grasa PU0001 |  | 176.8 | 90
2026-W16 | 2026-04-20 | M01 | PASMEC01 | Eléctrica | 32 | 7.9 | 8.5 | 1.9 | 18.3 | 57.2 | No | 3 | 3 | 500057 | PM01 | CM - Bomba rotativa aceite PU0510 | 1000700 | 153.8 | 90
2026-W16 | 2026-04-20 | M01 | PASMEC01 | Instrumentación | 39 | 14.6 | 6.3 | 1.5 | 22.4 | 57.4 | No | 6 | 4 | 500054 | PM01 | CM - Intercambiador calor calentamiento | 1003897 | 113.2 | 90
2026-W16 | 2026-04-20 | M01 | PASELE01 | Mecánica | 28 | 4.9 | 5.1 | 0.3 | 10.3 | 36.8 | No | 4 | 1 | 500138 | PM02 | PM - Motor eléctrico HY0036M1 |  | 67 | 90
2026-W16 | 2026-04-20 | M01 | PASELE01 | Eléctrica | 35 | 9 | 3.5 | 0.3 | 12.8 | 36.6 | No | 7 | 4 | 500103 | PM02 | PM - Tablero SCI |  | 44.5 | 90
2026-W16 | 2026-04-20 | M01 | PASELE01 | Instrumentación | 37 | 18.4 | 3.2 | 0.2 | 21.8 | 58.9 | No | 4 | 1 | 500061 | PM01 | CM - Transmisor presión aceite PIT4875 | 1000384 | 169.8 | 90
2026-W16 | 2026-04-20 | M01 | PASINS01 | Mecánica | 19 | 5.8 | 2.3 | 1.3 | 9.4 | 49.5 | No | 3 | 4 | 500179 | PM01 | CM - Transmisor nivel atricción carbón LIT3627 | 1001988 | 194.2 | 90
2026-W16 | 2026-04-20 | M01 | PASINS01 | Eléctrica | 20 | 4.8 | 4.4 | 1.8 | 11 | 55 | No | 6 | 4 | 500076 | PM02 | PM - Cajón (Futuro) |  | 118.4 | 90
2026-W16 | 2026-04-20 | M01 | PASINS01 | Instrumentación | 27 | 5 | 3.6 | 2 | 10.6 | 39.3 | No | 2 | 2 | 500164 | PM02 | PM - Bomba muestreo pulpa relaves PU0267 |  | 77.7 | 90
2026-W16 | 2026-04-20 | M01 | PAHMEC01 | Mecánica | 19 | 8.6 | 3.6 | 0.8 | 13 | 68.4 | No | 2 | 1 | 500141 | PM02 | PM - Lava ojos emergencia |  | 145.2 | 90
2026-W16 | 2026-04-20 | M01 | PAHMEC01 | Eléctrica | 36 | 7.9 | 3.2 | 0 | 11.1 | 30.8 | No | 5 | 3 | 500050 | PM01 | CM - Línea agua sell 3700-5476-AA1A-3"-WGS-ET |  | 39.3 | 90
2026-W16 | 2026-04-20 | M01 | PAHMEC01 | Instrumentación | 36 | 10 | 10.5 | 2.6 | 23.1 | 64.2 | No | 2 | 3 | 500101 | PM02 | PM - Subestación unitaria |  | 23.4 | 90
2026-W16 | 2026-04-20 | M01 | PAHELE01 | Mecánica | 22 | 4.7 | 2.7 | 2.1 | 9.5 | 43.2 | No | 6 | 2 | 500155 | PM02 | PM - Válvula control salida precapa HV3102 |  | 196 | 90
2026-W16 | 2026-04-20 | M01 | PAHELE01 | Eléctrica | 23 | 11.3 | 6.8 | 1.3 | 19.4 | 84.3 | No | 7 | 1 | 500185 | PM01 | CM - Motor eléctrico HY0036M1 | 1003451 | 117.4 | 90
2026-W16 | 2026-04-20 | M01 | PAHELE01 | Instrumentación | 35 | 5.1 | 4.1 | 2.7 | 11.9 | 34 | No | 4 | 4 | 500047 | PM01 | CM - Indicador presión agua PI0251 |  | 187 | 90
2026-W16 | 2026-04-20 | M01 | PAHINS01 | Mecánica | 30 | 13.9 | 5.7 | 2.4 | 22 | 73.3 | No | 6 | 3 | 500039 | PM02 | PM - Chute carbónHO0068 |  | 187 | 90
2026-W16 | 2026-04-20 | M01 | PAHINS01 | Eléctrica | 30 | 6.5 | 8.1 | 0.8 | 15.4 | 51.3 | No | 2 | 4 | 500022 | PM02 | PM - Unidad re-potabilizadora agua |  | 67.6 | 90
2026-W16 | 2026-04-20 | M01 | PAHINS01 | Instrumentación | 28 | 5.7 | 2.5 | 1.1 | 9.3 | 33.2 | No | 3 | 4 | 500149 | PM02 | PM - Indicador presión aceite PI1315 | 1000272 | 173.9 | 90
2026-W16 | 2026-04-20 | M02 | PASMEC01 | Mecánica | 27 | 8.2 | 2.4 | 2 | 12.6 | 46.7 | No | 4 | 2 | 500059 | PM01 | CM - Mezclador floculante | 1007082 | 75.7 | 90
2026-W16 | 2026-04-20 | M02 | PASMEC01 | Eléctrica | 16 | 5.4 | 4.1 | 0.9 | 10.4 | 65 | No | 4 | 2 | 500032 | PM02 | PM - Válvula control entrada cianuro sodio FV1903 | 1006911 | 117.8 | 90
2026-W16 | 2026-04-20 | M02 | PASMEC01 | Instrumentación | 27 | 11.5 | 6.6 | 0.6 | 18.7 | 69.3 | No | 3 | 4 | 500009 | PM02 | PM - Estanque diesel dia regeneración carbón |  | 84.4 | 90
2026-W16 | 2026-04-20 | M02 | PASELE01 | Mecánica | 26 | 8.1 | 6.2 | 0.2 | 14.5 | 55.8 | No | 5 | 1 | 500010 | PM02 | PM - Tablero SCI |  | 197 | 90
2026-W16 | 2026-04-20 | M02 | PASELE01 | Eléctrica | 25 | 5.4 | 3.5 | 0.8 | 9.7 | 38.8 | No | 7 | 2 | 500017 | PM02 | PM - Indicador presión agua PI0423 |  | 150.8 | 90
2026-W16 | 2026-04-20 | M02 | PASELE01 | Instrumentación | 29 | 9.4 | 7.4 | 1.3 | 18.1 | 62.4 | No | 3 | 3 | 500180 | PM01 | CM - Bomba diesel horno reactivación carbon | 1005755 | 121.6 | 90
2026-W16 | 2026-04-20 | M02 | PASINS01 | Mecánica | 37 | 15.5 | 7.3 | 2.4 | 25.2 | 68.1 | No | 4 | 1 | 500149 | PM02 | PM - Indicador presión aceite PI1315 |  | 97.1 | 90
2026-W16 | 2026-04-20 | M02 | PASINS01 | Eléctrica | 27 | 7.8 | 5.4 | 1.7 | 14.9 | 55.2 | No | 7 | 2 | 500065 | PM02 | PM - Muestreador alimentación filtros |  | 32.3 | 90
2026-W16 | 2026-04-20 | M02 | PASINS01 | Instrumentación | 37 | 6.2 | 10.7 | 1.5 | 18.4 | 49.7 | No | 5 | 4 | 500051 | PM01 | CM - Tablero distribución UPS | 1002537 | 54.1 | 90
2026-W16 | 2026-04-20 | M02 | PAHMEC01 | Mecánica | 33 | 9.5 | 7.3 | 0.1 | 16.9 | 51.2 | No | 2 | 3 | 500127 | PM01 | CM - Válvula control succión agua filtrado HV4810 |  | 119.7 | 90
2026-W16 | 2026-04-20 | M02 | PAHMEC01 | Eléctrica | 33 | 6.5 | 8.4 | 0.2 | 15.1 | 45.8 | No | 2 | 1 | 500104 | PM02 | PM - Hidrante/ Grifos FH0138 | 1003495 | 99.3 | 90
2026-W16 | 2026-04-20 | M02 | PAHMEC01 | Instrumentación | 36 | 11.7 | 4.4 | 0.9 | 17 | 47.2 | No | 6 | 2 | 500123 | PM01 | CM - Válvula control flujo sol barren FV5601 |  | 172.8 | 90
2026-W16 | 2026-04-20 | M02 | PAHELE01 | Mecánica | 33 | 14.8 | 4.7 | 1.1 | 20.6 | 62.4 | No | 2 | 4 | 500151 | PM02 | PM - Válvula control flujo entrada agua rechazo FV3576 | 1000509 | 29 | 90
2026-W16 | 2026-04-20 | M02 | PAHELE01 | Eléctrica | 36 | 5.7 | 2.3 | 0.4 | 8.4 | 23.3 | No | 3 | 3 | 500126 | PM01 | CM - Válvula control salida carbon descargado HV3394 | 1003490 | 143.7 | 90
2026-W16 | 2026-04-20 | M02 | PAHELE01 | Instrumentación | 17 | 7.4 | 2.9 | 0.7 | 11 | 64.7 | No | 2 | 4 | 500169 | PM02 | PM - Celosía XM0114 | 1005261 | 40 | 90
2026-W16 | 2026-04-20 | M02 | PAHINS01 | Mecánica | 30 | 14.3 | 6.9 | 2.7 | 23.9 | 79.7 | No | 3 | 1 | 500070 | PM02 | PM - Transmisor nivel hidrox sodio LIT3467 |  | 82.2 | 90
2026-W16 | 2026-04-20 | M02 | PAHINS01 | Eléctrica | 23 | 10 | 5.9 | 1.7 | 17.6 | 76.5 | No | 7 | 3 | 500052 | PM01 | CM - Tablero distribución instrumentación | 1003409 | 101.7 | 90
2026-W16 | 2026-04-20 | M02 | PAHINS01 | Instrumentación | 16 | 7.9 | 2.9 | 1.5 | 12.3 | 76.9 | No | 7 | 3 | 500063 | PM01 | CM - Válvula control entrada solucion barren FV2314 |  | 198 | 90
2026-W16 | 2026-04-20 | P01 | PASMEC01 | Mecánica | 36 | 6.9 | 9 | 2.3 | 18.2 | 50.6 | No | 2 | 2 | 500112 | PM02 | PM - Hidrante/ Grifos FH0129 |  | 61.8 | 90
2026-W16 | 2026-04-20 | P01 | PASMEC01 | Eléctrica | 16 | 4.5 | 3 | 1.2 | 8.7 | 54.4 | No | 3 | 1 | 500183 | PM01 | CM - Estanque separador TK0054 | 1003921 | 38.5 | 90
2026-W16 | 2026-04-20 | P01 | PASMEC01 | Instrumentación | 18 | 4.5 | 4 | 0.8 | 9.3 | 51.7 | No | 3 | 1 | 500015 | PM02 | PM - Sensor temperatura aire TS4591 |  | 57.6 | 90
2026-W16 | 2026-04-20 | P01 | PASELE01 | Mecánica | 18 | 7.2 | 2.1 | 0 | 9.3 | 51.7 | No | 2 | 1 | 500096 | PM02 | PM - Válvula control descarga agua fresca HV7819 |  | 65.3 | 90
2026-W16 | 2026-04-20 | P01 | PASELE01 | Eléctrica | 32 | 9.1 | 9 | 0.2 | 18.3 | 57.2 | No | 7 | 3 | 500146 | PM02 | PM - Válvula control alimenta pulpa HV1501C | 1000043 | 58.7 | 90
2026-W16 | 2026-04-20 | P01 | PASELE01 | Instrumentación | 30 | 9.7 | 7.5 | 2.5 | 19.7 | 65.7 | No | 3 | 2 | 500116 | PM01 | CM - Transmisor nivel hidrox sodio LIT3467 | 1004174 | 92.5 | 90
2026-W16 | 2026-04-20 | P01 | PASINS01 | Mecánica | 22 | 7.8 | 3.1 | 0.8 | 11.7 | 53.2 | No | 6 | 4 | 500058 | PM01 | CM - Sensor temperatura aire TS4591 | 1004770 | 175 | 90
2026-W16 | 2026-04-20 | P01 | PASINS01 | Eléctrica | 20 | 6.7 | 3.1 | 0.2 | 10 | 50 | No | 7 | 4 | 500189 | PM01 | CM - Switch gear SAG 630 A, 6.9 Kv, 31.5 kA | 1006872 | 197.8 | 90
2026-W16 | 2026-04-20 | P01 | PASINS01 | Instrumentación | 28 | 8.2 | 4.5 | 1.4 | 14.1 | 50.4 | No | 2 | 4 | 500059 | PM01 | CM - Mezclador floculante | 1004998 | 119.7 | 90
2026-W16 | 2026-04-20 | P01 | PAHMEC01 | Mecánica | 36 | 16.5 | 6.8 | 1.5 | 24.8 | 68.9 | No | 2 | 3 | 500121 | PM01 | CM - Calefactor eléctrico edificio | 1005288 | 148.5 | 90
2026-W16 | 2026-04-20 | P01 | PAHMEC01 | Eléctrica | 38 | 13.2 | 6.8 | 1.6 | 21.6 | 56.8 | No | 2 | 2 | 500083 | PM02 | PM - Válvula control descarga agua filtrado HV4824 |  | 66.2 | 90
2026-W16 | 2026-04-20 | P01 | PAHMEC01 | Instrumentación | 37 | 12.5 | 4.8 | 1.7 | 19 | 51.4 | No | 6 | 3 | 500027 | PM02 | PM - Válvula control aceite XV4883 |  | 106.3 | 90
2026-W16 | 2026-04-20 | P01 | PAHELE01 | Mecánica | 28 | 10.8 | 4 | 2.2 | 17 | 60.7 | No | 6 | 1 | 500013 | PM02 | PM - Válvula control drenaje pulpa HV1006 |  | 157.3 | 90
2026-W16 | 2026-04-20 | P01 | PAHELE01 | Eléctrica | 23 | 10.5 | 6.2 | 2.1 | 18.8 | 81.7 | No | 4 | 4 | 500190 | PM01 | CM - Colector polvo horno fundición | 1002764 | 149.3 | 90
2026-W16 | 2026-04-20 | P01 | PAHELE01 | Instrumentación | 22 | 7.6 | 6.6 | 2.2 | 16.4 | 74.5 | No | 2 | 2 | 500080 | PM02 | PM - Válvula control aire soplado HV4658 | 1001482 | 99.7 | 90
2026-W16 | 2026-04-20 | P01 | PAHINS01 | Mecánica | 33 | 4.1 | 7.4 | 1.8 | 13.3 | 40.3 | No | 7 | 2 | 500089 | PM02 | PM - Transmisor presión salida sol barren PIT3241 | 1000452 | 50.4 | 90
2026-W16 | 2026-04-20 | P01 | PAHINS01 | Eléctrica | 21 | 5.3 | 4.1 | 1.6 | 11 | 52.4 | No | 5 | 1 | 500172 | PM02 | PM - Tablero de comunicación |  | 66.3 | 90
2026-W16 | 2026-04-20 | P01 | PAHINS01 | Instrumentación | 24 | 8.9 | 7.1 | 0.3 | 16.3 | 67.9 | No | 7 | 1 | 500120 | PM01 | CM - Transmisor presión salida sol barren PIT3241 |  | 105.2 | 90
2026-W16 | 2026-04-20 | P02 | PASMEC01 | Mecánica | 19 | 8.2 | 5.3 | 0.6 | 14.1 | 74.2 | No | 5 | 2 | 500057 | PM01 | CM - Bomba rotativa aceite PU0510 |  | 188.5 | 90
2026-W16 | 2026-04-20 | P02 | PASMEC01 | Eléctrica | 31 | 13.8 | 8.8 | 0.3 | 22.9 | 73.9 | No | 7 | 1 | 500007 | PM02 | PM - Transmisor vibración VT0020A |  | 38.8 | 90
2026-W16 | 2026-04-20 | P02 | PASMEC01 | Instrumentación | 16 | 4 | 4.2 | 1 | 9.2 | 57.5 | No | 2 | 3 | 500119 | PM01 | CM - Calefactor eléctrico HE0137 | 1003063 | 87.5 | 90
2026-W16 | 2026-04-20 | P02 | PASELE01 | Mecánica | 16 | 6.4 | 2.9 | 0.9 | 10.2 | 63.7 | No | 5 | 1 | 500083 | PM02 | PM - Válvula control descarga agua filtrado HV4824 |  | 196.7 | 90
2026-W16 | 2026-04-20 | P02 | PASELE01 | Eléctrica | 36 | 7.4 | 5.8 | 2.7 | 15.9 | 44.2 | No | 6 | 4 | 500072 | PM02 | PM - Válvula control flujo entrada agua rechazo FV3576 | 1000113 | 32.3 | 90
2026-W16 | 2026-04-20 | P02 | PASELE01 | Instrumentación | 25 | 7.1 | 5.4 | 0.3 | 12.8 | 51.2 | No | 7 | 2 | 500012 | PM02 | PM - Gabinete PLC horno fundición 1 |  | 34 | 90
2026-W16 | 2026-04-20 | P02 | PASINS01 | Mecánica | 36 | 17.5 | 2.4 | 0.3 | 20.2 | 56.1 | No | 7 | 1 | 500075 | PM02 | PM - Switch posición giro rastras ZS4377D | 1000140 | 166.8 | 90
2026-W16 | 2026-04-20 | P02 | PASINS01 | Eléctrica | 24 | 9.4 | 4 | 1.2 | 14.6 | 60.8 | No | 4 | 4 | 500145 | PM02 | PM - Transmisor presion agua PT0404 |  | 136.2 | 90
2026-W16 | 2026-04-20 | P02 | PASINS01 | Instrumentación | 22 | 5.5 | 4.8 | 1.7 | 12 | 54.5 | No | 7 | 2 | 500005 | PM02 | PM - Válvula control succión agua fresca HV7808 |  | 88.3 | 90
2026-W16 | 2026-04-20 | P02 | PAHMEC01 | Mecánica | 32 | 9.1 | 5.1 | 3.2 | 17.4 | 54.4 | No | 3 | 2 | 500078 | PM02 | PM - Unidad aire acondicionado |  | 66.2 | 90
2026-W16 | 2026-04-20 | P02 | PAHMEC01 | Eléctrica | 30 | 9.4 | 6.2 | 0.3 | 15.9 | 53 | No | 6 | 4 | 500120 | PM01 | CM - Transmisor presión salida sol barren PIT3241 |  | 76.1 | 90
2026-W16 | 2026-04-20 | P02 | PAHMEC01 | Instrumentación | 30 | 7.2 | 5.3 | 3 | 15.5 | 51.7 | No | 4 | 4 | 500062 | PM01 | CM - Transmisor nivel lechada cal LIT5271 | 1003561 | 79 | 90
2026-W16 | 2026-04-20 | P02 | PAHELE01 | Mecánica | 19 | 7.7 | 2.1 | 1.6 | 11.4 | 60 | No | 7 | 2 | 500019 | PM02 | PM - Transmisor nivel lechada cal LIT5314 |  | 76.5 | 90
2026-W16 | 2026-04-20 | P02 | PAHELE01 | Eléctrica | 20 | 6.8 | 2 | 0.8 | 9.6 | 48 | No | 3 | 1 | 500123 | PM01 | CM - Válvula control flujo sol barren FV5601 | 1002607 | 183.3 | 90
2026-W16 | 2026-04-20 | P02 | PAHELE01 | Instrumentación | 33 | 9.4 | 9.7 | 0.5 | 19.6 | 59.4 | No | 5 | 4 | 500167 | PM02 | PM - Sensor temperatura TE0802 |  | 161.1 | 90
2026-W16 | 2026-04-20 | P02 | PAHINS01 | Mecánica | 38 | 17.7 | 3.8 | 2.3 | 23.8 | 62.6 | No | 5 | 3 | 500141 | PM02 | PM - Lava ojos emergencia |  | 178.8 | 90
2026-W16 | 2026-04-20 | P02 | PAHINS01 | Eléctrica | 27 | 5.7 | 6.2 | 2.2 | 14.1 | 52.2 | No | 3 | 3 | 500135 | PM02 | PM - Compresor de aire neumático |  | 56 | 90
2026-W16 | 2026-04-20 | P02 | PAHINS01 | Instrumentación | 28 | 10.6 | 4.1 | 1 | 15.7 | 56.1 | No | 2 | 3 | 500014 | PM02 | PM - Válvula control descarga agua filtrado HV4824 |  | 104.1 | 90
2026-W16 | 2026-04-21 | M01 | PASMEC01 | Mecánica | 39 | 14.1 | 3.2 | 0 | 17.3 | 44.4 | No | 5 | 1 | 500128 | PM01 | CM - Transmisor nivel solución barren LIT2787 |  | 184.9 | 90
2026-W16 | 2026-04-21 | M01 | PASMEC01 | Eléctrica | 26 | 11.7 | 3.5 | 0.9 | 16.1 | 61.9 | No | 5 | 2 | 500148 | PM02 | PM - Válvula control descarga sol rica HV2810 |  | 166 | 90
2026-W16 | 2026-04-21 | M01 | PASMEC01 | Instrumentación | 25 | 5.2 | 4.6 | 1.9 | 11.7 | 46.8 | No | 2 | 4 | 500082 | PM02 | PM - Válvula control agua filtrada HV4568B |  | 134 | 90
2026-W16 | 2026-04-21 | M01 | PASELE01 | Mecánica | 24 | 8.9 | 2.8 | 2 | 13.7 | 57.1 | No | 2 | 1 | 500105 | PM02 | PM - Tablero SCI |  | 70.7 | 90
2026-W16 | 2026-04-21 | M01 | PASELE01 | Eléctrica | 23 | 11.2 | 6.2 | 2.2 | 19.6 | 85.2 | No | 5 | 1 | 500062 | PM01 | CM - Transmisor nivel lechada cal LIT5271 | 1006161 | 49.8 | 90
2026-W16 | 2026-04-21 | M01 | PASELE01 | Instrumentación | 35 | 13.6 | 6.5 | 3.2 | 23.3 | 66.6 | No | 3 | 2 | 500066 | PM02 | PM - Hidrante/ Grifos FH0137 |  | 36.5 | 90
2026-W16 | 2026-04-21 | M01 | PASINS01 | Mecánica | 30 | 9.4 | 5.2 | 0.6 | 15.2 | 50.7 | No | 2 | 1 | 500069 | PM02 | PM - Puerta Taller Camiones |  | 101.2 | 90
2026-W16 | 2026-04-21 | M01 | PASINS01 | Eléctrica | 35 | 13.2 | 6.6 | 3.4 | 23.2 | 66.3 | No | 2 | 1 | 500169 | PM02 | PM - Celosía XM0114 |  | 152.8 | 90
2026-W16 | 2026-04-21 | M01 | PASINS01 | Instrumentación | 24 | 10.6 | 3.9 | 1.4 | 15.9 | 66.2 | No | 2 | 1 | 500169 | PM02 | PM - Celosía XM0114 |  | 116.4 | 90
2026-W16 | 2026-04-21 | M01 | PAHMEC01 | Mecánica | 17 | 6.4 | 3.7 | 1.1 | 11.2 | 65.9 | No | 4 | 2 | 500177 | PM01 | CM - Intercambiador calor por aire CQ0007 | 1007163 | 117.3 | 90
2026-W16 | 2026-04-21 | M01 | PAHMEC01 | Eléctrica | 30 | 4.8 | 2.3 | 0.7 | 7.8 | 26 | No | 4 | 3 | 500131 | PM01 | CM - Calefactor eléctrico estanque HE0012 | 1005923 | 196.3 | 90
2026-W16 | 2026-04-21 | M01 | PAHMEC01 | Instrumentación | 27 | 9.4 | 3.6 | 1.1 | 14.1 | 52.2 | No | 5 | 2 | 500002 | PM02 | PM - Chute carbónHO0068 |  | 52.1 | 90
2026-W16 | 2026-04-21 | M01 | PAHELE01 | Mecánica | 31 | 5.3 | 6.2 | 2.4 | 13.9 | 44.8 | No | 6 | 1 | 500074 | PM02 | PM - Transmisor presión agua potable PIT7025 |  | 196 | 90
2026-W16 | 2026-04-21 | M01 | PAHELE01 | Eléctrica | 28 | 13.4 | 6.3 | 0.7 | 20.4 | 72.9 | No | 7 | 1 | 500154 | PM02 | PM - Lava ojos emergencia |  | 99.6 | 90
2026-W16 | 2026-04-21 | M01 | PAHELE01 | Instrumentación | 16 | 6.1 | 4.4 | 1 | 11.5 | 71.9 | No | 3 | 1 | 500039 | PM02 | PM - Chute carbónHO0068 | 1001519 | 179.6 | 90
2026-W16 | 2026-04-21 | M01 | PAHINS01 | Mecánica | 25 | 4.1 | 3.8 | 0.9 | 8.8 | 35.2 | No | 5 | 4 | 500020 | PM02 | PM - Cajón (Futuro) |  | 196.3 | 90
2026-W16 | 2026-04-21 | M01 | PAHINS01 | Eléctrica | 21 | 5.7 | 2.6 | 1.1 | 9.4 | 44.8 | No | 6 | 1 | 500182 | PM01 | CM - Transmisor nivel agua potable LIT0060 | 1004499 | 130.9 | 90
2026-W16 | 2026-04-21 | M01 | PAHINS01 | Instrumentación | 24 | 4 | 4.6 | 2.4 | 11 | 45.8 | No | 3 | 4 | 500084 | PM02 | PM - Motor eléctrico HY0001M1 | 1005534 | 177.8 | 90
2026-W16 | 2026-04-21 | M02 | PASMEC01 | Mecánica | 30 | 9.1 | 6 | 2.4 | 17.5 | 58.3 | No | 4 | 4 | 500053 | PM01 | CM - Indicador presión aceite hidráulico PI4895E | 1005254 | 84.5 | 90
2026-W16 | 2026-04-21 | M02 | PASMEC01 | Eléctrica | 16 | 5.9 | 3.2 | 0.5 | 9.6 | 60 | No | 4 | 1 | 500027 | PM02 | PM - Válvula control aceite XV4883 |  | 163.5 | 90
2026-W16 | 2026-04-21 | M02 | PASMEC01 | Instrumentación | 37 | 15.3 | 5.9 | 2.2 | 23.4 | 63.2 | No | 2 | 3 | 500096 | PM02 | PM - Válvula control descarga agua fresca HV7819 |  | 78.8 | 90
2026-W16 | 2026-04-21 | M02 | PASELE01 | Mecánica | 27 | 9.8 | 6.3 | 1.8 | 17.9 | 66.3 | No | 6 | 3 | 500187 | PM01 | CM - Pesómetro SC0001 | 1002556 | 79.5 | 90
2026-W16 | 2026-04-21 | M02 | PASELE01 | Eléctrica | 34 | 11.1 | 5.3 | 1.5 | 17.9 | 52.6 | No | 7 | 4 | 500002 | PM02 | PM - Chute carbónHO0068 |  | 101.9 | 90
2026-W16 | 2026-04-21 | M02 | PASELE01 | Instrumentación | 30 | 13.1 | 8 | 0.7 | 21.8 | 72.7 | No | 5 | 4 | 500065 | PM02 | PM - Muestreador alimentación filtros | 1006105 | 153 | 90
2026-W16 | 2026-04-21 | M02 | PASINS01 | Mecánica | 39 | 12.8 | 6.9 | 3.3 | 23 | 59 | No | 6 | 1 | 500010 | PM02 | PM - Tablero SCI |  | 78.2 | 90
2026-W16 | 2026-04-21 | M02 | PASINS01 | Eléctrica | 39 | 7.2 | 5.3 | 0.5 | 13 | 33.3 | No | 5 | 2 | 500059 | PM01 | CM - Mezclador floculante |  | 73.8 | 90
2026-W16 | 2026-04-21 | M02 | PASINS01 | Instrumentación | 36 | 15.5 | 6.5 | 2.6 | 24.6 | 68.3 | No | 7 | 3 | 500048 | PM01 | CM - Válvula control flujo aire secado FV4662 | 1001272 | 75.1 | 90
2026-W16 | 2026-04-21 | M02 | PAHMEC01 | Mecánica | 20 | 7.9 | 3.5 | 2 | 13.4 | 67 | No | 4 | 1 | 500022 | PM02 | PM - Unidad re-potabilizadora agua |  | 65.1 | 90
2026-W16 | 2026-04-21 | M02 | PAHMEC01 | Eléctrica | 34 | 9.2 | 5.1 | 0.9 | 15.2 | 44.7 | No | 4 | 1 | 500158 | PM02 | PM - Válvula control flujo sol barren FV5601 |  | 84.9 | 90
2026-W16 | 2026-04-21 | M02 | PAHMEC01 | Instrumentación | 26 | 7.9 | 4.7 | 2.6 | 15.2 | 58.5 | No | 5 | 1 | 500028 | PM02 | PM - Válvula control succión agua fresca HV7808 |  | 29.8 | 90
2026-W16 | 2026-04-21 | M02 | PAHELE01 | Mecánica | 30 | 9.1 | 8.3 | 0.8 | 18.2 | 60.7 | No | 6 | 2 | 500045 | PM02 | PM - Transmisor presión agua potable PIT7025 |  | 169.1 | 90
2026-W16 | 2026-04-21 | M02 | PAHELE01 | Eléctrica | 38 | 4 | 7.8 | 0.7 | 12.5 | 32.9 | No | 5 | 1 | 500049 | PM01 | CM - Válvula control alimenta pulpa HV1501K | 1000083 | 137.6 | 90
2026-W16 | 2026-04-21 | M02 | PAHELE01 | Instrumentación | 25 | 8.8 | 4.2 | 1 | 14 | 56 | No | 6 | 1 | 500129 | PM01 | CM - Gabinete control Chancador Primario | 1003145 | 116.7 | 90
2026-W16 | 2026-04-21 | M02 | PAHINS01 | Mecánica | 28 | 6.6 | 2.6 | 0.2 | 9.4 | 33.6 | No | 6 | 2 | 500046 | PM02 | PM - Gabinete servidor core switch 1 y commun | 1006406 | 190.3 | 90
2026-W16 | 2026-04-21 | M02 | PAHINS01 | Eléctrica | 21 | 5.7 | 2.4 | 1.3 | 9.4 | 44.8 | No | 2 | 1 | 500176 | PM01 | CM - Válvula control succión nitrato plomo HV2962 | 1004938 | 135.7 | 90
2026-W16 | 2026-04-21 | M02 | PAHINS01 | Instrumentación | 35 | 13.9 | 5.6 | 1.8 | 21.3 | 60.9 | No | 6 | 4 | 500114 | PM01 | CM - Transmisor vibración VT0020A |  | 130.4 | 90
2026-W16 | 2026-04-21 | P01 | PASMEC01 | Mecánica | 37 | 13.2 | 7.3 | 2.9 | 23.4 | 63.2 | No | 4 | 2 | 500178 | PM01 | CM - Sensor temperatura TE0802 | 1001365 | 156.1 | 90
2026-W16 | 2026-04-21 | P01 | PASMEC01 | Eléctrica | 21 | 5.6 | 4.9 | 1.9 | 12.4 | 59 | No | 5 | 2 | 500127 | PM01 | CM - Válvula control succión agua filtrado HV4810 |  | 160.2 | 90
2026-W16 | 2026-04-21 | P01 | PASMEC01 | Instrumentación | 37 | 4.9 | 7.3 | 0.5 | 12.7 | 34.3 | No | 2 | 3 | 500111 | PM02 | PM - Servidor secundario |  | 166.1 | 90
2026-W16 | 2026-04-21 | P01 | PASELE01 | Mecánica | 23 | 4.9 | 4.9 | 0.8 | 10.6 | 46.1 | No | 6 | 1 | 500093 | PM02 | PM - Sensor temperatura horno TE3533 |  | 117.5 | 90
2026-W16 | 2026-04-21 | P01 | PASELE01 | Eléctrica | 34 | 5.2 | 3.3 | 0.3 | 8.8 | 25.9 | No | 5 | 4 | 500155 | PM02 | PM - Válvula control salida precapa HV3102 | 1005368 | 168 | 90
2026-W16 | 2026-04-21 | P01 | PASELE01 | Instrumentación | 18 | 4.4 | 4.2 | 1.2 | 9.8 | 54.4 | No | 4 | 4 | 500092 | PM02 | PM - Bomba precipitado |  | 140.1 | 90
2026-W16 | 2026-04-21 | P01 | PASINS01 | Mecánica | 23 | 7.7 | 3.9 | 0.2 | 11.8 | 51.3 | No | 3 | 2 | 500121 | PM01 | CM - Calefactor eléctrico edificio | 1004018 | 109.1 | 90
2026-W16 | 2026-04-21 | P01 | PASINS01 | Eléctrica | 22 | 8.9 | 4 | 1.2 | 14.1 | 64.1 | No | 5 | 1 | 500168 | PM02 | PM - Gabinete RIO |  | 69.9 | 90
2026-W16 | 2026-04-21 | P01 | PASINS01 | Instrumentación | 18 | 6.4 | 3.3 | 1.5 | 11.2 | 62.2 | No | 4 | 1 | 500151 | PM02 | PM - Válvula control flujo entrada agua rechazo FV3576 | 1005556 | 127.8 | 90
2026-W16 | 2026-04-21 | P01 | PAHMEC01 | Mecánica | 35 | 15.7 | 9.6 | 0.9 | 26.2 | 74.9 | No | 7 | 4 | 500047 | PM01 | CM - Indicador presión agua PI0251 | 1002785 | 152.9 | 90
2026-W16 | 2026-04-21 | P01 | PAHMEC01 | Eléctrica | 25 | 12.4 | 4.9 | 2.1 | 19.4 | 77.6 | No | 6 | 3 | 500110 | PM02 | PM - Válvula control entrada pulpa HV1706 |  | 177.3 | 90
2026-W16 | 2026-04-21 | P01 | PAHMEC01 | Instrumentación | 27 | 10.1 | 5.4 | 2 | 17.5 | 64.8 | No | 5 | 2 | 500176 | PM01 | CM - Válvula control succión nitrato plomo HV2962 |  | 37.4 | 90
2026-W16 | 2026-04-21 | P01 | PAHELE01 | Mecánica | 24 | 7.8 | 5.1 | 0.2 | 13.1 | 54.6 | No | 4 | 4 | 500061 | PM01 | CM - Transmisor presión aceite PIT4875 | 1003902 | 78 | 90
2026-W16 | 2026-04-21 | P01 | PAHELE01 | Eléctrica | 28 | 6.8 | 2.6 | 0.5 | 9.9 | 35.4 | No | 3 | 3 | 500058 | PM01 | CM - Sensor temperatura aire TS4591 | 1001552 | 171.7 | 90
2026-W16 | 2026-04-21 | P01 | PAHELE01 | Instrumentación | 39 | 10.4 | 9.2 | 1.6 | 21.2 | 54.4 | No | 3 | 4 | 500082 | PM02 | PM - Válvula control agua filtrada HV4568B |  | 157.5 | 90
2026-W16 | 2026-04-21 | P01 | PAHINS01 | Mecánica | 29 | 7.6 | 4.8 | 0.5 | 12.9 | 44.5 | No | 3 | 1 | 500138 | PM02 | PM - Motor eléctrico HY0036M1 |  | 144.8 | 90
2026-W16 | 2026-04-21 | P01 | PAHINS01 | Eléctrica | 23 | 8.4 | 2.3 | 0.1 | 10.8 | 47 | No | 6 | 1 | 500127 | PM01 | CM - Válvula control succión agua filtrado HV4810 |  | 189.5 | 90
2026-W16 | 2026-04-21 | P01 | PAHINS01 | Instrumentación | 33 | 6.9 | 7.8 | 0 | 14.7 | 44.5 | No | 3 | 3 | 500187 | PM01 | CM - Pesómetro SC0001 | 1006648 | 162.9 | 90
2026-W16 | 2026-04-21 | P02 | PASMEC01 | Mecánica | 34 | 13.3 | 9.2 | 1.5 | 24 | 70.6 | No | 4 | 1 | 500174 | PM02 | PM - Bomba precipitado |  | 187.7 | 90
2026-W16 | 2026-04-21 | P02 | PASMEC01 | Eléctrica | 21 | 9.4 | 5.3 | 0.7 | 15.4 | 73.3 | No | 2 | 3 | 500102 | PM02 | PM - Ciclo convertidor potencia MI0001SE |  | 32.9 | 90
2026-W16 | 2026-04-21 | P02 | PASMEC01 | Instrumentación | 21 | 6.5 | 5.7 | 1.4 | 13.6 | 64.8 | No | 4 | 2 | 500120 | PM01 | CM - Transmisor presión salida sol barren PIT3241 |  | 47.1 | 90
2026-W16 | 2026-04-21 | P02 | PASELE01 | Mecánica | 23 | 9.6 | 3.2 | 1.7 | 14.5 | 63 | No | 6 | 2 | 500008 | PM02 | PM - Bomba precipitado | 1000490 | 113.8 | 90
2026-W16 | 2026-04-21 | P02 | PASELE01 | Eléctrica | 19 | 8.7 | 4.3 | 1.4 | 14.4 | 75.8 | No | 5 | 4 | 500073 | PM02 | PM - Válvula control sol barren a estanque HV3266 |  | 126.5 | 90
2026-W16 | 2026-04-21 | P02 | PASELE01 | Instrumentación | 25 | 8.4 | 6.5 | 1.8 | 16.7 | 66.8 | No | 2 | 3 | 500107 | PM02 | PM - Gabinete manguera y equipo contraincendios HH0105 |  | 47.1 | 90
2026-W16 | 2026-04-21 | P02 | PASINS01 | Mecánica | 35 | 9.3 | 4.4 | 2.6 | 16.3 | 46.6 | No | 4 | 2 | 500113 | PM01 | CM - Puerta enrollable Molienda |  | 155.8 | 90
2026-W16 | 2026-04-21 | P02 | PASINS01 | Eléctrica | 25 | 5.7 | 6.4 | 1.9 | 14 | 56 | No | 4 | 4 | 500097 | PM02 | PM - Gabinete RIO |  | 29 | 90
2026-W16 | 2026-04-21 | P02 | PASINS01 | Instrumentación | 29 | 8.3 | 4.1 | 1.9 | 14.3 | 49.3 | No | 6 | 2 | 500137 | PM02 | PM - Hidrante/ Grifos FH0138 | 1003259 | 184.9 | 90
2026-W16 | 2026-04-21 | P02 | PAHMEC01 | Mecánica | 34 | 4.7 | 6.3 | 0.3 | 11.3 | 33.2 | No | 5 | 1 | 500085 | PM02 | PM - Gabinete servidor core switch 1 y commun |  | 130.3 | 90
2026-W16 | 2026-04-21 | P02 | PAHMEC01 | Eléctrica | 20 | 9.4 | 5.6 | 1.4 | 16.4 | 82 | No | 4 | 1 | 500058 | PM01 | CM - Sensor temperatura aire TS4591 | 1005308 | 166.1 | 90
2026-W16 | 2026-04-21 | P02 | PAHMEC01 | Instrumentación | 33 | 6.8 | 4.6 | 0.7 | 12.1 | 36.7 | No | 4 | 3 | 500168 | PM02 | PM - Gabinete RIO |  | 133.1 | 90
2026-W16 | 2026-04-21 | P02 | PAHELE01 | Mecánica | 17 | 8.3 | 4.9 | 1 | 14.2 | 83.5 | No | 6 | 3 | 500107 | PM02 | PM - Gabinete manguera y equipo contraincendios HH0105 |  | 35 | 90
2026-W16 | 2026-04-21 | P02 | PAHELE01 | Eléctrica | 39 | 4.5 | 7.5 | 3 | 15 | 38.5 | No | 2 | 1 | 500092 | PM02 | PM - Bomba precipitado |  | 118.1 | 90
2026-W16 | 2026-04-21 | P02 | PAHELE01 | Instrumentación | 23 | 4.7 | 3.6 | 0 | 8.3 | 36.1 | No | 2 | 3 | 500063 | PM01 | CM - Válvula control entrada solucion barren FV2314 | 1005259 | 169.3 | 90
2026-W16 | 2026-04-21 | P02 | PAHINS01 | Mecánica | 18 | 4.3 | 4.2 | 1.5 | 10 | 55.6 | No | 5 | 2 | 500186 | PM01 | CM - Tablero distribución instrumentación | 1006916 | 177.4 | 90
2026-W16 | 2026-04-21 | P02 | PAHINS01 | Eléctrica | 23 | 7.9 | 3.8 | 1.7 | 13.4 | 58.3 | No | 6 | 1 | 500135 | PM02 | PM - Compresor de aire neumático | 1004918 | 117.7 | 90
2026-W16 | 2026-04-21 | P02 | PAHINS01 | Instrumentación | 35 | 11.4 | 7.3 | 3.3 | 22 | 62.9 | No | 2 | 3 | 500088 | PM02 | PM - Transmisor presión entrada sol precipitado PIT3017 |  | 84.6 | 90
2026-W16 | 2026-04-22 | M01 | PASMEC01 | Mecánica | 22 | 8.1 | 4.8 | 1.8 | 14.7 | 66.8 | No | 7 | 3 | 500129 | PM01 | CM - Gabinete control Chancador Primario |  | 54.9 | 90
2026-W16 | 2026-04-22 | M01 | PASMEC01 | Eléctrica | 33 | 6.2 | 9.3 | 2.5 | 18 | 54.5 | No | 6 | 4 | 500166 | PM02 | PM - Bomba muestreo pulpa relaves PU0267 |  | 142.4 | 90
2026-W16 | 2026-04-22 | M01 | PASMEC01 | Instrumentación | 30 | 10.9 | 2 | 0.1 | 13 | 43.3 | No | 2 | 3 | 500129 | PM01 | CM - Gabinete control Chancador Primario |  | 144.4 | 90
2026-W16 | 2026-04-22 | M01 | PASELE01 | Mecánica | 29 | 8.5 | 6.6 | 1.5 | 16.6 | 57.2 | No | 6 | 1 | 500085 | PM02 | PM - Gabinete servidor core switch 1 y commun | 1000645 | 49.2 | 90
2026-W16 | 2026-04-22 | M01 | PASELE01 | Eléctrica | 37 | 17.9 | 5.8 | 3.5 | 27.2 | 73.5 | No | 2 | 1 | 500092 | PM02 | PM - Bomba precipitado |  | 106.6 | 90
2026-W16 | 2026-04-22 | M01 | PASELE01 | Instrumentación | 22 | 6.6 | 3.1 | 0.9 | 10.6 | 48.2 | No | 2 | 1 | 500109 | PM02 | PM - Variador frecuencia 3620PU0239M1VF |  | 154 | 90
2026-W16 | 2026-04-22 | M01 | PASINS01 | Mecánica | 39 | 6.5 | 7.7 | 3.5 | 17.7 | 45.4 | No | 4 | 2 | 500083 | PM02 | PM - Válvula control descarga agua filtrado HV4824 | 1004165 | 105.1 | 90
2026-W16 | 2026-04-22 | M01 | PASINS01 | Eléctrica | 36 | 8 | 7.2 | 1.1 | 16.3 | 45.3 | No | 2 | 1 | 500129 | PM01 | CM - Gabinete control Chancador Primario | 1003516 | 20.5 | 90
2026-W16 | 2026-04-22 | M01 | PASINS01 | Instrumentación | 19 | 5 | 5.6 | 0.7 | 11.3 | 59.5 | No | 7 | 3 | 500027 | PM02 | PM - Válvula control aceite XV4883 |  | 94.5 | 90
2026-W16 | 2026-04-22 | M01 | PAHMEC01 | Mecánica | 38 | 7.2 | 4.7 | 3.2 | 15.1 | 39.7 | No | 5 | 2 | 500023 | PM02 | PM - Válvula control entrada aire FV1804 |  | 157.6 | 90
2026-W16 | 2026-04-22 | M01 | PAHMEC01 | Eléctrica | 33 | 13.9 | 6.7 | 0.3 | 20.9 | 63.3 | No | 5 | 1 | 500061 | PM01 | CM - Transmisor presión aceite PIT4875 | 1006196 | 34 | 90
2026-W16 | 2026-04-22 | M01 | PAHMEC01 | Instrumentación | 28 | 8.2 | 3.9 | 1.8 | 13.9 | 49.6 | No | 4 | 2 | 500088 | PM02 | PM - Transmisor presión entrada sol precipitado PIT3017 |  | 92.1 | 90
2026-W16 | 2026-04-22 | M01 | PAHELE01 | Mecánica | 34 | 10 | 6.3 | 0.8 | 17.1 | 50.3 | No | 4 | 1 | 500055 | PM01 | CM - Baliza YL3612 | 1000567 | 194.8 | 90
2026-W16 | 2026-04-22 | M01 | PAHELE01 | Eléctrica | 34 | 9.8 | 4.3 | 3.2 | 17.3 | 50.9 | No | 6 | 3 | 500096 | PM02 | PM - Válvula control descarga agua fresca HV7819 |  | 35.1 | 90
2026-W16 | 2026-04-22 | M01 | PAHELE01 | Instrumentación | 31 | 9.7 | 7.9 | 2.1 | 19.7 | 63.5 | No | 2 | 3 | 500110 | PM02 | PM - Válvula control entrada pulpa HV1706 |  | 82.4 | 90
2026-W16 | 2026-04-22 | M01 | PAHINS01 | Mecánica | 21 | 5.4 | 5.4 | 1.3 | 12.1 | 57.6 | No | 4 | 1 | 500106 | PM02 | PM - Válvula control succión ayuda filtrante HV3281 |  | 59.1 | 90
2026-W16 | 2026-04-22 | M01 | PAHINS01 | Eléctrica | 37 | 17.5 | 10.9 | 2.9 | 31.3 | 84.6 | No | 4 | 4 | 500080 | PM02 | PM - Válvula control aire soplado HV4658 |  | 173.6 | 90
2026-W16 | 2026-04-22 | M01 | PAHINS01 | Instrumentación | 23 | 6.6 | 2.9 | 1.3 | 10.8 | 47 | No | 4 | 2 | 500061 | PM01 | CM - Transmisor presión aceite PIT4875 | 1007155 | 31.1 | 90
2026-W16 | 2026-04-22 | M02 | PASMEC01 | Mecánica | 16 | 4.7 | 4.7 | 0.8 | 10.2 | 63.7 | No | 6 | 1 | 500109 | PM02 | PM - Variador frecuencia 3620PU0239M1VF |  | 183.3 | 90
2026-W16 | 2026-04-22 | M02 | PASMEC01 | Eléctrica | 32 | 10.6 | 3.6 | 2.4 | 16.6 | 51.9 | No | 3 | 2 | 500150 | PM02 | PM - Válvula control entrada sol precipitado HV3185 |  | 119.5 | 90
2026-W16 | 2026-04-22 | M02 | PASMEC01 | Instrumentación | 24 | 4.9 | 2.4 | 0.8 | 8.1 | 33.8 | No | 3 | 4 | 500005 | PM02 | PM - Válvula control succión agua fresca HV7808 |  | 45.4 | 90
2026-W16 | 2026-04-22 | M02 | PASELE01 | Mecánica | 32 | 11.9 | 5.9 | 0.5 | 18.3 | 57.2 | No | 7 | 4 | 500076 | PM02 | PM - Cajón (Futuro) |  | 87.5 | 90
2026-W16 | 2026-04-22 | M02 | PASELE01 | Eléctrica | 33 | 9.3 | 8.9 | 1.3 | 19.5 | 59.1 | No | 5 | 2 | 500158 | PM02 | PM - Válvula control flujo sol barren FV5601 |  | 80.9 | 90
2026-W16 | 2026-04-22 | M02 | PASELE01 | Instrumentación | 30 | 7 | 2.3 | 2.5 | 11.8 | 39.3 | No | 5 | 3 | 500029 | PM02 | PM - Switch posición ZS0038A |  | 127.3 | 90
2026-W16 | 2026-04-22 | M02 | PASINS01 | Mecánica | 39 | 16.3 | 7.6 | 2.6 | 26.5 | 67.9 | No | 5 | 1 | 500087 | PM02 | PM - Línea agua sell 3700-5476-AA1A-3"-WGS-ET | 1003630 | 123.4 | 90
2026-W16 | 2026-04-22 | M02 | PASINS01 | Eléctrica | 24 | 12 | 2.6 | 2 | 16.6 | 69.2 | No | 4 | 3 | 500116 | PM01 | CM - Transmisor nivel hidrox sodio LIT3467 | 1006039 | 89.8 | 90
2026-W16 | 2026-04-22 | M02 | PASINS01 | Instrumentación | 34 | 10.9 | 9.7 | 2.3 | 22.9 | 67.4 | No | 6 | 2 | 500045 | PM02 | PM - Transmisor presión agua potable PIT7025 | 1003688 | 148.1 | 90
2026-W16 | 2026-04-22 | M02 | PAHMEC01 | Mecánica | 36 | 17.2 | 5.8 | 1.3 | 24.3 | 67.5 | No | 4 | 4 | 500085 | PM02 | PM - Gabinete servidor core switch 1 y commun |  | 113.5 | 90
2026-W16 | 2026-04-22 | M02 | PAHMEC01 | Eléctrica | 35 | 14.8 | 5.8 | 2.9 | 23.5 | 67.1 | No | 5 | 2 | 500134 | PM02 | PM - Intercambiador calor por aire CQ0007 |  | 33.3 | 90
2026-W16 | 2026-04-22 | M02 | PAHMEC01 | Instrumentación | 37 | 9.3 | 7.7 | 0.2 | 17.2 | 46.5 | No | 6 | 2 | 500094 | PM02 | PM - Switch baja presión descarga fluido térmico PSL3498 | 1004385 | 70.9 | 90
2026-W16 | 2026-04-22 | M02 | PAHELE01 | Mecánica | 30 | 12.8 | 6.8 | 0.6 | 20.2 | 67.3 | No | 5 | 1 | 500158 | PM02 | PM - Válvula control flujo sol barren FV5601 | 1006379 | 169.3 | 90
2026-W16 | 2026-04-22 | M02 | PAHELE01 | Eléctrica | 17 | 5 | 4.7 | 0.1 | 9.8 | 57.6 | No | 5 | 2 | 500160 | PM02 | PM - Gabinete control Chancador Primario |  | 172.9 | 90
2026-W16 | 2026-04-22 | M02 | PAHELE01 | Instrumentación | 36 | 8.4 | 5.9 | 0.4 | 14.7 | 40.8 | No | 2 | 2 | 500122 | PM01 | CM - Carro mantención regeneración carbon | 1003068 | 122.5 | 90
2026-W16 | 2026-04-22 | M02 | PAHINS01 | Mecánica | 21 | 10.5 | 2 | 0.1 | 12.6 | 60 | No | 6 | 2 | 500115 | PM01 | CM - Bomba vacío retorta | 1001737 | 136.6 | 90
2026-W16 | 2026-04-22 | M02 | PAHINS01 | Eléctrica | 17 | 5.1 | 3.3 | 1.2 | 9.6 | 56.5 | No | 6 | 3 | 500028 | PM02 | PM - Válvula control succión agua fresca HV7808 |  | 62.8 | 90
2026-W16 | 2026-04-22 | M02 | PAHINS01 | Instrumentación | 16 | 4.5 | 4.4 | 0.2 | 9.1 | 56.9 | No | 6 | 1 | 500167 | PM02 | PM - Sensor temperatura TE0802 | 1006902 | 149.6 | 90
2026-W16 | 2026-04-22 | P01 | PASMEC01 | Mecánica | 37 | 4.9 | 2.3 | 0.6 | 7.8 | 21.1 | No | 7 | 3 | 500127 | PM01 | CM - Válvula control succión agua filtrado HV4810 | 1003983 | 53.1 | 90
2026-W16 | 2026-04-22 | P01 | PASMEC01 | Eléctrica | 35 | 4.9 | 5.8 | 3 | 13.7 | 39.1 | No | 7 | 3 | 500126 | PM01 | CM - Válvula control salida carbon descargado HV3394 |  | 190.1 | 90
2026-W16 | 2026-04-22 | P01 | PASMEC01 | Instrumentación | 30 | 7.4 | 7.4 | 1.6 | 16.4 | 54.7 | No | 7 | 2 | 500072 | PM02 | PM - Válvula control flujo entrada agua rechazo FV3576 |  | 40.1 | 90
2026-W16 | 2026-04-22 | P01 | PASELE01 | Mecánica | 16 | 5.5 | 4.6 | 1.1 | 11.2 | 70 | No | 5 | 4 | 500137 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 86 | 90
2026-W16 | 2026-04-22 | P01 | PASELE01 | Eléctrica | 24 | 11.8 | 2.1 | 2.3 | 16.2 | 67.5 | No | 3 | 4 | 500190 | PM01 | CM - Colector polvo horno fundición |  | 21.8 | 90
2026-W16 | 2026-04-22 | P01 | PASELE01 | Instrumentación | 37 | 18.2 | 10.8 | 0.6 | 29.6 | 80 | No | 2 | 3 | 500074 | PM02 | PM - Transmisor presión agua potable PIT7025 |  | 58.9 | 90
2026-W16 | 2026-04-22 | P01 | PASINS01 | Mecánica | 18 | 7.7 | 2.6 | 1.7 | 12 | 66.7 | No | 2 | 2 | 500157 | PM02 | PM - Tablero distribución instrumentación |  | 172.5 | 90
2026-W16 | 2026-04-22 | P01 | PASINS01 | Eléctrica | 31 | 7.2 | 3.8 | 1.7 | 12.7 | 41 | No | 3 | 2 | 500141 | PM02 | PM - Lava ojos emergencia |  | 191.6 | 90
2026-W16 | 2026-04-22 | P01 | PASINS01 | Instrumentación | 29 | 10.6 | 3.6 | 1.3 | 15.5 | 53.4 | No | 3 | 4 | 500162 | PM02 | PM - Tecle bomba sumergible lixiviación | 1000239 | 179.2 | 90
2026-W16 | 2026-04-22 | P01 | PAHMEC01 | Mecánica | 38 | 7.8 | 4.9 | 1.4 | 14.1 | 37.1 | No | 7 | 3 | 500048 | PM01 | CM - Válvula control flujo aire secado FV4662 | 1004928 | 37.8 | 90
2026-W16 | 2026-04-22 | P01 | PAHMEC01 | Eléctrica | 22 | 8.7 | 4.5 | 1 | 14.2 | 64.5 | No | 2 | 4 | 500061 | PM01 | CM - Transmisor presión aceite PIT4875 | 1002688 | 97 | 90
2026-W16 | 2026-04-22 | P01 | PAHMEC01 | Instrumentación | 35 | 17.2 | 5.1 | 0.7 | 23 | 65.7 | No | 5 | 3 | 500088 | PM02 | PM - Transmisor presión entrada sol precipitado PIT3017 |  | 51.5 | 90
2026-W16 | 2026-04-22 | P01 | PAHELE01 | Mecánica | 33 | 5.9 | 7.2 | 0.5 | 13.6 | 41.2 | No | 6 | 3 | 500071 | PM02 | PM - Calefactor eléctrico estanque HE0112 | 1004401 | 121.7 | 90
2026-W16 | 2026-04-22 | P01 | PAHELE01 | Eléctrica | 18 | 6.9 | 2.1 | 1.1 | 10.1 | 56.1 | No | 5 | 3 | 500007 | PM02 | PM - Transmisor vibración VT0020A |  | 64.3 | 90
2026-W16 | 2026-04-22 | P01 | PAHELE01 | Instrumentación | 36 | 7.9 | 9 | 1 | 17.9 | 49.7 | No | 5 | 4 | 500103 | PM02 | PM - Tablero SCI |  | 195.3 | 90
2026-W16 | 2026-04-22 | P01 | PAHINS01 | Mecánica | 36 | 12.4 | 7.4 | 2 | 21.8 | 60.6 | No | 5 | 4 | 500062 | PM01 | CM - Transmisor nivel lechada cal LIT5271 |  | 141.4 | 90
2026-W16 | 2026-04-22 | P01 | PAHINS01 | Eléctrica | 32 | 10.4 | 8.7 | 3 | 22.1 | 69.1 | No | 3 | 4 | 500025 | PM02 | PM - Válvula control succión agua filtrada HV4771A |  | 68.9 | 90
2026-W16 | 2026-04-22 | P01 | PAHINS01 | Instrumentación | 30 | 13 | 6.6 | 2.5 | 22.1 | 73.7 | No | 5 | 3 | 500131 | PM01 | CM - Calefactor eléctrico estanque HE0012 | 1003701 | 69.1 | 90
2026-W16 | 2026-04-22 | P02 | PASMEC01 | Mecánica | 34 | 15.1 | 9.2 | 1 | 25.3 | 74.4 | No | 6 | 3 | 500160 | PM02 | PM - Gabinete control Chancador Primario |  | 84.5 | 90
2026-W16 | 2026-04-22 | P02 | PASMEC01 | Eléctrica | 33 | 16.1 | 7.5 | 1.3 | 24.9 | 75.5 | No | 5 | 2 | 500144 | PM02 | PM - Motor eléctrico PU0516M1 | 1006812 | 84.1 | 90
2026-W16 | 2026-04-22 | P02 | PASMEC01 | Instrumentación | 28 | 12.6 | 7.2 | 0.4 | 20.2 | 72.1 | No | 3 | 1 | 500073 | PM02 | PM - Válvula control sol barren a estanque HV3266 |  | 58.6 | 90
2026-W16 | 2026-04-22 | P02 | PASELE01 | Mecánica | 31 | 7.8 | 5.4 | 0.6 | 13.8 | 44.5 | No | 3 | 4 | 500065 | PM02 | PM - Muestreador alimentación filtros |  | 56.2 | 90
2026-W16 | 2026-04-22 | P02 | PASELE01 | Eléctrica | 30 | 8.1 | 6 | 2.5 | 16.6 | 55.3 | No | 7 | 3 | 500086 | PM02 | PM - Sensor nivel refrigerante LE0177 |  | 164.4 | 90
2026-W16 | 2026-04-22 | P02 | PASELE01 | Instrumentación | 28 | 5.7 | 3.4 | 1.5 | 10.6 | 37.9 | No | 4 | 2 | 500108 | PM02 | PM - Motor eléctrico HY0036M1 |  | 98.6 | 90
2026-W16 | 2026-04-22 | P02 | PASINS01 | Mecánica | 31 | 12.4 | 6.1 | 0.6 | 19.1 | 61.6 | No | 3 | 4 | 500157 | PM02 | PM - Tablero distribución instrumentación | 1005058 | 143.3 | 90
2026-W16 | 2026-04-22 | P02 | PASINS01 | Eléctrica | 38 | 13.8 | 2.4 | 0.3 | 16.5 | 43.4 | No | 2 | 3 | 500169 | PM02 | PM - Celosía XM0114 |  | 38.9 | 90
2026-W16 | 2026-04-22 | P02 | PASINS01 | Instrumentación | 22 | 5.2 | 6 | 0.9 | 12.1 | 55 | No | 5 | 3 | 500131 | PM01 | CM - Calefactor eléctrico estanque HE0012 | 1002990 | 172.6 | 90
2026-W16 | 2026-04-22 | P02 | PAHMEC01 | Mecánica | 23 | 8.6 | 4 | 1.5 | 14.1 | 61.3 | No | 7 | 4 | 500030 | PM02 | PM - Indicador nivel solución LI5563 |  | 188.8 | 90
2026-W16 | 2026-04-22 | P02 | PAHMEC01 | Eléctrica | 28 | 12.1 | 3.5 | 1.3 | 16.9 | 60.4 | No | 6 | 1 | 500146 | PM02 | PM - Válvula control alimenta pulpa HV1501C |  | 81.3 | 90
2026-W16 | 2026-04-22 | P02 | PAHMEC01 | Instrumentación | 31 | 5.1 | 2.8 | 2.3 | 10.2 | 32.9 | No | 3 | 1 | 500048 | PM01 | CM - Válvula control flujo aire secado FV4662 | 1003720 | 87 | 90
2026-W16 | 2026-04-22 | P02 | PAHELE01 | Mecánica | 31 | 12.8 | 3.9 | 0.1 | 16.8 | 54.2 | No | 6 | 1 | 500022 | PM02 | PM - Unidad re-potabilizadora agua |  | 83.1 | 90
2026-W16 | 2026-04-22 | P02 | PAHELE01 | Eléctrica | 25 | 4.9 | 4.6 | 1.3 | 10.8 | 43.2 | No | 7 | 4 | 500185 | PM01 | CM - Motor eléctrico HY0036M1 |  | 135.7 | 90
2026-W16 | 2026-04-22 | P02 | PAHELE01 | Instrumentación | 31 | 7.4 | 7.5 | 0.6 | 15.5 | 50 | No | 2 | 1 | 500079 | PM02 | PM - Gabinete RIO | 1002873 | 164.8 | 90
2026-W16 | 2026-04-22 | P02 | PAHINS01 | Mecánica | 30 | 8.4 | 3.3 | 1.7 | 13.4 | 44.7 | No | 6 | 2 | 500049 | PM01 | CM - Válvula control alimenta pulpa HV1501K | 1006978 | 115.8 | 90
2026-W16 | 2026-04-22 | P02 | PAHINS01 | Eléctrica | 26 | 11.5 | 6.2 | 2.1 | 19.8 | 76.2 | No | 6 | 4 | 500077 | PM02 | PM - Válvula control entrada solucion barren FV2314 |  | 89.7 | 90
2026-W16 | 2026-04-22 | P02 | PAHINS01 | Instrumentación | 18 | 6.1 | 3 | 0.8 | 9.9 | 55 | No | 7 | 2 | 500079 | PM02 | PM - Gabinete RIO |  | 28.3 | 90
2026-W16 | 2026-04-23 | M01 | PASMEC01 | Mecánica | 32 | 14.4 | 9.1 | 1.1 | 24.6 | 76.9 | No | 7 | 2 | 500123 | PM01 | CM - Válvula control flujo sol barren FV5601 | 1002371 | 95.9 | 90
2026-W16 | 2026-04-23 | M01 | PASMEC01 | Eléctrica | 21 | 10.4 | 3.9 | 0.6 | 14.9 | 71 | No | 7 | 4 | 500083 | PM02 | PM - Válvula control descarga agua filtrado HV4824 | 1000206 | 91.4 | 90
2026-W16 | 2026-04-23 | M01 | PASMEC01 | Instrumentación | 21 | 4.5 | 3.4 | 2 | 9.9 | 47.1 | No | 2 | 3 | 500064 | PM01 | CM - Válvula control drenaje relaves alimentación HV4602 | 1007095 | 153.7 | 90
2026-W16 | 2026-04-23 | M01 | PASELE01 | Mecánica | 32 | 4.1 | 5.9 | 1.8 | 11.8 | 36.9 | No | 2 | 3 | 500062 | PM01 | CM - Transmisor nivel lechada cal LIT5271 | 1006004 | 110.8 | 90
2026-W16 | 2026-04-23 | M01 | PASELE01 | Eléctrica | 22 | 7.8 | 3 | 1.4 | 12.2 | 55.5 | No | 7 | 1 | 500075 | PM02 | PM - Switch posición giro rastras ZS4377D |  | 35.4 | 90
2026-W16 | 2026-04-23 | M01 | PASELE01 | Instrumentación | 24 | 5.5 | 6.8 | 0.1 | 12.4 | 51.7 | No | 3 | 3 | 500107 | PM02 | PM - Gabinete manguera y equipo contraincendios HH0105 |  | 76.4 | 90
2026-W16 | 2026-04-23 | M01 | PASINS01 | Mecánica | 34 | 16.2 | 8.2 | 2.4 | 26.8 | 78.8 | No | 6 | 4 | 500158 | PM02 | PM - Válvula control flujo sol barren FV5601 |  | 41.3 | 90
2026-W16 | 2026-04-23 | M01 | PASINS01 | Eléctrica | 33 | 15.2 | 5.5 | 0.8 | 21.5 | 65.2 | No | 5 | 4 | 500062 | PM01 | CM - Transmisor nivel lechada cal LIT5271 |  | 148.9 | 90
2026-W16 | 2026-04-23 | M01 | PASINS01 | Instrumentación | 27 | 7 | 7.2 | 1.6 | 15.8 | 58.5 | No | 3 | 2 | 500137 | PM02 | PM - Hidrante/ Grifos FH0138 | 1020032 | 150.8 | 90
2026-W16 | 2026-04-23 | M01 | PAHMEC01 | Mecánica | 25 | 7.7 | 5.6 | 0.7 | 14 | 56 | No | 5 | 2 | 500061 | PM01 | CM - Transmisor presión aceite PIT4875 | 1005168 | 152.1 | 90
2026-W16 | 2026-04-23 | M01 | PAHMEC01 | Eléctrica | 32 | 6.8 | 2.8 | 0.5 | 10.1 | 31.6 | No | 2 | 2 | 500153 | PM02 | PM - Sistema Spray Grasa Engranaje - Molino SAG |  | 150.6 | 90
2026-W16 | 2026-04-23 | M01 | PAHMEC01 | Instrumentación | 22 | 6.4 | 2.8 | 1.3 | 10.5 | 47.7 | No | 4 | 3 | 500058 | PM01 | CM - Sensor temperatura aire TS4591 |  | 151.2 | 90
2026-W16 | 2026-04-23 | M01 | PAHELE01 | Mecánica | 23 | 11.4 | 4.1 | 2 | 17.5 | 76.1 | No | 7 | 4 | 500173 | PM02 | PM - Bomba agua sello |  | 170.5 | 90
2026-W16 | 2026-04-23 | M01 | PAHELE01 | Eléctrica | 38 | 9.2 | 2.3 | 0.7 | 12.2 | 32.1 | No | 7 | 3 | 500058 | PM01 | CM - Sensor temperatura aire TS4591 |  | 55 | 90
2026-W16 | 2026-04-23 | M01 | PAHELE01 | Instrumentación | 17 | 7.2 | 3.8 | 1.6 | 12.6 | 74.1 | No | 4 | 3 | 500099 | PM02 | PM - Indicador presión agua PI0251 |  | 153 | 90
2026-W16 | 2026-04-23 | M01 | PAHINS01 | Mecánica | 27 | 13.4 | 4.6 | 1.7 | 19.7 | 73 | No | 2 | 3 | 500192 | PM01 | CM - Calefactor eléctrico edificio |  | 128.2 | 90
2026-W16 | 2026-04-23 | M01 | PAHINS01 | Eléctrica | 18 | 5.6 | 3.8 | 1.2 | 10.6 | 58.9 | No | 6 | 2 | 500059 | PM01 | CM - Mezclador floculante | 1001289 | 173.7 | 90
2026-W16 | 2026-04-23 | M01 | PAHINS01 | Instrumentación | 36 | 4.9 | 7.5 | 0.8 | 13.2 | 36.7 | No | 7 | 1 | 500127 | PM01 | CM - Válvula control succión agua filtrado HV4810 |  | 192.2 | 90
2026-W16 | 2026-04-23 | M02 | PASMEC01 | Mecánica | 31 | 4.3 | 6.1 | 2.3 | 12.7 | 41 | No | 3 | 2 | 500157 | PM02 | PM - Tablero distribución instrumentación | 1003472 | 190.1 | 90
2026-W16 | 2026-04-23 | M02 | PASMEC01 | Eléctrica | 18 | 6.7 | 2 | 0.6 | 9.3 | 51.7 | No | 6 | 4 | 500131 | PM01 | CM - Calefactor eléctrico estanque HE0012 | 1004954 | 194.8 | 90
2026-W16 | 2026-04-23 | M02 | PASMEC01 | Instrumentación | 38 | 16.6 | 4.9 | 2.2 | 23.7 | 62.4 | No | 2 | 4 | 500036 | PM02 | PM - Colector polvo horno fundición |  | 142 | 90
2026-W16 | 2026-04-23 | M02 | PASELE01 | Mecánica | 32 | 14 | 6.7 | 2 | 22.7 | 70.9 | No | 5 | 2 | 500062 | PM01 | CM - Transmisor nivel lechada cal LIT5271 | 1001706 | 186.9 | 90
2026-W16 | 2026-04-23 | M02 | PASELE01 | Eléctrica | 26 | 4.2 | 2.8 | 1.8 | 8.8 | 33.8 | No | 6 | 4 | 500189 | PM01 | CM - Switch gear SAG 630 A, 6.9 Kv, 31.5 kA |  | 40.8 | 90
2026-W16 | 2026-04-23 | M02 | PASELE01 | Instrumentación | 16 | 6 | 2.3 | 0.3 | 8.6 | 53.8 | No | 2 | 1 | 500054 | PM01 | CM - Intercambiador calor calentamiento | 1000616 | 151.8 | 90
2026-W16 | 2026-04-23 | M02 | PASINS01 | Mecánica | 31 | 11.8 | 4.5 | 1.8 | 18.1 | 58.4 | No | 6 | 2 | 500059 | PM01 | CM - Mezclador floculante | 1020145 | 138.6 | 90
2026-W16 | 2026-04-23 | M02 | PASINS01 | Eléctrica | 18 | 6.9 | 2.8 | 1.2 | 10.9 | 60.6 | No | 7 | 4 | 500187 | PM01 | CM - Pesómetro SC0001 |  | 52.9 | 90
2026-W16 | 2026-04-23 | M02 | PASINS01 | Instrumentación | 22 | 8.6 | 2.2 | 0.4 | 11.2 | 50.9 | No | 6 | 2 | 500138 | PM02 | PM - Motor eléctrico HY0036M1 |  | 189 | 90
2026-W16 | 2026-04-23 | M02 | PAHMEC01 | Mecánica | 31 | 7.6 | 4.9 | 1.1 | 13.6 | 43.9 | No | 4 | 1 | 500080 | PM02 | PM - Válvula control aire soplado HV4658 | 1002562 | 28 | 90
2026-W16 | 2026-04-23 | M02 | PAHMEC01 | Eléctrica | 24 | 10.5 | 7.1 | 2 | 19.6 | 81.7 | No | 6 | 3 | 500178 | PM01 | CM - Sensor temperatura TE0802 | 1000858 | 73.2 | 90
2026-W16 | 2026-04-23 | M02 | PAHMEC01 | Instrumentación | 32 | 9.2 | 5.8 | 2.9 | 17.9 | 55.9 | No | 6 | 3 | 500023 | PM02 | PM - Válvula control entrada aire FV1804 |  | 176.2 | 90
2026-W16 | 2026-04-23 | M02 | PAHELE01 | Mecánica | 35 | 5.4 | 3.1 | 2.4 | 10.9 | 31.1 | No | 6 | 3 | 500113 | PM01 | CM - Puerta enrollable Molienda | 1003878 | 162.4 | 90
2026-W16 | 2026-04-23 | M02 | PAHELE01 | Eléctrica | 26 | 6.7 | 3.5 | 1 | 11.2 | 43.1 | No | 5 | 2 | 500166 | PM02 | PM - Bomba muestreo pulpa relaves PU0267 |  | 87 | 90
2026-W16 | 2026-04-23 | M02 | PAHELE01 | Instrumentación | 19 | 8.9 | 4.4 | 1.4 | 14.7 | 77.4 | No | 3 | 4 | 500061 | PM01 | CM - Transmisor presión aceite PIT4875 | 1006829 | 133.1 | 90
2026-W16 | 2026-04-23 | M02 | PAHINS01 | Mecánica | 38 | 16.8 | 4.3 | 0.1 | 21.2 | 55.8 | No | 3 | 1 | 500156 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 102.4 | 90
2026-W16 | 2026-04-23 | M02 | PAHINS01 | Eléctrica | 30 | 12.9 | 3.3 | 2.4 | 18.6 | 62 | No | 4 | 1 | 500110 | PM02 | PM - Válvula control entrada pulpa HV1706 |  | 80.4 | 90
2026-W16 | 2026-04-23 | M02 | PAHINS01 | Instrumentación | 17 | 4.7 | 4.3 | 0.7 | 9.7 | 57.1 | No | 5 | 1 | 500100 | PM02 | PM - Puerta enrollable Stockpile |  | 75.5 | 90
2026-W16 | 2026-04-23 | P01 | PASMEC01 | Mecánica | 35 | 15.8 | 8 | 2.3 | 26.1 | 74.6 | No | 3 | 2 | 500074 | PM02 | PM - Transmisor presión agua potable PIT7025 |  | 85.9 | 90
2026-W16 | 2026-04-23 | P01 | PASMEC01 | Eléctrica | 22 | 5.6 | 6.1 | 0.1 | 11.8 | 53.6 | No | 4 | 1 | 500132 | PM02 | PM - Válvula control agua sello HV2723 |  | 118.8 | 90
2026-W16 | 2026-04-23 | P01 | PASMEC01 | Instrumentación | 33 | 8.6 | 7.8 | 1.4 | 17.8 | 53.9 | No | 5 | 4 | 500119 | PM01 | CM - Calefactor eléctrico HE0137 | 1001364 | 143.6 | 90
2026-W16 | 2026-04-23 | P01 | PASELE01 | Mecánica | 16 | 5.1 | 3 | 1 | 9.1 | 56.9 | No | 7 | 4 | 500101 | PM02 | PM - Subestación unitaria |  | 83.8 | 90
2026-W16 | 2026-04-23 | P01 | PASELE01 | Eléctrica | 36 | 12.9 | 8.9 | 2.5 | 24.3 | 67.5 | No | 6 | 2 | 500161 | PM02 | PM - Unidad aire acondicionado |  | 32.9 | 90
2026-W16 | 2026-04-23 | P01 | PASELE01 | Instrumentación | 36 | 11.2 | 8.2 | 1.7 | 21.1 | 58.6 | No | 6 | 3 | 500001 | PM02 | PM - Válvula control entrada lechada cal AV1902B |  | 71.3 | 90
2026-W16 | 2026-04-23 | P01 | PASINS01 | Mecánica | 20 | 9 | 4.8 | 1.7 | 15.5 | 77.5 | No | 6 | 2 | 500022 | PM02 | PM - Unidad re-potabilizadora agua | 1004501 | 82.4 | 90
2026-W16 | 2026-04-23 | P01 | PASINS01 | Eléctrica | 17 | 4.9 | 4.1 | 1 | 10 | 58.8 | No | 2 | 3 | 500096 | PM02 | PM - Válvula control descarga agua fresca HV7819 |  | 72.4 | 90
2026-W16 | 2026-04-23 | P01 | PASINS01 | Instrumentación | 36 | 9.9 | 3.8 | 1.4 | 15.1 | 41.9 | No | 3 | 2 | 500005 | PM02 | PM - Válvula control succión agua fresca HV7808 |  | 174 | 90
2026-W16 | 2026-04-23 | P01 | PAHMEC01 | Mecánica | 24 | 7.2 | 5.8 | 0.5 | 13.5 | 56.2 | No | 2 | 2 | 500046 | PM02 | PM - Gabinete servidor core switch 1 y commun |  | 21.5 | 90
2026-W16 | 2026-04-23 | P01 | PAHMEC01 | Eléctrica | 23 | 10.7 | 3.9 | 1.3 | 15.9 | 69.1 | No | 3 | 2 | 500134 | PM02 | PM - Intercambiador calor por aire CQ0007 |  | 53.9 | 90
2026-W16 | 2026-04-23 | P01 | PAHMEC01 | Instrumentación | 22 | 8.2 | 6.1 | 0.4 | 14.7 | 66.8 | No | 3 | 3 | 500110 | PM02 | PM - Válvula control entrada pulpa HV1706 |  | 146.9 | 90
2026-W16 | 2026-04-23 | P01 | PAHELE01 | Mecánica | 26 | 5 | 7.7 | 0.7 | 13.4 | 51.5 | No | 4 | 3 | 500157 | PM02 | PM - Tablero distribución instrumentación |  | 52.9 | 90
2026-W16 | 2026-04-23 | P01 | PAHELE01 | Eléctrica | 18 | 7.7 | 3.1 | 0.6 | 11.4 | 63.3 | No | 3 | 2 | 500077 | PM02 | PM - Válvula control entrada solucion barren FV2314 |  | 100.2 | 90
2026-W16 | 2026-04-23 | P01 | PAHELE01 | Instrumentación | 19 | 5.3 | 3.6 | 0.3 | 9.2 | 48.4 | No | 6 | 3 | 500002 | PM02 | PM - Chute carbónHO0068 |  | 65.1 | 90
2026-W16 | 2026-04-23 | P01 | PAHINS01 | Mecánica | 22 | 6.7 | 4.3 | 0.4 | 11.4 | 51.8 | No | 5 | 4 | 500182 | PM01 | CM - Transmisor nivel agua potable LIT0060 |  | 123 | 90
2026-W16 | 2026-04-23 | P01 | PAHINS01 | Eléctrica | 17 | 7.9 | 4.2 | 0 | 12.1 | 71.2 | No | 3 | 2 | 500038 | PM02 | PM - Switch bajo flujo aire FSL1357A | 1003348 | 36.9 | 90
2026-W16 | 2026-04-23 | P01 | PAHINS01 | Instrumentación | 31 | 5.3 | 3.6 | 0.9 | 9.8 | 31.6 | No | 4 | 2 | 500140 | PM02 | PM - Correa retorno pebbles |  | 109.6 | 90
2026-W16 | 2026-04-23 | P02 | PASMEC01 | Mecánica | 24 | 10.8 | 2.9 | 0.6 | 14.3 | 59.6 | No | 6 | 3 | 500031 | PM02 | PM - Celosía XM0114 |  | 148.2 | 90
2026-W16 | 2026-04-23 | P02 | PASMEC01 | Eléctrica | 32 | 15.1 | 2.7 | 1.2 | 19 | 59.4 | No | 4 | 2 | 500061 | PM01 | CM - Transmisor presión aceite PIT4875 |  | 64.1 | 90
2026-W16 | 2026-04-23 | P02 | PASMEC01 | Instrumentación | 24 | 5.3 | 2.3 | 0.3 | 7.9 | 32.9 | No | 6 | 2 | 500109 | PM02 | PM - Variador frecuencia 3620PU0239M1VF |  | 119.3 | 90
2026-W16 | 2026-04-23 | P02 | PASELE01 | Mecánica | 37 | 8.6 | 3.8 | 3.2 | 15.6 | 42.2 | No | 4 | 1 | 500095 | PM02 | PM - Bomba sumidero lixiviación | 1006397 | 49.1 | 90
2026-W16 | 2026-04-23 | P02 | PASELE01 | Eléctrica | 38 | 4.7 | 7.2 | 1.8 | 13.7 | 36.1 | No | 4 | 1 | 500013 | PM02 | PM - Válvula control drenaje pulpa HV1006 | 1005108 | 66.3 | 90
2026-W16 | 2026-04-23 | P02 | PASELE01 | Instrumentación | 19 | 6.3 | 2.9 | 0.2 | 9.4 | 49.5 | No | 3 | 1 | 500187 | PM01 | CM - Pesómetro SC0001 |  | 120.5 | 90
2026-W16 | 2026-04-23 | P02 | PASINS01 | Mecánica | 19 | 4.7 | 5.2 | 0.1 | 10 | 52.6 | No | 4 | 4 | 500182 | PM01 | CM - Transmisor nivel agua potable LIT0060 | 1006143 | 198.4 | 90
2026-W16 | 2026-04-23 | P02 | PASINS01 | Eléctrica | 19 | 4.7 | 5.6 | 1.9 | 12.2 | 64.2 | No | 7 | 1 | 500048 | PM01 | CM - Válvula control flujo aire secado FV4662 | 1006742 | 175.7 | 90
2026-W16 | 2026-04-23 | P02 | PASINS01 | Instrumentación | 26 | 11.2 | 6.8 | 0.8 | 18.8 | 72.3 | No | 2 | 2 | 500166 | PM02 | PM - Bomba muestreo pulpa relaves PU0267 | 1000920 | 177.3 | 90
2026-W16 | 2026-04-23 | P02 | PAHMEC01 | Mecánica | 17 | 8.2 | 4.1 | 1.5 | 13.8 | 81.2 | No | 5 | 1 | 500114 | PM01 | CM - Transmisor vibración VT0020A |  | 43.6 | 90
2026-W16 | 2026-04-23 | P02 | PAHMEC01 | Eléctrica | 16 | 7.4 | 2.3 | 0.6 | 10.3 | 64.4 | No | 2 | 4 | 500100 | PM02 | PM - Puerta enrollable Stockpile | 1006351 | 166 | 90
2026-W16 | 2026-04-23 | P02 | PAHMEC01 | Instrumentación | 30 | 13.9 | 2.4 | 0.4 | 16.7 | 55.7 | No | 5 | 1 | 500186 | PM01 | CM - Tablero distribución instrumentación | 1005328 | 131.4 | 90
2026-W16 | 2026-04-23 | P02 | PAHELE01 | Mecánica | 39 | 10.2 | 7.7 | 2.9 | 20.8 | 53.3 | No | 6 | 2 | 500085 | PM02 | PM - Gabinete servidor core switch 1 y commun |  | 107.1 | 90
2026-W16 | 2026-04-23 | P02 | PAHELE01 | Eléctrica | 38 | 10.4 | 4.1 | 1.7 | 16.2 | 42.6 | No | 5 | 2 | 500083 | PM02 | PM - Válvula control descarga agua filtrado HV4824 |  | 173.1 | 90
2026-W16 | 2026-04-23 | P02 | PAHELE01 | Instrumentación | 31 | 4.3 | 8.8 | 1.6 | 14.7 | 47.4 | No | 5 | 3 | 500061 | PM01 | CM - Transmisor presión aceite PIT4875 | 1000019 | 126.6 | 90
2026-W16 | 2026-04-23 | P02 | PAHINS01 | Mecánica | 23 | 7.6 | 6.7 | 1.5 | 15.8 | 68.7 | No | 6 | 3 | 500171 | PM02 | PM - Switch bajo nivel aceite LSL0253 |  | 96.2 | 90
2026-W16 | 2026-04-23 | P02 | PAHINS01 | Eléctrica | 35 | 14.4 | 4.5 | 0.1 | 19 | 54.3 | No | 3 | 1 | 500061 | PM01 | CM - Transmisor presión aceite PIT4875 | 1005396 | 50.5 | 90
2026-W16 | 2026-04-23 | P02 | PAHINS01 | Instrumentación | 26 | 4.3 | 7.3 | 2.1 | 13.7 | 52.7 | No | 5 | 2 | 500048 | PM01 | CM - Válvula control flujo aire secado FV4662 | 1006040 | 30.5 | 90
2026-W16 | 2026-04-24 | M01 | PASMEC01 | Mecánica | 16 | 5.8 | 3.2 | 0.9 | 9.9 | 61.9 | No | 5 | 1 | 500139 | PM02 | PM - Hidrante/ Grifos FH0136 |  | 29.4 | 90
2026-W16 | 2026-04-24 | M01 | PASMEC01 | Eléctrica | 34 | 12.3 | 6.7 | 0.4 | 19.4 | 57.1 | No | 7 | 1 | 500183 | PM01 | CM - Estanque separador TK0054 | 1003263 | 55.8 | 90
2026-W16 | 2026-04-24 | M01 | PASMEC01 | Instrumentación | 16 | 4.6 | 3.1 | 1.1 | 8.8 | 55 | No | 3 | 3 | 500059 | PM01 | CM - Mezclador floculante | 1005781 | 96.1 | 90
2026-W16 | 2026-04-24 | M01 | PASELE01 | Mecánica | 31 | 7.4 | 7.4 | 3.1 | 17.9 | 57.7 | No | 5 | 4 | 500012 | PM02 | PM - Gabinete PLC horno fundición 1 |  | 116 | 90
2026-W16 | 2026-04-24 | M01 | PASELE01 | Eléctrica | 16 | 4.4 | 3.2 | 0 | 7.6 | 47.5 | No | 7 | 3 | 500113 | PM01 | CM - Puerta enrollable Molienda | 1006041 | 106.9 | 90
2026-W16 | 2026-04-24 | M01 | PASELE01 | Instrumentación | 25 | 11.2 | 5.3 | 1.1 | 17.6 | 70.4 | No | 7 | 2 | 500014 | PM02 | PM - Válvula control descarga agua filtrado HV4824 | 1003979 | 129.7 | 90
2026-W16 | 2026-04-24 | M01 | PASINS01 | Mecánica | 23 | 10.7 | 6.9 | 0.4 | 18 | 78.3 | No | 4 | 2 | 500189 | PM01 | CM - Switch gear SAG 630 A, 6.9 Kv, 31.5 kA | 1005687 | 45.8 | 90
2026-W16 | 2026-04-24 | M01 | PASINS01 | Eléctrica | 31 | 14.4 | 6 | 1.8 | 22.2 | 71.6 | No | 3 | 3 | 500182 | PM01 | CM - Transmisor nivel agua potable LIT0060 | 1006615 | 130.3 | 90
2026-W16 | 2026-04-24 | M01 | PASINS01 | Instrumentación | 20 | 8 | 2.4 | 0.9 | 11.3 | 56.5 | No | 4 | 4 | 500075 | PM02 | PM - Switch posición giro rastras ZS4377D | 1003717 | 135.9 | 90
2026-W16 | 2026-04-24 | M01 | PAHMEC01 | Mecánica | 17 | 5.5 | 3.5 | 1.1 | 10.1 | 59.4 | No | 5 | 4 | 500087 | PM02 | PM - Línea agua sell 3700-5476-AA1A-3"-WGS-ET |  | 63.5 | 90
2026-W16 | 2026-04-24 | M01 | PAHMEC01 | Eléctrica | 25 | 6.4 | 5.3 | 1.4 | 13.1 | 52.4 | No | 6 | 4 | 500089 | PM02 | PM - Transmisor presión salida sol barren PIT3241 |  | 90.9 | 90
2026-W16 | 2026-04-24 | M01 | PAHMEC01 | Instrumentación | 31 | 7.7 | 8.2 | 0.7 | 16.6 | 53.5 | No | 7 | 1 | 500150 | PM02 | PM - Válvula control entrada sol precipitado HV3185 | 1007232 | 22.8 | 90
2026-W16 | 2026-04-24 | M01 | PAHELE01 | Mecánica | 25 | 8 | 6.8 | 1.1 | 15.9 | 63.6 | No | 2 | 1 | 500071 | PM02 | PM - Calefactor eléctrico estanque HE0112 |  | 154 | 90
2026-W16 | 2026-04-24 | M01 | PAHELE01 | Eléctrica | 36 | 6.3 | 2.2 | 0.3 | 8.8 | 24.4 | No | 2 | 2 | 500143 | PM02 | PM - Transmisor nivel solución barren LIT2787 |  | 195 | 90
2026-W16 | 2026-04-24 | M01 | PAHELE01 | Instrumentación | 29 | 5.3 | 6.2 | 0.2 | 11.7 | 40.3 | No | 4 | 2 | 500150 | PM02 | PM - Válvula control entrada sol precipitado HV3185 |  | 106.7 | 90
2026-W16 | 2026-04-24 | M01 | PAHINS01 | Mecánica | 32 | 14.2 | 8.4 | 1.6 | 24.2 | 75.6 | No | 6 | 2 | 500175 | PM01 | CM - Válvula control aceite XV0279 | 1002478 | 52.3 | 90
2026-W16 | 2026-04-24 | M01 | PAHINS01 | Eléctrica | 39 | 4 | 6.5 | 1.9 | 12.4 | 31.8 | No | 2 | 1 | 500142 | PM02 | PM - Calefactor eléctrico estanque HE0113 | 1004530 | 27.2 | 90
2026-W16 | 2026-04-24 | M01 | PAHINS01 | Instrumentación | 30 | 5.9 | 6.4 | 0.3 | 12.6 | 42 | No | 7 | 2 | 500112 | PM02 | PM - Hidrante/ Grifos FH0129 | 1007227 | 72.5 | 90
2026-W16 | 2026-04-24 | M02 | PASMEC01 | Mecánica | 20 | 4.8 | 5.8 | 1.4 | 12 | 60 | No | 2 | 3 | 500043 | PM02 | PM - Sirena YA3453 |  | 109.9 | 90
2026-W16 | 2026-04-24 | M02 | PASMEC01 | Eléctrica | 38 | 15.4 | 4.5 | 3.4 | 23.3 | 61.3 | No | 7 | 1 | 500040 | PM02 | PM - Mesa rodillos |  | 109 | 90
2026-W16 | 2026-04-24 | M02 | PASMEC01 | Instrumentación | 31 | 4 | 8.5 | 1 | 13.5 | 43.5 | No | 2 | 1 | 500166 | PM02 | PM - Bomba muestreo pulpa relaves PU0267 |  | 61.1 | 90
2026-W16 | 2026-04-24 | M02 | PASELE01 | Mecánica | 23 | 5.6 | 6.4 | 2.1 | 14.1 | 61.3 | No | 3 | 1 | 500184 | PM01 | CM - Válvula control descarga agua filtrado HV4812 |  | 154.7 | 90
2026-W16 | 2026-04-24 | M02 | PASELE01 | Eléctrica | 31 | 8.6 | 3.2 | 1.6 | 13.4 | 43.2 | No | 6 | 4 | 500013 | PM02 | PM - Válvula control drenaje pulpa HV1006 | 1000805 | 149.7 | 90
2026-W16 | 2026-04-24 | M02 | PASELE01 | Instrumentación | 29 | 6.2 | 4.3 | 0.9 | 11.4 | 39.3 | No | 4 | 2 | 500177 | PM01 | CM - Intercambiador calor por aire CQ0007 | 1003876 | 162 | 90
2026-W16 | 2026-04-24 | M02 | PASINS01 | Mecánica | 29 | 5.4 | 4.8 | 0.4 | 10.6 | 36.6 | No | 7 | 4 | 500182 | PM01 | CM - Transmisor nivel agua potable LIT0060 | 1002924 | 176.8 | 90
2026-W16 | 2026-04-24 | M02 | PASINS01 | Eléctrica | 17 | 7.5 | 3.7 | 1.2 | 12.4 | 72.9 | No | 3 | 2 | 500168 | PM02 | PM - Gabinete RIO |  | 198.7 | 90
2026-W16 | 2026-04-24 | M02 | PASINS01 | Instrumentación | 28 | 11.3 | 3.4 | 0.2 | 14.9 | 53.2 | No | 3 | 3 | 500148 | PM02 | PM - Válvula control descarga sol rica HV2810 | 1004392 | 157.4 | 90
2026-W16 | 2026-04-24 | M02 | PAHMEC01 | Mecánica | 26 | 5.7 | 5.3 | 0.9 | 11.9 | 45.8 | No | 2 | 3 | 500158 | PM02 | PM - Válvula control flujo sol barren FV5601 |  | 53.1 | 90
2026-W16 | 2026-04-24 | M02 | PAHMEC01 | Eléctrica | 22 | 9.7 | 5.6 | 2.1 | 17.4 | 79.1 | No | 3 | 1 | 500084 | PM02 | PM - Motor eléctrico HY0001M1 |  | 87.6 | 90
2026-W16 | 2026-04-24 | M02 | PAHMEC01 | Instrumentación | 25 | 8.2 | 2.5 | 1.5 | 12.2 | 48.8 | No | 6 | 4 | 500144 | PM02 | PM - Motor eléctrico PU0516M1 |  | 54.3 | 90
2026-W16 | 2026-04-24 | M02 | PAHELE01 | Mecánica | 28 | 9.3 | 7.7 | 0.7 | 17.7 | 63.2 | No | 2 | 3 | 500007 | PM02 | PM - Transmisor vibración VT0020A |  | 67.4 | 90
2026-W16 | 2026-04-24 | M02 | PAHELE01 | Eléctrica | 28 | 8.1 | 5.6 | 2.2 | 15.9 | 56.8 | No | 3 | 3 | 500187 | PM01 | CM - Pesómetro SC0001 |  | 199.2 | 90
2026-W16 | 2026-04-24 | M02 | PAHELE01 | Instrumentación | 25 | 6.2 | 3.6 | 1.9 | 11.7 | 46.8 | No | 2 | 1 | 500176 | PM01 | CM - Válvula control succión nitrato plomo HV2962 | 1020123 | 147.6 | 90
2026-W16 | 2026-04-24 | M02 | PAHINS01 | Mecánica | 20 | 9.6 | 5 | 0.1 | 14.7 | 73.5 | No | 5 | 1 | 500088 | PM02 | PM - Transmisor presión entrada sol precipitado PIT3017 |  | 133.2 | 90
2026-W16 | 2026-04-24 | M02 | PAHINS01 | Eléctrica | 17 | 4.6 | 3.9 | 0.3 | 8.8 | 51.8 | No | 5 | 4 | 500073 | PM02 | PM - Válvula control sol barren a estanque HV3266 |  | 154.2 | 90
2026-W16 | 2026-04-24 | M02 | PAHINS01 | Instrumentación | 33 | 14.1 | 9.1 | 0 | 23.2 | 70.3 | No | 7 | 3 | 500037 | PM02 | PM - Sirena YA1151 |  | 105.2 | 90
2026-W16 | 2026-04-24 | P01 | PASMEC01 | Mecánica | 24 | 5 | 4.1 | 0.7 | 9.8 | 40.8 | No | 4 | 2 | 500119 | PM01 | CM - Calefactor eléctrico HE0137 | 1001231 | 42.2 | 90
2026-W16 | 2026-04-24 | P01 | PASMEC01 | Eléctrica | 23 | 10.8 | 4.3 | 1 | 16.1 | 70 | No | 2 | 4 | 500095 | PM02 | PM - Bomba sumidero lixiviación |  | 76.2 | 90
2026-W16 | 2026-04-24 | P01 | PASMEC01 | Instrumentación | 19 | 6.7 | 4.4 | 0.2 | 11.3 | 59.5 | No | 7 | 4 | 500110 | PM02 | PM - Válvula control entrada pulpa HV1706 |  | 64.5 | 90
2026-W16 | 2026-04-24 | P01 | PASELE01 | Mecánica | 31 | 8.6 | 6.4 | 0.7 | 15.7 | 50.6 | No | 5 | 3 | 500053 | PM01 | CM - Indicador presión aceite hidráulico PI4895E |  | 33.3 | 90
2026-W16 | 2026-04-24 | P01 | PASELE01 | Eléctrica | 37 | 16.9 | 2.1 | 3 | 22 | 59.5 | No | 5 | 1 | 500177 | PM01 | CM - Intercambiador calor por aire CQ0007 | 1006954 | 198.7 | 90
2026-W16 | 2026-04-24 | P01 | PASELE01 | Instrumentación | 32 | 9.2 | 2.9 | 0.3 | 12.4 | 38.8 | No | 4 | 4 | 500094 | PM02 | PM - Switch baja presión descarga fluido térmico PSL3498 |  | 152.7 | 90
2026-W16 | 2026-04-24 | P01 | PASINS01 | Mecánica | 27 | 8.9 | 3.7 | 0.4 | 13 | 48.1 | No | 4 | 3 | 500011 | PM02 | PM - Válvula control agua sello HV2723 |  | 43.6 | 90
2026-W16 | 2026-04-24 | P01 | PASINS01 | Eléctrica | 23 | 7.4 | 4.6 | 0.3 | 12.3 | 53.5 | No | 6 | 3 | 500071 | PM02 | PM - Calefactor eléctrico estanque HE0112 |  | 56.1 | 90
2026-W16 | 2026-04-24 | P01 | PASINS01 | Instrumentación | 36 | 12.4 | 3.4 | 0.8 | 16.6 | 46.1 | No | 4 | 2 | 500034 | PM02 | PM - Puerta enrollable Molienda |  | 114.4 | 90
2026-W16 | 2026-04-24 | P01 | PAHMEC01 | Mecánica | 34 | 8 | 4.4 | 1 | 13.4 | 39.4 | No | 4 | 3 | 500050 | PM01 | CM - Línea agua sell 3700-5476-AA1A-3"-WGS-ET | 1005002 | 79.6 | 90
2026-W16 | 2026-04-24 | P01 | PAHMEC01 | Eléctrica | 20 | 4.1 | 5.6 | 0.1 | 9.8 | 49 | No | 6 | 2 | 500160 | PM02 | PM - Gabinete control Chancador Primario | 1006629 | 122.5 | 90
2026-W16 | 2026-04-24 | P01 | PAHMEC01 | Instrumentación | 28 | 10.4 | 7.6 | 1.1 | 19.1 | 68.2 | No | 6 | 4 | 500084 | PM02 | PM - Motor eléctrico HY0001M1 |  | 112.9 | 90
2026-W16 | 2026-04-24 | P01 | PAHELE01 | Mecánica | 26 | 10.1 | 7.5 | 1.3 | 18.9 | 72.7 | No | 5 | 2 | 500126 | PM01 | CM - Válvula control salida carbon descargado HV3394 | 1000584 | 137.8 | 90
2026-W16 | 2026-04-24 | P01 | PAHELE01 | Eléctrica | 38 | 15.8 | 8.7 | 0.6 | 25.1 | 66.1 | No | 2 | 2 | 500040 | PM02 | PM - Mesa rodillos | 1001943 | 26.9 | 90
2026-W16 | 2026-04-24 | P01 | PAHELE01 | Instrumentación | 35 | 13.2 | 8.5 | 2.9 | 24.6 | 70.3 | No | 4 | 1 | 500104 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 187.6 | 90
2026-W16 | 2026-04-24 | P01 | PAHINS01 | Mecánica | 17 | 7.4 | 2.1 | 0.6 | 10.1 | 59.4 | No | 3 | 4 | 500192 | PM01 | CM - Calefactor eléctrico edificio | 1000862 | 89.5 | 90
2026-W16 | 2026-04-24 | P01 | PAHINS01 | Eléctrica | 24 | 6 | 6.2 | 1.5 | 13.7 | 57.1 | No | 6 | 1 | 500056 | PM01 | CM - Gabinete control Merril Crowe & Refinación | 1004135 | 112.8 | 90
2026-W16 | 2026-04-24 | P01 | PAHINS01 | Instrumentación | 23 | 7.9 | 4.5 | 1.6 | 14 | 60.9 | No | 3 | 3 | 500028 | PM02 | PM - Válvula control succión agua fresca HV7808 |  | 147.8 | 90
2026-W16 | 2026-04-24 | P02 | PASMEC01 | Mecánica | 37 | 6.9 | 2.4 | 0.4 | 9.7 | 26.2 | No | 2 | 1 | 500125 | PM01 | CM - Transmisor presión aceite PIT4824 | 1004132 | 156.5 | 90
2026-W16 | 2026-04-24 | P02 | PASMEC01 | Eléctrica | 32 | 12.8 | 9 | 1.4 | 23.2 | 72.5 | No | 7 | 3 | 500101 | PM02 | PM - Subestación unitaria | 1003588 | 81.8 | 90
2026-W16 | 2026-04-24 | P02 | PASMEC01 | Instrumentación | 30 | 5.6 | 5.9 | 0.6 | 12.1 | 40.3 | No | 6 | 4 | 500082 | PM02 | PM - Válvula control agua filtrada HV4568B |  | 169.7 | 90
2026-W16 | 2026-04-24 | P02 | PASELE01 | Mecánica | 21 | 4.2 | 4.8 | 0.4 | 9.4 | 44.8 | No | 3 | 2 | 500127 | PM01 | CM - Válvula control succión agua filtrado HV4810 |  | 75.8 | 90
2026-W16 | 2026-04-24 | P02 | PASELE01 | Eléctrica | 17 | 4.8 | 4.1 | 1.3 | 10.2 | 60 | No | 2 | 2 | 500120 | PM01 | CM - Transmisor presión salida sol barren PIT3241 | 1003714 | 160.6 | 90
2026-W16 | 2026-04-24 | P02 | PASELE01 | Instrumentación | 20 | 5.7 | 2.4 | 0.4 | 8.5 | 42.5 | No | 6 | 2 | 500031 | PM02 | PM - Celosía XM0114 |  | 185.2 | 90
2026-W16 | 2026-04-24 | P02 | PASINS01 | Mecánica | 22 | 7 | 4.4 | 2 | 13.4 | 60.9 | No | 4 | 3 | 500046 | PM02 | PM - Gabinete servidor core switch 1 y commun |  | 155.6 | 90
2026-W16 | 2026-04-24 | P02 | PASINS01 | Eléctrica | 16 | 7.1 | 4.7 | 1.1 | 12.9 | 80.6 | No | 2 | 3 | 500192 | PM01 | CM - Calefactor eléctrico edificio | 1001448 | 92.3 | 90
2026-W16 | 2026-04-24 | P02 | PASINS01 | Instrumentación | 36 | 9.1 | 6.5 | 1.3 | 16.9 | 46.9 | No | 5 | 1 | 500128 | PM01 | CM - Transmisor nivel solución barren LIT2787 | 1006060 | 195.5 | 90
2026-W16 | 2026-04-24 | P02 | PAHMEC01 | Mecánica | 35 | 14.4 | 8.1 | 3.4 | 25.9 | 74 | No | 4 | 2 | 500112 | PM02 | PM - Hidrante/ Grifos FH0129 | 1005463 | 157.2 | 90
2026-W16 | 2026-04-24 | P02 | PAHMEC01 | Eléctrica | 20 | 4.2 | 5.6 | 0.7 | 10.5 | 52.5 | No | 5 | 2 | 500145 | PM02 | PM - Transmisor presion agua PT0404 |  | 162.1 | 90
2026-W16 | 2026-04-24 | P02 | PAHMEC01 | Instrumentación | 25 | 9.1 | 3.8 | 0 | 12.9 | 51.6 | No | 3 | 3 | 500057 | PM01 | CM - Bomba rotativa aceite PU0510 |  | 171.7 | 90
2026-W16 | 2026-04-24 | P02 | PAHELE01 | Mecánica | 31 | 13.6 | 6 | 2.1 | 21.7 | 70 | No | 4 | 3 | 500181 | PM01 | CM - Bomba diafragma grasa PU0001 | 1000777 | 71.1 | 90
2026-W16 | 2026-04-24 | P02 | PAHELE01 | Eléctrica | 29 | 10.9 | 5.9 | 0.1 | 16.9 | 58.3 | No | 7 | 3 | 500022 | PM02 | PM - Unidad re-potabilizadora agua |  | 68.2 | 90
2026-W16 | 2026-04-24 | P02 | PAHELE01 | Instrumentación | 36 | 16.1 | 5.7 | 3.3 | 25.1 | 69.7 | No | 3 | 1 | 500176 | PM01 | CM - Válvula control succión nitrato plomo HV2962 | 1005068 | 91.8 | 90
2026-W16 | 2026-04-24 | P02 | PAHINS01 | Mecánica | 27 | 12.6 | 5.1 | 0.7 | 18.4 | 68.1 | No | 3 | 3 | 500168 | PM02 | PM - Gabinete RIO |  | 56.3 | 90
2026-W16 | 2026-04-24 | P02 | PAHINS01 | Eléctrica | 16 | 7.7 | 3.1 | 1 | 11.8 | 73.8 | No | 2 | 4 | 500106 | PM02 | PM - Válvula control succión ayuda filtrante HV3281 |  | 196.7 | 90
2026-W16 | 2026-04-24 | P02 | PAHINS01 | Instrumentación | 36 | 17 | 8.5 | 2.5 | 28 | 77.8 | No | 2 | 2 | 500063 | PM01 | CM - Válvula control entrada solucion barren FV2314 | 1002897 | 38.7 | 90
2026-W16 | 2026-04-25 | M01 | PASMEC01 | Mecánica | 38 | 18.2 | 2.2 | 3.7 | 24.1 | 63.4 | No | 7 | 2 | 500032 | PM02 | PM - Válvula control entrada cianuro sodio FV1903 |  | 167.5 | 90
2026-W16 | 2026-04-25 | M01 | PASMEC01 | Eléctrica | 20 | 5.1 | 4.4 | 1.1 | 10.6 | 53 | No | 3 | 1 | 500148 | PM02 | PM - Válvula control descarga sol rica HV2810 | 1007125 | 112.4 | 90
2026-W16 | 2026-04-25 | M01 | PASMEC01 | Instrumentación | 29 | 4.2 | 2.4 | 0.3 | 6.9 | 23.8 | No | 4 | 1 | 500082 | PM02 | PM - Válvula control agua filtrada HV4568B |  | 166.7 | 90
2026-W16 | 2026-04-25 | M01 | PASELE01 | Mecánica | 25 | 5.6 | 3.8 | 1 | 10.4 | 41.6 | No | 2 | 4 | 500191 | PM01 | CM - Calefactor eléctrico estanque HE0112 | 1003110 | 175.4 | 90
2026-W16 | 2026-04-25 | M01 | PASELE01 | Eléctrica | 29 | 9.5 | 2.9 | 0.1 | 12.5 | 43.1 | No | 6 | 2 | 500188 | PM01 | CM - Switch posición ZS1716 | 1000227 | 132.8 | 90
2026-W16 | 2026-04-25 | M01 | PASELE01 | Instrumentación | 24 | 5.5 | 3.8 | 0.2 | 9.5 | 39.6 | No | 5 | 1 | 500048 | PM01 | CM - Válvula control flujo aire secado FV4662 | 1005559 | 184 | 90
2026-W16 | 2026-04-25 | M01 | PASINS01 | Mecánica | 30 | 11.2 | 4.7 | 2 | 17.9 | 59.7 | No | 2 | 3 | 500039 | PM02 | PM - Chute carbónHO0068 |  | 60.2 | 90
2026-W16 | 2026-04-25 | M01 | PASINS01 | Eléctrica | 20 | 7.4 | 3.9 | 1.3 | 12.6 | 63 | No | 3 | 3 | 500089 | PM02 | PM - Transmisor presión salida sol barren PIT3241 |  | 158.7 | 90
2026-W16 | 2026-04-25 | M01 | PASINS01 | Instrumentación | 33 | 15.1 | 5.6 | 1.8 | 22.5 | 68.2 | No | 6 | 3 | 500141 | PM02 | PM - Lava ojos emergencia |  | 74 | 90
2026-W16 | 2026-04-25 | M01 | PAHMEC01 | Mecánica | 26 | 6.9 | 6.6 | 0.5 | 14 | 53.8 | No | 6 | 4 | 500134 | PM02 | PM - Intercambiador calor por aire CQ0007 |  | 175.6 | 90
2026-W16 | 2026-04-25 | M01 | PAHMEC01 | Eléctrica | 30 | 14.2 | 3 | 1.9 | 19.1 | 63.7 | No | 5 | 1 | 500188 | PM01 | CM - Switch posición ZS1716 | 1001631 | 41.7 | 90
2026-W16 | 2026-04-25 | M01 | PAHMEC01 | Instrumentación | 34 | 12.2 | 5.6 | 2.1 | 19.9 | 58.5 | No | 4 | 2 | 500054 | PM01 | CM - Intercambiador calor calentamiento | 1001575 | 151.3 | 90
2026-W16 | 2026-04-25 | M01 | PAHELE01 | Mecánica | 27 | 8.3 | 6.6 | 0.8 | 15.7 | 58.1 | No | 2 | 2 | 500072 | PM02 | PM - Válvula control flujo entrada agua rechazo FV3576 |  | 117.4 | 90
2026-W16 | 2026-04-25 | M01 | PAHELE01 | Eléctrica | 39 | 12.6 | 5.1 | 0.5 | 18.2 | 46.7 | No | 7 | 3 | 500160 | PM02 | PM - Gabinete control Chancador Primario |  | 114.5 | 90
2026-W16 | 2026-04-25 | M01 | PAHELE01 | Instrumentación | 28 | 13.7 | 6.4 | 2.5 | 22.6 | 80.7 | No | 7 | 1 | 500191 | PM01 | CM - Calefactor eléctrico estanque HE0112 | 1000220 | 152.3 | 90
2026-W16 | 2026-04-25 | M01 | PAHINS01 | Mecánica | 19 | 4.9 | 3.3 | 1.4 | 9.6 | 50.5 | No | 6 | 2 | 500053 | PM01 | CM - Indicador presión aceite hidráulico PI4895E | 1001667 | 64.9 | 90
2026-W16 | 2026-04-25 | M01 | PAHINS01 | Eléctrica | 26 | 5.7 | 3.8 | 1.3 | 10.8 | 41.5 | No | 6 | 4 | 500150 | PM02 | PM - Válvula control entrada sol precipitado HV3185 |  | 39.1 | 90
2026-W16 | 2026-04-25 | M01 | PAHINS01 | Instrumentación | 21 | 5.8 | 3.4 | 0.7 | 9.9 | 47.1 | No | 6 | 3 | 500166 | PM02 | PM - Bomba muestreo pulpa relaves PU0267 |  | 197.5 | 90
2026-W16 | 2026-04-25 | M02 | PASMEC01 | Mecánica | 17 | 4.6 | 2.4 | 0.8 | 7.8 | 45.9 | No | 5 | 3 | 500072 | PM02 | PM - Válvula control flujo entrada agua rechazo FV3576 |  | 196.3 | 90
2026-W16 | 2026-04-25 | M02 | PASMEC01 | Eléctrica | 22 | 8.8 | 2.5 | 1.4 | 12.7 | 57.7 | No | 5 | 2 | 500006 | PM02 | PM - Válvula control entrada sol precipitado HV3185 |  | 25.2 | 90
2026-W16 | 2026-04-25 | M02 | PASMEC01 | Instrumentación | 32 | 7.4 | 3.9 | 2.4 | 13.7 | 42.8 | No | 6 | 2 | 500099 | PM02 | PM - Indicador presión agua PI0251 |  | 86.6 | 90
2026-W16 | 2026-04-25 | M02 | PASELE01 | Mecánica | 31 | 7 | 3.1 | 2.7 | 12.8 | 41.3 | No | 5 | 2 | 500187 | PM01 | CM - Pesómetro SC0001 | 1000827 | 121 | 90
2026-W16 | 2026-04-25 | M02 | PASELE01 | Eléctrica | 20 | 6.8 | 4 | 1.3 | 12.1 | 60.5 | No | 4 | 3 | 500031 | PM02 | PM - Celosía XM0114 |  | 72 | 90
2026-W16 | 2026-04-25 | M02 | PASELE01 | Instrumentación | 39 | 6.4 | 8.2 | 3.4 | 18 | 46.2 | No | 3 | 1 | 500069 | PM02 | PM - Puerta Taller Camiones | 1003417 | 158.5 | 90
2026-W16 | 2026-04-25 | M02 | PASINS01 | Mecánica | 25 | 11.1 | 6.8 | 1.5 | 19.4 | 77.6 | No | 3 | 3 | 500127 | PM01 | CM - Válvula control succión agua filtrado HV4810 | 1004862 | 22.8 | 90
2026-W16 | 2026-04-25 | M02 | PASINS01 | Eléctrica | 35 | 5.2 | 8.1 | 0.2 | 13.5 | 38.6 | No | 2 | 2 | 500084 | PM02 | PM - Motor eléctrico HY0001M1 |  | 105.1 | 90
2026-W16 | 2026-04-25 | M02 | PASINS01 | Instrumentación | 26 | 4.1 | 4 | 0.3 | 8.4 | 32.3 | No | 5 | 4 | 500150 | PM02 | PM - Válvula control entrada sol precipitado HV3185 |  | 185.3 | 90
2026-W16 | 2026-04-25 | M02 | PAHMEC01 | Mecánica | 21 | 9.3 | 6 | 1.8 | 17.1 | 81.4 | No | 6 | 1 | 500045 | PM02 | PM - Transmisor presión agua potable PIT7025 |  | 125.5 | 90
2026-W16 | 2026-04-25 | M02 | PAHMEC01 | Eléctrica | 39 | 4.6 | 11.7 | 2.3 | 18.6 | 47.7 | No | 7 | 1 | 500114 | PM01 | CM - Transmisor vibración VT0020A | 1002548 | 82.5 | 90
2026-W16 | 2026-04-25 | M02 | PAHMEC01 | Instrumentación | 22 | 7 | 4.1 | 2.1 | 13.2 | 60 | No | 6 | 4 | 500081 | PM02 | PM - Transmisor nivel lechada cal LIT5271 | 1004577 | 132.9 | 90
2026-W16 | 2026-04-25 | M02 | PAHELE01 | Mecánica | 22 | 4.4 | 4.3 | 1.8 | 10.5 | 47.7 | No | 4 | 3 | 500129 | PM01 | CM - Gabinete control Chancador Primario | 1020181 | 32.5 | 90
2026-W16 | 2026-04-25 | M02 | PAHELE01 | Eléctrica | 16 | 6.5 | 2.7 | 0.9 | 10.1 | 63.1 | No | 2 | 4 | 500152 | PM02 | PM - Válvula control entrada pulpa HV1706 |  | 158 | 90
2026-W16 | 2026-04-25 | M02 | PAHELE01 | Instrumentación | 38 | 7.6 | 5.3 | 1 | 13.9 | 36.6 | No | 4 | 2 | 500109 | PM02 | PM - Variador frecuencia 3620PU0239M1VF |  | 92.8 | 90
2026-W16 | 2026-04-25 | M02 | PAHINS01 | Mecánica | 28 | 4.2 | 2.3 | 2.7 | 9.2 | 32.9 | No | 7 | 1 | 500072 | PM02 | PM - Válvula control flujo entrada agua rechazo FV3576 |  | 177.2 | 90
2026-W16 | 2026-04-25 | M02 | PAHINS01 | Eléctrica | 29 | 9.5 | 2.9 | 1.6 | 14 | 48.3 | No | 5 | 1 | 500111 | PM02 | PM - Servidor secundario |  | 174.4 | 90
2026-W16 | 2026-04-25 | M02 | PAHINS01 | Instrumentación | 39 | 14.9 | 11.6 | 1.7 | 28.2 | 72.3 | No | 4 | 2 | 500167 | PM02 | PM - Sensor temperatura TE0802 | 1000156 | 113.9 | 90
2026-W16 | 2026-04-25 | P01 | PASMEC01 | Mecánica | 34 | 10.7 | 2.1 | 0 | 12.8 | 37.6 | No | 7 | 4 | 500189 | PM01 | CM - Switch gear SAG 630 A, 6.9 Kv, 31.5 kA | 1003074 | 38.3 | 90
2026-W16 | 2026-04-25 | P01 | PASMEC01 | Eléctrica | 24 | 8.8 | 3.6 | 0.8 | 13.2 | 55 | No | 2 | 3 | 500145 | PM02 | PM - Transmisor presion agua PT0404 |  | 124.9 | 90
2026-W16 | 2026-04-25 | P01 | PASMEC01 | Instrumentación | 19 | 5.5 | 3.9 | 0.3 | 9.7 | 51.1 | No | 5 | 3 | 500013 | PM02 | PM - Válvula control drenaje pulpa HV1006 |  | 190.6 | 90
2026-W16 | 2026-04-25 | P01 | PASELE01 | Mecánica | 21 | 6.8 | 5.3 | 0.2 | 12.3 | 58.6 | No | 3 | 1 | 500094 | PM02 | PM - Switch baja presión descarga fluido térmico PSL3498 |  | 155.6 | 90
2026-W16 | 2026-04-25 | P01 | PASELE01 | Eléctrica | 22 | 7.6 | 4 | 2 | 13.6 | 61.8 | No | 3 | 1 | 500171 | PM02 | PM - Switch bajo nivel aceite LSL0253 | 1006805 | 116.1 | 90
2026-W16 | 2026-04-25 | P01 | PASELE01 | Instrumentación | 27 | 11.8 | 7.6 | 0.8 | 20.2 | 74.8 | No | 5 | 2 | 500112 | PM02 | PM - Hidrante/ Grifos FH0129 |  | 47.3 | 90
2026-W16 | 2026-04-25 | P01 | PASINS01 | Mecánica | 28 | 5 | 2.7 | 2.5 | 10.2 | 36.4 | No | 3 | 4 | 500168 | PM02 | PM - Gabinete RIO |  | 149.4 | 90
2026-W16 | 2026-04-25 | P01 | PASINS01 | Eléctrica | 34 | 6.7 | 9.8 | 0.2 | 16.7 | 49.1 | No | 4 | 1 | 500143 | PM02 | PM - Transmisor nivel solución barren LIT2787 |  | 74.8 | 90
2026-W16 | 2026-04-25 | P01 | PASINS01 | Instrumentación | 37 | 15.2 | 9.5 | 2.6 | 27.3 | 73.8 | No | 5 | 3 | 500108 | PM02 | PM - Motor eléctrico HY0036M1 |  | 111.1 | 90
2026-W16 | 2026-04-25 | P01 | PAHMEC01 | Mecánica | 30 | 9.4 | 7.6 | 1.7 | 18.7 | 62.3 | No | 5 | 4 | 500128 | PM01 | CM - Transmisor nivel solución barren LIT2787 | 1004513 | 134.6 | 90
2026-W16 | 2026-04-25 | P01 | PAHMEC01 | Eléctrica | 16 | 4.6 | 3.6 | 1.2 | 9.4 | 58.8 | No | 4 | 2 | 500057 | PM01 | CM - Bomba rotativa aceite PU0510 | 1001718 | 83.9 | 90
2026-W16 | 2026-04-25 | P01 | PAHMEC01 | Instrumentación | 28 | 11.8 | 3.6 | 2.2 | 17.6 | 62.9 | No | 7 | 3 | 500111 | PM02 | PM - Servidor secundario | 1002787 | 59.1 | 90
2026-W16 | 2026-04-25 | P01 | PAHELE01 | Mecánica | 16 | 7.1 | 4.1 | 1.3 | 12.5 | 78.1 | No | 6 | 3 | 500075 | PM02 | PM - Switch posición giro rastras ZS4377D |  | 110.2 | 90
2026-W16 | 2026-04-25 | P01 | PAHELE01 | Eléctrica | 36 | 6.2 | 7.7 | 0.3 | 14.2 | 39.4 | No | 3 | 3 | 500009 | PM02 | PM - Estanque diesel dia regeneración carbón |  | 109.7 | 90
2026-W16 | 2026-04-25 | P01 | PAHELE01 | Instrumentación | 31 | 5.7 | 3.4 | 0.6 | 9.7 | 31.3 | No | 2 | 3 | 500140 | PM02 | PM - Correa retorno pebbles |  | 60.8 | 90
2026-W16 | 2026-04-25 | P01 | PAHINS01 | Mecánica | 20 | 7.4 | 4.1 | 1.4 | 12.9 | 64.5 | No | 4 | 2 | 500185 | PM01 | CM - Motor eléctrico HY0036M1 | 1001691 | 42.8 | 90
2026-W16 | 2026-04-25 | P01 | PAHINS01 | Eléctrica | 19 | 7.9 | 2.1 | 0.7 | 10.7 | 56.3 | No | 5 | 2 | 500190 | PM01 | CM - Colector polvo horno fundición | 1006251 | 192.5 | 90
2026-W16 | 2026-04-25 | P01 | PAHINS01 | Instrumentación | 19 | 8.6 | 5.2 | 0.2 | 14 | 73.7 | No | 6 | 4 | 500042 | PM02 | PM - Válvula control salida precapa HV3102 |  | 78.4 | 90
2026-W16 | 2026-04-25 | P02 | PASMEC01 | Mecánica | 38 | 6.3 | 3.3 | 0.5 | 10.1 | 26.6 | No | 2 | 1 | 500139 | PM02 | PM - Hidrante/ Grifos FH0136 |  | 75.2 | 90
2026-W16 | 2026-04-25 | P02 | PASMEC01 | Eléctrica | 21 | 9.1 | 4 | 0.1 | 13.2 | 62.9 | No | 3 | 3 | 500095 | PM02 | PM - Bomba sumidero lixiviación |  | 78.4 | 90
2026-W16 | 2026-04-25 | P02 | PASMEC01 | Instrumentación | 35 | 17.3 | 8.9 | 2.5 | 28.7 | 82 | No | 5 | 4 | 500160 | PM02 | PM - Gabinete control Chancador Primario |  | 125.7 | 90
2026-W16 | 2026-04-25 | P02 | PASELE01 | Mecánica | 33 | 9.3 | 3.5 | 1.2 | 14 | 42.4 | No | 3 | 3 | 500085 | PM02 | PM - Gabinete servidor core switch 1 y commun |  | 162.6 | 90
2026-W16 | 2026-04-25 | P02 | PASELE01 | Eléctrica | 26 | 4.5 | 6.6 | 0.7 | 11.8 | 45.4 | No | 3 | 4 | 500056 | PM01 | CM - Gabinete control Merril Crowe & Refinación | 1005042 | 99.9 | 90
2026-W16 | 2026-04-25 | P02 | PASELE01 | Instrumentación | 34 | 16.4 | 8.5 | 2.2 | 27.1 | 79.7 | No | 5 | 2 | 500102 | PM02 | PM - Ciclo convertidor potencia MI0001SE | 1000192 | 33.6 | 90
2026-W16 | 2026-04-25 | P02 | PASINS01 | Mecánica | 34 | 16.9 | 8.3 | 3.3 | 28.5 | 83.8 | No | 7 | 1 | 500054 | PM01 | CM - Intercambiador calor calentamiento | 1001969 | 147.2 | 90
2026-W16 | 2026-04-25 | P02 | PASINS01 | Eléctrica | 39 | 6.7 | 10 | 1.3 | 18 | 46.2 | No | 6 | 2 | 500115 | PM01 | CM - Bomba vacío retorta | 1000817 | 161.3 | 90
2026-W16 | 2026-04-25 | P02 | PASINS01 | Instrumentación | 35 | 10.6 | 3.6 | 2.3 | 16.5 | 47.1 | No | 6 | 3 | 500149 | PM02 | PM - Indicador presión aceite PI1315 |  | 81.3 | 90
2026-W16 | 2026-04-25 | P02 | PAHMEC01 | Mecánica | 31 | 13.6 | 7.9 | 2 | 23.5 | 75.8 | No | 2 | 3 | 500063 | PM01 | CM - Válvula control entrada solucion barren FV2314 | 1000871 | 74.7 | 90
2026-W16 | 2026-04-25 | P02 | PAHMEC01 | Eléctrica | 34 | 14.5 | 6.7 | 0 | 21.2 | 62.4 | No | 5 | 1 | 500156 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 39.2 | 90
2026-W16 | 2026-04-25 | P02 | PAHMEC01 | Instrumentación | 27 | 12.8 | 2.2 | 2.1 | 17.1 | 63.3 | No | 5 | 1 | 500006 | PM02 | PM - Válvula control entrada sol precipitado HV3185 |  | 26.9 | 90
2026-W16 | 2026-04-25 | P02 | PAHELE01 | Mecánica | 16 | 7.6 | 3.7 | 0.3 | 11.6 | 72.5 | No | 4 | 1 | 500028 | PM02 | PM - Válvula control succión agua fresca HV7808 |  | 97.8 | 90
2026-W16 | 2026-04-25 | P02 | PAHELE01 | Eléctrica | 23 | 8.6 | 5.9 | 1 | 15.5 | 67.4 | No | 5 | 1 | 500119 | PM01 | CM - Calefactor eléctrico HE0137 | 1020152 | 129.9 | 90
2026-W16 | 2026-04-25 | P02 | PAHELE01 | Instrumentación | 38 | 10.6 | 2.5 | 2.1 | 15.2 | 40 | No | 6 | 2 | 500068 | PM02 | PM - Tecle eléctrico tolva carbon |  | 169 | 90
2026-W16 | 2026-04-25 | P02 | PAHINS01 | Mecánica | 34 | 6.6 | 9.8 | 1.8 | 18.2 | 53.5 | No | 6 | 2 | 500177 | PM01 | CM - Intercambiador calor por aire CQ0007 | 1002106 | 37.9 | 90
2026-W16 | 2026-04-25 | P02 | PAHINS01 | Eléctrica | 36 | 6.6 | 2.1 | 1.2 | 9.9 | 27.5 | No | 7 | 4 | 500013 | PM02 | PM - Válvula control drenaje pulpa HV1006 | 1003360 | 53.2 | 90
2026-W16 | 2026-04-25 | P02 | PAHINS01 | Instrumentación | 23 | 11.5 | 6.4 | 0 | 17.9 | 77.8 | No | 4 | 2 | 500105 | PM02 | PM - Tablero SCI |  | 185.5 | 90
2026-W16 | 2026-04-26 | M01 | PASMEC01 | Mecánica | 33 | 6.1 | 5.4 | 1.2 | 12.7 | 38.5 | No | 4 | 1 | 500188 | PM01 | CM - Switch posición ZS1716 |  | 164.7 | 90
2026-W16 | 2026-04-26 | M01 | PASMEC01 | Eléctrica | 34 | 9.5 | 3.2 | 2.8 | 15.5 | 45.6 | No | 6 | 2 | 500186 | PM01 | CM - Tablero distribución instrumentación | 1005870 | 92 | 90
2026-W16 | 2026-04-26 | M01 | PASMEC01 | Instrumentación | 31 | 13.5 | 9.3 | 0.5 | 23.3 | 75.2 | No | 2 | 1 | 500104 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 135 | 90
2026-W16 | 2026-04-26 | M01 | PASELE01 | Mecánica | 38 | 16.9 | 7 | 1.6 | 25.5 | 67.1 | No | 6 | 1 | 500028 | PM02 | PM - Válvula control succión agua fresca HV7808 |  | 134.3 | 90
2026-W16 | 2026-04-26 | M01 | PASELE01 | Eléctrica | 33 | 13.6 | 9.7 | 2.6 | 25.9 | 78.5 | No | 7 | 1 | 500048 | PM01 | CM - Válvula control flujo aire secado FV4662 |  | 198.7 | 90
2026-W16 | 2026-04-26 | M01 | PASELE01 | Instrumentación | 31 | 7.9 | 4.3 | 2.8 | 15 | 48.4 | No | 4 | 2 | 500191 | PM01 | CM - Calefactor eléctrico estanque HE0112 |  | 58.7 | 90
2026-W16 | 2026-04-26 | M01 | PASINS01 | Mecánica | 34 | 16.9 | 2.7 | 2.9 | 22.5 | 66.2 | No | 3 | 3 | 500114 | PM01 | CM - Transmisor vibración VT0020A |  | 114.3 | 90
2026-W16 | 2026-04-26 | M01 | PASINS01 | Eléctrica | 33 | 14.1 | 3.1 | 1.4 | 18.6 | 56.4 | No | 6 | 4 | 500155 | PM02 | PM - Válvula control salida precapa HV3102 | 1002960 | 120.9 | 90
2026-W16 | 2026-04-26 | M01 | PASINS01 | Instrumentación | 33 | 4.6 | 7.3 | 3.3 | 15.2 | 46.1 | No | 2 | 1 | 500184 | PM01 | CM - Válvula control descarga agua filtrado HV4812 | 1006616 | 149.1 | 90
2026-W16 | 2026-04-26 | M01 | PAHMEC01 | Mecánica | 29 | 6.5 | 3.3 | 1 | 10.8 | 37.2 | No | 7 | 4 | 500119 | PM01 | CM - Calefactor eléctrico HE0137 |  | 64 | 90
2026-W16 | 2026-04-26 | M01 | PAHMEC01 | Eléctrica | 24 | 6.5 | 5.5 | 2.3 | 14.3 | 59.6 | No | 5 | 4 | 500025 | PM02 | PM - Válvula control succión agua filtrada HV4771A |  | 155.3 | 90
2026-W16 | 2026-04-26 | M01 | PAHMEC01 | Instrumentación | 22 | 6.3 | 2.1 | 0.1 | 8.5 | 38.6 | No | 2 | 1 | 500067 | PM02 | PM - Indicador presión aceite hidráulico PI4895E |  | 104.3 | 90
2026-W16 | 2026-04-26 | M01 | PAHELE01 | Mecánica | 22 | 6.5 | 6.3 | 1.4 | 14.2 | 64.5 | No | 2 | 1 | 500118 | PM01 | CM - Gabinete RIO | 1001306 | 156.3 | 90
2026-W16 | 2026-04-26 | M01 | PAHELE01 | Eléctrica | 24 | 4.5 | 4 | 2.1 | 10.6 | 44.2 | No | 5 | 1 | 500148 | PM02 | PM - Válvula control descarga sol rica HV2810 |  | 47.7 | 90
2026-W16 | 2026-04-26 | M01 | PAHELE01 | Instrumentación | 23 | 11.2 | 4.1 | 1.8 | 17.1 | 74.3 | No | 6 | 4 | 500010 | PM02 | PM - Tablero SCI | 1004248 | 177.9 | 90
2026-W16 | 2026-04-26 | M01 | PAHINS01 | Mecánica | 37 | 10.8 | 5.9 | 1.9 | 18.6 | 50.3 | No | 4 | 1 | 500005 | PM02 | PM - Válvula control succión agua fresca HV7808 | 1003355 | 103.8 | 90
2026-W16 | 2026-04-26 | M01 | PAHINS01 | Eléctrica | 26 | 8.1 | 5 | 2.6 | 15.7 | 60.4 | No | 7 | 3 | 500113 | PM01 | CM - Puerta enrollable Molienda | 1004556 | 159.1 | 90
2026-W16 | 2026-04-26 | M01 | PAHINS01 | Instrumentación | 26 | 5.4 | 5.5 | 0.6 | 11.5 | 44.2 | No | 6 | 2 | 500105 | PM02 | PM - Tablero SCI |  | 78.9 | 90
2026-W16 | 2026-04-26 | M02 | PASMEC01 | Mecánica | 20 | 7.9 | 3.1 | 0.9 | 11.9 | 59.5 | No | 7 | 2 | 500026 | PM02 | PM - Estanque almacenamiento aceite hidráulico TK0088 |  | 83.7 | 90
2026-W16 | 2026-04-26 | M02 | PASMEC01 | Eléctrica | 20 | 8.1 | 5 | 0.3 | 13.4 | 67 | No | 4 | 4 | 500095 | PM02 | PM - Bomba sumidero lixiviación |  | 184.2 | 90
2026-W16 | 2026-04-26 | M02 | PASMEC01 | Instrumentación | 17 | 7.4 | 4.6 | 0.4 | 12.4 | 72.9 | No | 3 | 4 | 500140 | PM02 | PM - Correa retorno pebbles |  | 109.7 | 90
2026-W16 | 2026-04-26 | M02 | PASELE01 | Mecánica | 31 | 5.3 | 4.9 | 1.4 | 11.6 | 37.4 | No | 3 | 3 | 500087 | PM02 | PM - Línea agua sell 3700-5476-AA1A-3"-WGS-ET |  | 104.3 | 90
2026-W16 | 2026-04-26 | M02 | PASELE01 | Eléctrica | 24 | 6.8 | 3 | 0.8 | 10.6 | 44.2 | No | 4 | 3 | 500112 | PM02 | PM - Hidrante/ Grifos FH0129 |  | 67.3 | 90
2026-W16 | 2026-04-26 | M02 | PASELE01 | Instrumentación | 21 | 6.5 | 5.3 | 1.9 | 13.7 | 65.2 | No | 6 | 2 | 500089 | PM02 | PM - Transmisor presión salida sol barren PIT3241 |  | 81.5 | 90
2026-W16 | 2026-04-26 | M02 | PASINS01 | Mecánica | 37 | 6.1 | 3.5 | 0.6 | 10.2 | 27.6 | No | 4 | 2 | 500131 | PM01 | CM - Calefactor eléctrico estanque HE0012 | 1005081 | 52.3 | 90
2026-W16 | 2026-04-26 | M02 | PASINS01 | Eléctrica | 37 | 4.6 | 6.2 | 1.6 | 12.4 | 33.5 | No | 7 | 4 | 500084 | PM02 | PM - Motor eléctrico HY0001M1 |  | 83.9 | 90
2026-W16 | 2026-04-26 | M02 | PASINS01 | Instrumentación | 29 | 5.9 | 6 | 0.3 | 12.2 | 42.1 | No | 5 | 3 | 500190 | PM01 | CM - Colector polvo horno fundición | 1004980 | 199.1 | 90
2026-W16 | 2026-04-26 | M02 | PAHMEC01 | Mecánica | 25 | 11.4 | 5.7 | 1.6 | 18.7 | 74.8 | No | 5 | 2 | 500038 | PM02 | PM - Switch bajo flujo aire FSL1357A |  | 41 | 90
2026-W16 | 2026-04-26 | M02 | PAHMEC01 | Eléctrica | 16 | 5.6 | 4.8 | 0.2 | 10.6 | 66.2 | No | 5 | 1 | 500110 | PM02 | PM - Válvula control entrada pulpa HV1706 |  | 36 | 90
2026-W16 | 2026-04-26 | M02 | PAHMEC01 | Instrumentación | 32 | 13.2 | 8.5 | 2.5 | 24.2 | 75.6 | No | 7 | 2 | 500046 | PM02 | PM - Gabinete servidor core switch 1 y commun |  | 112.5 | 90
2026-W16 | 2026-04-26 | M02 | PAHELE01 | Mecánica | 39 | 12.1 | 2.1 | 1.9 | 16.1 | 41.3 | No | 5 | 4 | 500121 | PM01 | CM - Calefactor eléctrico edificio | 1002118 | 59.5 | 90
2026-W16 | 2026-04-26 | M02 | PAHELE01 | Eléctrica | 35 | 16 | 4.1 | 1.3 | 21.4 | 61.1 | No | 7 | 1 | 500113 | PM01 | CM - Puerta enrollable Molienda | 1001327 | 180.1 | 90
2026-W16 | 2026-04-26 | M02 | PAHELE01 | Instrumentación | 28 | 12.9 | 5 | 1.4 | 19.3 | 68.9 | No | 7 | 1 | 500091 | PM02 | PM - Estanque diesel dia regeneración carbón |  | 69.8 | 90
2026-W16 | 2026-04-26 | M02 | PAHINS01 | Mecánica | 23 | 8.9 | 3.5 | 0.4 | 12.8 | 55.7 | No | 6 | 1 | 500104 | PM02 | PM - Hidrante/ Grifos FH0138 |  | 128.5 | 90
2026-W16 | 2026-04-26 | M02 | PAHINS01 | Eléctrica | 28 | 6.7 | 4.6 | 2 | 13.3 | 47.5 | No | 7 | 1 | 500040 | PM02 | PM - Mesa rodillos |  | 115.8 | 90
2026-W16 | 2026-04-26 | M02 | PAHINS01 | Instrumentación | 17 | 5.7 | 4.7 | 1.6 | 12 | 70.6 | No | 6 | 1 | 500089 | PM02 | PM - Transmisor presión salida sol barren PIT3241 |  | 108.7 | 90
2026-W16 | 2026-04-26 | P01 | PASMEC01 | Mecánica | 28 | 12.2 | 5.5 | 0.6 | 18.3 | 65.4 | No | 2 | 2 | 500061 | PM01 | CM - Transmisor presión aceite PIT4875 |  | 82.4 | 90
2026-W16 | 2026-04-26 | P01 | PASMEC01 | Eléctrica | 27 | 8.5 | 7.1 | 1.8 | 17.4 | 64.4 | No | 5 | 3 | 500122 | PM01 | CM - Carro mantención regeneración carbon | 1000311 | 59.1 | 90
2026-W16 | 2026-04-26 | P01 | PASMEC01 | Instrumentación | 39 | 10.9 | 4.9 | 3.8 | 19.6 | 50.3 | No | 5 | 1 | 500037 | PM02 | PM - Sirena YA1151 | 1001261 | 108.2 | 90
2026-W16 | 2026-04-26 | P01 | PASELE01 | Mecánica | 25 | 8.6 | 2.8 | 1.4 | 12.8 | 51.2 | No | 7 | 3 | 500102 | PM02 | PM - Ciclo convertidor potencia MI0001SE |  | 90.2 | 90
2026-W16 | 2026-04-26 | P01 | PASELE01 | Eléctrica | 33 | 14.9 | 3.7 | 2.1 | 20.7 | 62.7 | No | 3 | 2 | 500073 | PM02 | PM - Válvula control sol barren a estanque HV3266 |  | 26.6 | 90
2026-W16 | 2026-04-26 | P01 | PASELE01 | Instrumentación | 30 | 12.4 | 4.8 | 2.6 | 19.8 | 66 | No | 3 | 3 | 500002 | PM02 | PM - Chute carbónHO0068 |  | 24 | 90
2026-W16 | 2026-04-26 | P01 | PASINS01 | Mecánica | 16 | 5.2 | 3.6 | 1.5 | 10.3 | 64.4 | No | 4 | 2 | 500188 | PM01 | CM - Switch posición ZS1716 | 1005899 | 157 | 90
2026-W16 | 2026-04-26 | P01 | PASINS01 | Eléctrica | 39 | 9.8 | 10 | 0.7 | 20.5 | 52.6 | No | 5 | 3 | 500108 | PM02 | PM - Motor eléctrico HY0036M1 | 1001626 | 165.2 | 90
2026-W16 | 2026-04-26 | P01 | PASINS01 | Instrumentación | 20 | 5.8 | 2.5 | 0.8 | 9.1 | 45.5 | No | 3 | 2 | 500123 | PM01 | CM - Válvula control flujo sol barren FV5601 |  | 135.9 | 90
2026-W16 | 2026-04-26 | P01 | PAHMEC01 | Mecánica | 27 | 4.1 | 5.3 | 1.5 | 10.9 | 40.4 | No | 6 | 1 | 500192 | PM01 | CM - Calefactor eléctrico edificio |  | 111.1 | 90
2026-W16 | 2026-04-26 | P01 | PAHMEC01 | Eléctrica | 35 | 10.4 | 4.3 | 0.2 | 14.9 | 42.6 | No | 7 | 3 | 500182 | PM01 | CM - Transmisor nivel agua potable LIT0060 | 1004702 | 29.5 | 90
2026-W16 | 2026-04-26 | P01 | PAHMEC01 | Instrumentación | 26 | 8.8 | 5.6 | 2.6 | 17 | 65.4 | No | 6 | 4 | 500103 | PM02 | PM - Tablero SCI |  | 31.9 | 90
2026-W16 | 2026-04-26 | P01 | PAHELE01 | Mecánica | 26 | 5.7 | 4 | 1.6 | 11.3 | 43.5 | No | 3 | 2 | 500184 | PM01 | CM - Válvula control descarga agua filtrado HV4812 | 1005367 | 65.2 | 90
2026-W16 | 2026-04-26 | P01 | PAHELE01 | Eléctrica | 20 | 5.6 | 4.8 | 0.3 | 10.7 | 53.5 | No | 3 | 3 | 500031 | PM02 | PM - Celosía XM0114 | 1001612 | 187.8 | 90
2026-W16 | 2026-04-26 | P01 | PAHELE01 | Instrumentación | 36 | 5.5 | 10.5 | 2.1 | 18.1 | 50.3 | No | 2 | 3 | 500129 | PM01 | CM - Gabinete control Chancador Primario | 1004648 | 76.1 | 90
2026-W16 | 2026-04-26 | P01 | PAHINS01 | Mecánica | 20 | 4.4 | 5.6 | 1.7 | 11.7 | 58.5 | No | 7 | 2 | 500101 | PM02 | PM - Subestación unitaria |  | 180.4 | 90
2026-W16 | 2026-04-26 | P01 | PAHINS01 | Eléctrica | 28 | 10.6 | 7.9 | 0.7 | 19.2 | 68.6 | No | 4 | 4 | 500065 | PM02 | PM - Muestreador alimentación filtros | 1006838 | 185.7 | 90
2026-W16 | 2026-04-26 | P01 | PAHINS01 | Instrumentación | 38 | 18.3 | 9.9 | 2.3 | 30.5 | 80.3 | No | 2 | 2 | 500170 | PM02 | PM - Switch posición ZS0038A |  | 108.5 | 90
2026-W16 | 2026-04-26 | P02 | PASMEC01 | Mecánica | 23 | 8 | 4.2 | 1.8 | 14 | 60.9 | No | 7 | 1 | 500022 | PM02 | PM - Unidad re-potabilizadora agua |  | 129.7 | 90
2026-W16 | 2026-04-26 | P02 | PASMEC01 | Eléctrica | 20 | 4.2 | 4.3 | 1.8 | 10.3 | 51.5 | No | 7 | 3 | 500008 | PM02 | PM - Bomba precipitado | 1005905 | 92.9 | 90
2026-W16 | 2026-04-26 | P02 | PASMEC01 | Instrumentación | 20 | 9.9 | 4 | 1.1 | 15 | 75 | No | 6 | 2 | 500017 | PM02 | PM - Indicador presión agua PI0423 |  | 31.7 | 90
2026-W16 | 2026-04-26 | P02 | PASELE01 | Mecánica | 22 | 7.8 | 6.3 | 0.9 | 15 | 68.2 | No | 5 | 2 | 500141 | PM02 | PM - Lava ojos emergencia | 1004945 | 196 | 90
2026-W16 | 2026-04-26 | P02 | PASELE01 | Eléctrica | 17 | 4.1 | 3.5 | 1.5 | 9.1 | 53.5 | No | 3 | 3 | 500078 | PM02 | PM - Unidad aire acondicionado |  | 192.1 | 90
2026-W16 | 2026-04-26 | P02 | PASELE01 | Instrumentación | 16 | 5.5 | 2.4 | 0.6 | 8.5 | 53.1 | No | 5 | 2 | 500163 | PM02 | PM - Válvula control salida precapa HV3102 |  | 180.2 | 90
2026-W16 | 2026-04-26 | P02 | PASINS01 | Mecánica | 32 | 5 | 9 | 1.5 | 15.5 | 48.4 | No | 6 | 4 | 500072 | PM02 | PM - Válvula control flujo entrada agua rechazo FV3576 |  | 133.3 | 90
2026-W16 | 2026-04-26 | P02 | PASINS01 | Eléctrica | 38 | 6.8 | 7.1 | 0.9 | 14.8 | 38.9 | No | 2 | 3 | 500054 | PM01 | CM - Intercambiador calor calentamiento |  | 90.3 | 90
2026-W16 | 2026-04-26 | P02 | PASINS01 | Instrumentación | 38 | 7.4 | 3.8 | 2.3 | 13.5 | 35.5 | No | 4 | 4 | 500013 | PM02 | PM - Válvula control drenaje pulpa HV1006 |  | 122 | 90
2026-W16 | 2026-04-26 | P02 | PAHMEC01 | Mecánica | 39 | 12.6 | 4.8 | 3.2 | 20.6 | 52.8 | No | 6 | 2 | 500163 | PM02 | PM - Válvula control salida precapa HV3102 | 1005078 | 194.7 | 90
2026-W16 | 2026-04-26 | P02 | PAHMEC01 | Eléctrica | 35 | 5.3 | 3.1 | 0.2 | 8.6 | 24.6 | No | 5 | 4 | 500058 | PM01 | CM - Sensor temperatura aire TS4591 | 1020125 | 89.7 | 90
2026-W16 | 2026-04-26 | P02 | PAHMEC01 | Instrumentación | 27 | 8.2 | 4.2 | 0 | 12.4 | 45.9 | No | 5 | 4 | 500162 | PM02 | PM - Tecle bomba sumergible lixiviación | 1003077 | 80.3 | 90
2026-W16 | 2026-04-26 | P02 | PAHELE01 | Mecánica | 27 | 6.9 | 3.7 | 1.1 | 11.7 | 43.3 | No | 5 | 2 | 500020 | PM02 | PM - Cajón (Futuro) |  | 111.4 | 90
2026-W16 | 2026-04-26 | P02 | PAHELE01 | Eléctrica | 37 | 13.1 | 9.3 | 1.7 | 24.1 | 65.1 | No | 3 | 1 | 500059 | PM01 | CM - Mezclador floculante | 1006290 | 165.9 | 90
2026-W16 | 2026-04-26 | P02 | PAHELE01 | Instrumentación | 19 | 7.9 | 3.6 | 0.8 | 12.3 | 64.7 | No | 3 | 3 | 500132 | PM02 | PM - Válvula control agua sello HV2723 |  | 51.5 | 90
2026-W16 | 2026-04-26 | P02 | PAHINS01 | Mecánica | 31 | 14.2 | 6.9 | 2 | 23.1 | 74.5 | No | 6 | 2 | 500014 | PM02 | PM - Válvula control descarga agua filtrado HV4824 |  | 143 | 90
2026-W16 | 2026-04-26 | P02 | PAHINS01 | Eléctrica | 28 | 7.2 | 3.4 | 1.7 | 12.3 | 43.9 | No | 4 | 1 | 500135 | PM02 | PM - Compresor de aire neumático |  | 151.4 | 90
2026-W16 | 2026-04-26 | P02 | PAHINS01 | Instrumentación | 33 | 8.4 | 9.1 | 1.7 | 19.2 | 58.2 | No | 6 | 1 | 500119 | PM01 | CM - Calefactor eléctrico HE0137 | 1004671 | 57.7 | 90